- Supply of lines materials as per BOQ and drawing of the same shall be provided separately.

- Construction of Normal Foundation at New Loc. No. 95 & erection of 01 no. 400 kV D/C (WZ-IV) Twin DB+6 Tower, erection of 01 no. 400 kV D/C (WZ-IV) Twin DC+9 Tower at new Pile Location No. – 94 of 400 kV D/C Binaguri -New Purnea T/L.

- De-stringing of existing conductors from existing Tower Loc. No. 93 to existing Tower Loc 98 of 400 kV D/C Binaguri -New Purnea T/L.

- Providing necessary Back–stay at Tower Loc No.-93 and Loc No. 98 (Existing towers).

- Dismantling of 02 Nos. of 400 kV D/C (WZ-IV) Twin Tower at Loc No- 94 (DA+0) & Loc. No. 95 (DA+3) of 400 kV D/C Binaguri -New Purnea T/L.

- Re-stringing of conductor between Tower No 93 (DC+6) to new Pile Location 94 (DC+9), New Tower No 94 (DC+9) to new Loc. No. 95 (DB+6) and in between new Loc. No. 95 (DB+6) to existing Tower No. 98 (DC+0) of 400 kV D/C Binaguri -New Purnea T/L.

- Providing Earthing in New Pile Location Tower No-94 & No. 95 complying with POWERGRID SFQP & Drawing.

- Erection & Stringing gang shall consist of sufficient trained manpower in order to complete the work within shortest possible time from the date of S/D of the line. The gangs deployed shall be equipped with sufficient/suitable T&P for carrying out erection & stringing in 400kV Double circuit Tower at River crossing location.

- Work shall be carried out strictly as per POWERGRID Safety Rules & Regulations and as per instruction of EIC.

- Necessary WC Policy/Insurance shall be taken by the agency for all engaged manpower which shall be reimbursed as per actual.

- The work shall be carried out on banks of Parman River and as such water may be encountered in the river during tower erection/dismantling and conductor de-stringing & re-stringing work. Party shall have to take all necessary measures keeping in mind the same in order to complete the work on-time.

- No conductor joint is acceptable in River Crossing Span and as such existing conductor shall have to be interchanged in order to utilize the existing conductor to the maximum. However, if any additional conductor required same shall be judiciously used in order to minimize the damage of the existing conductors as per discussion with EIC.

- Party shall have to dismantle the tower in re-usable condition, and the Dismantled Tower parts have to be transported back to POWERGRID Store, segregated and stacked properly.

- Party shall have to dismantle the Conductor, Insulator & Hardware fittings in re-usable condition and the Dismantled Conductor, Insulator & Hardware fittings have to be transported back to POWERGRID Store, segregated and stacked properly.

- Proper Safety PPE’s and T&P’s shall be available with gangs without which gangs will not be allowed to work & if safety PPE, T&P’s are taken from POWERGRID on Loan basis, then suitable recovery of the same shall be done from Party invoice as per POWERGRID policy.

- Fooding, lodging & required vehicle for movement of fitters shall be in the scope of the agency.

- No idling charges shall be payable to the agency in case of deny of any shutdown approval by ERLDC.

- The new Towers, Conductor and H/W etc required for erection have to be lifted from POWERGRID nearest store which shall be in the scope of contractor.

- The agency shall be capable of mobilizing gangs with T&P’s within 7(Seven) days after communication by EIC.

- Party shall have to hand over all the dismantled materials, unused materials at POWERGRID store by taking handing over receipt from concerned store within 7 days after Completion of work.

- Risk and Cost: During the period of the work and during defect liability period, if the contractor fails to rectify any defect pointed out, the same shall be carried out by POWERGRID at the risk and cost and suitable amount shall be recovered from amount payable to the contractor.

- First Aid: To deal with any emergency /accidental eventualities at the work site, the contractor shall make necessary arrangements, such as services of ambulance etc., for transportation to hospital at his own cost.

- Insurance:

1) The contractor shall take necessary WCI policy for the works and the premium amount shall not be reimbursed.

2) EAR/ CAR policy shall be taken by the contractor @ 100% of the contact prices plus value of POWERGRID supplied material. The premium amount shall be reimbursed by POWERGRID subjected that the insurance premium taken should be the lowest by comparing amongst minimum of 3 (three) insurance agencies.