## Proposed L1
L1 SCHEDULE
Sl No | Description of Activity | Period from date of LOA (in days)
1 | Date of Notification of award(NOA) shall be treated as zero date/Commencement date | Commencment | Completion
2 | Contract Agreement, signing and submission of CPG
a | Site Handing over | 0 | 5
b | Labour licence, stuatory compliances lnsurance. | 5 | 10
c | Source approval of materials including all testing as per SFQP requirement to start the works | 10 | 30
3 | Repairing of 4 DC hall roof and walls at ± 800 kV Agra HVDC station |  |  | 360
a | DC hall Roof/Corner: Fixing of corner flashing with POP Riveting & Self Drilling screws (without Flashing). | 30 | 90
b | DC Hall Roof: Fixing full ridge flashing with Sheet, POP rivets size 200/8 (with Flashing). | 90 | 120
c | DC Hall Wall: Both side wall cladding, inner & outer repair work with boom lift. DC hall 1,2,3 and 4 as per requirement | 120 | 210
d | DC Hall Roof: DC hall 1,2,3 and 4 roof sheet replacement with material (PPGI Sheet and self drilling screws) | 210 | 270
e | DC Hall Roof: Replacement of self typing screws 200/8 with cylone washer type screws on DC Hall Roof DC hall 1,2,3 and 4 roof top. | 90 | 330
f | DC hall Roof Top hand rail repair for 1,2,3 and 4. | 300 | 330
g | Balance works | 330 | 360
The Contractor/bidder shall submit L-2 schedule showing the above activities /milestone keeping the overall comnpletion period unchanged.Minor changes in the individual activity schedule are permissible which the contractor /bidder may suggest considering the volume of work as per their wisdom

## Contractor submission
L2 SCHEDULE PROPOSED BY CONTRACTOR
Sl No | Description of Activity | Period from date of LOA (in days)
1 | Date of Notification of award(NOA) shall be treated as zero date/Commencement date | Commencment | Completion
2 | Contract Agreement, signing and submission of CPG
a | Site Handing over
b | Labour licence, stuatory compliances lnsurance.
c | Source approval of materials including all testing as per SFQP requirement to start the works
3 | Repairing of 4 DC hall roof and walls at ± 800 kV Agra HVDC station
a | DC hall Roof/Corner: Fixing of corner flashing with POP Riveting & Self Drilling screws (without Flashing).
b | DC Hall Roof: Fixing full ridge flashing with Sheet, POP rivets size 200/8 (with Flashing).
c | DC Hall Wall: Both side wall cladding, inner & outer repair work with boom lift. DC hall 1,2,3 and 4 as per requirement
d | DC Hall Roof: DC hall 1,2,3 and 4 roof sheet replacement with material (PPGI Sheet and self drilling screws)
e | DC Hall Roof: Replacement of self typing screws 200/8 with cylone washer type screws on DC Hall Roof DC hall 1,2,3 and 4 roof top.
f | DC hall Roof Top hand rail repair for 1,2,3 and 4.
g | Balance works
The Contractor/bidder shall submit L-2 schedule showing the above activities /milestone keeping the overall comnpletion period unchanged.Minor changes in the individual activity schedule are permissible which the contractor /bidder may suggest considering the volume of work as per their wisdom