Framework for Assessment of Contractor’s Execution Performance (FACEp)

POWERGRID has instituted a structured and data driven Framework for Assessment of Contractor’s Execution Performance (FACEp) in its ongoing Contracts on a continuous basis. The salient aspects and detailed methodology for the same are as follows:

- Scope

The FACEp framework is applicable for the following categories of packages :

| Sl No | Type of Packages | Packages covered |
| --- | --- | --- |
| 1. | Supply cum installation or Supply cum Supervision packages | - Transformers - Reactors |
| 2. | Engineering, Procurement and Construction (EPC) packages | - Transmission Lines, - AIS Substations & AIS Substation Extension packages |

- FACEp – Methodology

- Weighted Activity Performance Analysis for Contractors:

Activity-wise performance data shall be compiled and aggregated across all ongoing contracts of a given Contractor.

- Total Scheduled Completion of quantity as envisaged in the L2 (A)

- Total Actual Completion of quantity attained by the Contractor (B)

- Adjusted Scheduled Completion of quantity: Delays (C), if any, arising from reasons not attributable to the Contractor – such as Force majeure events or non-availability of work fronts shall be deducted from the corresponding L2 schedule values and shall be the Adjusted Scheduled Completion.

- Calculation of Achievement Percentage: Based on the Adjusted scheduled quantities and Actual completed quantities, Activity wise percentage achievements shall be computed for each Contractor using the formula:

Achievement (%) = Actual Completed QuantityAdjusted Scheduled Quantity x 100

- Weightage Based Consolidation: Each activity has been assigned a predefined weight (D), based on its criticality and work content. Using these weights, a weighted average performance score shall be calculated to determine the contractor’s overall execution performance for that category of contract.

- In case, cumulative adjusted scheduled value (A-C) of a particular activity is zero, the entire score against the activity shall be considered for evaluation.

  - Supply cum installation or Supply cum Supervision contracts (Transformers, Reactors):

| Sl. No. | Critical activities | Scheduled (A) | Completed (B) | Delays (C) | Weight (D) |
| --- | --- | --- | --- | --- | --- |
|  | Supply of Reactor / Transformer, (Nos) |  |  |  | 50% |
|  | Supply of Other material (Bushings, Transformer Oil auxiliary materials (Sets) ** |  |  |  | 20% |
|  | Erection/ commissioning of Reactor / Transformer, (Nos) |  |  |  | 30% |
| Overall Weighted Average Score in Percentage |  |  | i=13 [(Bi*Di)/(Ai-Ci)] |  |  |

**	Complete Bushing required for One physical unit to be counted as One Set, Complete Oil required for one physical unit to be counted as one set, Complete Auxiliary material for one physical unit to be counted as one Set.

  - Transmission Line-based EPC contracts:

| Sl. No. | Critical activities | Scheduled (A) | Completed (B) | Delays (C) | Weight (D) |
| --- | --- | --- | --- | --- | --- |
|  | Foundation (Nos.) |  |  |  | 40% |
|  | Tower Erection (Nos.) |  |  |  | 30% |
|  | Stringing (ckm) |  |  |  | 30% |
| Overall Weighted Average Score in Percentage |  |  | i=13 [(Bi*Di)/(Ai-Ci)] |  |  |

  - AIS Substation based EPC contracts:

| Sl. No. | Critical activities | Scheduled (A) | Completed (B) | Delays (C) | Weight (D) |
| --- | --- | --- | --- | --- | --- |
|  | Supply of tower and equipment Structure (MT) |  |  |  | 20% |
|  | Supply of Equipment [CT, CB, CVT, LA, WT, Isolator, SAS&CRP, PLCC/Communication (Nos) ** |  |  |  | 20% |
|  | Foundations (only for Firewall, Gantry Tower, Transformer, Reactor (Nos) |  |  |  | 20% |
|  | Equipment Erection [CT, CB, CVT, LA, WT, Isolator, SAS&CRP (Nos) ** |  |  |  | 20% |
|  | Cable Laying and Termination in % |  |  |  | 20% |
| Overall Weighted Average Score in Percentage |  |  | i=15 [(Bi*Di)/(Ai-Ci)] |  |  |

**	3 phase set of CBs to be counted as three numbers, 3ph set of Isolators to be counted as one number, each Bay and Bus set of SAS&CRP shall be counted as one Number, each line set of one end of PLCC/communication shall be counted as one Number.  For other equipment each phase of equipment to be counted as one number

- FACEp – Salient aspects of Assessment

- The Contractor shall be evaluated and treated separately for each category (i.e. supply and Installation/ supply-cum-supervision Transformer/ Reactor contracts, transmission line EPC contracts, and AIS substation EPC contracts).

- Assessment shall be conducted on a Quarterly basis with following considerations:

    - Schedule quantity and Actual quantity each shall be the cumulative quantities as on last day of the Quarter.

    - Front non-availability in a quarter shall be based on the Average non-availability of front as on the last day of each month in the quarter.

In instances where there is a sudden release of working fronts under any package for certain activities, the maximum adjustment allowed for such front release shall be capped at 3 months’ work of maximum L2 quantities for the purpose of performance calculation. This is in order to prevent disproportionate penalty owing to bulk working front releases in a short time window.

- Corrective Action Framework

- Corrective Action:

Based on the outcome of the FACEp, the following actions would be taken:

| Sl No | Outcome as per FACEp | Action |
| --- | --- | --- |
| 1 | 75% and above | Nil. |
| 2 | For scores < 75% and >= 60% | Performance of such contractors shall be considered as marginal, and a letter advising the Contractor to take urgent steps to improve their performance shall be issued. Contractor will be encouraged to submit a Performance Improvement Plan (PIP) within seven (07) calendar days, outlining remedial actions, and resource augmentation commitments. Failure to submit or adhere to the PIP in coming quarter may lead to escalation in the next level management review of respective Contractors. |
| 3 | For scores below 60% | Action as per Sl.no. 02. Additionally, Bids submitted by the Contractor shall be treated as non-responsive in the relevant category till the next assessment cycle. |

- Procedure:

- For the above analysis, only the Corporate awarded packages shall be considered. The applicability of its outcome shall also be limited to Corporate Centre packages (including Consultancy Packages).

- The corporate awarded ongoing contracts in which any of the elements is yet to be ready for commissioning on the first date of concerned quarter; shall be included in the performance evaluation process for the contractor.

- The outcome of the report shall be applicable till the next assessment cycle report comes.

- The Performance Assessment shall not restrict any other remedies to Employer provided in the contract.

*************