| Volume-I; Conditions of Contract |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Clause No. 6.4, ITB (BDS), Section-III, Volume-I of the bidding documents | The Bidder’s designated representative(s) is/are invited to attend a pre-bid meeting, which, if convened, will take place at the venue and time stipulated in the BDS………………… | Venue, date and time for Pre-bid Meeting: Request to conduct the pre bid meet through video conferencing considering the prevailing circumstances. | The meeting was conducted through Video Conferencing on Microsoft Teams. Please refer Amendment No.-01 dated 28/11/2020 in this regard. |
|  | GCC 1.1 (e), Section IV: General Conditions of Contract | “Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the SCC) have been completed operationally and structurally and put in a tight and clean condition and that all works in respect of precommissioning of the Facilities (or a specific part thereof where specific parts are specified in the SCC) has been completed (wherever required, as per Technical Specifications) and Commissioning followed by Trail – Operation has been completed, as provided in GCC Sub-Clause 20.1 (Completion of Facilities) hereof. | "Bidder requests for the modification of said clause as suggested below: Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the SCC) have been completed operationally and structurally and put in a tight and clean condition and that all works in respect of pre-commissioning of the Facilities (or a specific part thereof where specific parts are specified in the SCC) has been completed (wherever required, as per Technical Specifications) and Commissioning followed by Trial – Operation has been completed, as provided in GCC Sub-Clause 20.1 (Completion of Facilities) hereof. Furthermore, the facility shall be deemed to have been takeover and the Employer shall issue a TOC if the Facilities is put to commercial use by the Employer. The Employer is also bound to accept commencement of defect liability period from the said deemed date. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 2.8, Section IV: General Conditions of Contract | 2.8 Independent Contractor The Contractor shall be an independent contractor performing the Contract. The Contract does not create any agency, partnership, joint venture or other joint relationship between the parties hereto. Subject to the provisions of the Contract, the Contractor shall be solely responsible for the manner in which the Contract is performed. All employees, representatives or Subcontractors engaged by the Contractor in connection with the performance of the Contract shall be under the complete control of the Contractor and shall not be deemed to be employees of the Employer, and nothing contained in the Contract or in any subcontract awarded by the Contractor shall be construed to create any contractual relationship between any such employees, representatives or Subcontractors and the Employer. | Please modify the paragraph as below: Subject to the provisions of the Contract, the Contractor shall be solely responsible for the manner in which the Contract is performed, as far as Contractor´s explicit obligations are concerned. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 3.3, Section IV: General Conditions of Contract | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | Bidder requests for the modification of said clause as suggested below: The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of spare parts, or their functionally equivalent, required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 05 years from Completion of the Facilities....... | Provisions of the Bidding Documents shall remain unchanged. |
|  | Section IV: General Conditions of Contract GCC 3.4 - Scope of Facilities | The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: - The Contractor shall send advance notification to the Employer of the pending termination, with 2 (two) years time to permit the Employer to procure needed requirements, and - Following such termination, the Contractor shall furnish at no cost to the Employer the blueprints, drawings and specification of the spare parts, if requested. | Bidder requests for the modification of said clause as suggested below: The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: (i) The Contractor shall send advance notification to the Employer of the pending termination, with one (1) year 2 (two) years time to permit the Employer to procure needed requirements, and (ii) Following such termination, the Contractor shall furnish at no cost to the Employer the relevant information/ documents and specification of the spare parts from third party, information/documents and specifications of the spare parts shall be furnished by the Contractor to the extent that such documents are available to the Contractor. Such specification / documentation shall be utilized by the Employer only for the purpose of O & M & future procurement of functionally equivalent spares Specifications of the functionally equivalent spare parts shall be furnished by the Contractor to the extent that such documents are available to the Contractor. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 5.3, Section – IV, General Conditions of Contract [Contractor's Responsibilities] | The Contractor shall acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located that are necessary for the performance of the Contract, including, without limitation, visas for the Contractor’s and Subcontractor’s personnel and entry permits for all imported Contractor’s Equipment. The Contractor shall acquire all other permits, approvals and/or licenses that are not the responsibility of the Employer under GCC Sub-Clause 6.3 hereof and that are necessary for the performance of the Contract. | Please modify the provision as below: The Contractor shall only acquire in its name all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located , that are not otherwise in the responsibility of the Contractor and further described in Annexure to the Contract, that are necessary for the performance of the Contract, including, without limitation, visas for the Contractor‟s and Subcontractor‟s personnel and entry permits for all imported Contractor‟s Equipment. Right of Way shall be in Employer scope. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 5.6, Section IV : General Conditions of Contract [Contractor's Responsibility] | The Contractor shall permit the Employer to inspect the Contractor’s accounts and records relating to the performance of the Contractor. | Bidder requests that; 1. Inspection of accounts and records would be limited to the performance of this Contract only. 2. The auditors appointed would be an independent, internationally certified public accountants acceptable to both Customer and Contractor. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 6.2, Section – IV, General Conditions of Contract, [Employer's responsibilities] | The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the corresponding Appendix – 6 (Scope of Works and Supply by the Employer) to the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix. | Please confirm that the site are available for all locations, duly secured with permanent boundary wall and security gate. Please further confirm that in case of any delay in acquiring and providing legal and physical possession of the site and its access, and for providing possession of and access to all other areas reasonably required for the proper execution of the contract, including all requisite rights of way, as applicable, the employer shall pay reasonable cost incurred by the contractor along with suitable time extension. | Provisions of the Bidding Documents are amply clear. Employer and Bidder/Contractor shall discharge their responsibilities in line with the relevant provisions of the Bidding Documents. |
|  | GCC 6.3, Section – IV, General Conditions of Contract, [Employer's responsibilities] | The Employer shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located which such authorities or undertakings require the Employer to obtain them in the Employer's name, are necessary for the execution of the Contract (they include those required for the performance by both the Contractor and the Employer of their respective obligations under the Contract), including those specified in Appendix 6 (Scope of Works and Supply by the Employer) to the Contract Agreement. | Please confirm that in case of delay by Employer in acquiring and providing permits, approvals and/or licenses required for the proper execution of the contract, including all requisite rights of way, as applicable, the Employer shall pay reasonable cost incurred by the contractor along with suitable time extension. | Provisions of the Bidding Documents are amply clear. Employer and Bidder/Contractor shall discharge their responsibilities in line with the relevant provisions of the Bidding Documents. |
|  | GCC Cl. 18.3.1.4(o), Section-IV: GCC, Volume-I of the Bidding Documents | The Building and Other Construction workers (Regulation of Employment and Conditions of Service) Act 1996 and the Cess Act of 1996: All the establishments who carry on any building or other construction work and employ 10 or more workers are covered under this Act. All such establishments are required to pay cess at the rate not exceeding 2% of the cost of construction as may be modified by the Government. The Employer of the establishment is required to provide safety measures at the Building or construction work and other welfare measures, such as Canteens, First-Aid facilities, Ambulance, Housing accommodations for workers near the work place etc. The Employer to whom the Act applies has to obtain a registration certificate from the Registering Officer appointed by the government. | The Bidder requests to confirm that the BOCW taxes @1% shall be applicable on the Contract for Services only. The same shall not be applicable on Contract for Supply of the Equipment. | The bidders are required to bid as per the provisions of Bidding Documents which are amply clear. |
|  | GCC 10.11, Section-IV: General Conditions of Contract [Taxes and Duties] | For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2(Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date seven (07) days prior to the last date of bid submission (hereinafter called “Tax” in this GCC Sub-clause 10.7). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation except for classification related purpose, or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Contractor in connection with performance of the Contract, an equitable adjustment of the Contract price shall be made to fully take into account any such change by addition to the Contract price or deduction therefrom, as the case may be, in accordance with GCC Clause 31 (Changes in Laws and Regulations) hereof. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor and on account of variation in taxes, duties & levies applicable locally. In respect of raw materials, intermediary components etc and the taxes, duties & levies applicable locally, neither the Employer nor the Contractor shall be entitled to any claim arising due to increase or decrease in the rate of Tax, introduction of a new Tax or abolition of an existing Tax in the course of the performance of the Contract. | In lieu of the on-going updates in lieu of proposal of introduction of GST and further high propoability of the same being introduced during the currency of the project, please modify the clause as below: For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2(Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date seven (07) days thirty (30) days prior to the last date of bid submission (hereinafter called “Tax” in this GCC Sub-clause 10.7). If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation except for classification related purpose, or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Contractor in connection with performance of the Contract, an equitable adjustment of the Contract price shall be made to fully take into account any such change by addition to the Contract price or deduction therefrom, as the case may be, in accordance with GCC Clause 31 (Changes in Laws and Regulations) hereof. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor and on account of variation in taxes, duties & levies applicable locally. In respect of raw materials, intermediary components etc and the taxes, duties & levies applicable locally, neither the Employer nor the Contractor shall be entitled to any claim arising due to increase or decrease in the rate of Tax, introduction of a new Tax or abolition of an existing Tax in the course of the performance of the Contract. Further, In the event of introduction of any other tax the impact of differential tax duty , if any on the total contract price including bought out items (to be dispatched directly from sub-vendors works to the site) will also be adjusted in contract price subject to documentary evidence. The total differential tax liability will be limited to the applicable increase/decrease in Tax rate on the contract price including sub vendor items. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 13.2.2, Section IV: General Conditions of Contract [Contractor’s Representative & Construction Manager] | The Contractor’s Representative shall represent and act for the Contractor at all times during the currency of the Contract and shall give to the Project Manager all the Contractor’s notices, instructions, information and all other communications under the Contract. All notices, instructions, information and all other communications given by the Employer or the Project Manager to the Contractor under the Contract shall be given to the Contractor’s Representative or, in its absence, its deputy, except as herein otherwise provided. The Contractor shall not revoke the appointment of the Contractor’s Representative without the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, the Contractor shall appoint some other person as the Contractor’s Representative, pursuant to the procedure set out in GCC Sub-Clause 13.2.1. | Please modify the paragraph as below: ......The Contractor shall not revoke the appointment of the Contractor’s Representative without notifying the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, tThe Contractor shall appoint some other person as the Contractor’s Representative, pursuant to the procedure set out in GCC Sub-Clause 13.2.1. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 13.2.3, Section IV: General Conditions of Contract [Contractor’s Representative & Construction Manager] | The Contractor’s Representative may, subject to the approval of the Employer (which shall not be unreasonably withheld), at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Contractor’s Representative, and shall specify the powers, functions and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Employer and the Project Manager. Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GCC Sub-Clause 13.2.3 shall be deemed to be an act or exercise by the Contractor’s Representative. | Please modify the paragraph as below: The Contractor’s Representative may, subject to the approval of the Employer which shall not be unreasonably withheld, at any time delegate to any person any of the powers, functions and authorities vested in him or her and notify to the Employer. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 14.4, Section IV: General Conditions of Contract [Progress of Performance] | Progress of Performance If at any time the Contractor’s actual progress falls behind the program referred to in GCC Sub-Clause 14.2, or it becomes apparent that it will so fall behind, the Contractor shall, at the request of the Employer or the Project Manager, prepare and submit to the Project Manager a revised program, taking into account the prevailing circumstances, and shall notify the Project Manager of the steps being taken to expedite progress so as to attain Completion of the Facilities within the Time for Completion under GCC Sub-Clause 4.2, any extension thereof entitled under GCC Sub-Clause 34.1, or any extended period as may otherwise be agreed upon between the Employer and the Contractor. | Please confirm that: In case such expedited progress is required due to reasons not attributable to the Contractor, the Parties shall proceed in accordance with Clause no. 33 (Change in the Facilities) of the GCC. | Provisions of the Bidding Documents are amply clear. |
|  | GCC 16.3.2, Section IV: General Conditions of Contract [Approval/Review of Technical Documents by Project Manager] | Within twenty one (21) days after receipt by the Project Manager of any document requiring the Project Manager's approval in accordance with GCC Sub-Clause 16.3.1, the Project Manager shall either return one copy thereof to the Contractor with its approval endorsed thereon or shall notify the Contractor in writing of its disapproval thereof and the reasons therefor and the modifications that the Project Manager proposes. | Please modify the paragraph as below: Within twenty one (21) days 7 days (for documents of normal/standard configurations) and 14 days (for documents related to detail design) after receipt by the Project Manager / Employer's personnel of any document requiring the Project Manager's / Employer's personnel approval in accordance with GCC Sub-Clause 16.3.1, the Project Manager / Employer's personnel shall either return one copy thereof to the Contractor with its approval endorsed thereon or shall notify the Contractor in writing of its disapproval thereof and the reasons thereof and the modifications that the Project Manager / Employer's personnel proposes. If the Project Manager / Employer's personnel fails to take such action within the said seven (7)/fourteen (14) days, such document is deemed to have been reviewed by the Project Manager / Employer's personnel and approved. Alternatively, If such review and approval is delayed beyond seven (7)/ fourteen (14) days, for reasons not attributable to the Contractor, then the Contractor shall be entitled to extension of Time for Completion pursuant to GCC 34.1 (e) and the Contractor shall be compensated for the cost incurred on account of such time extensions. | Provisions of the Bidding Documents shall remain unchanged. |
|  | 1st para of GCC Clause 18.3.1.3, Section IV: General Conditions of Contract [Compliance with Labour Regulations] | If the Employer is caused to pay under any law as principal employer such amounts as may be necessary to cause or observe, or for non observance of the provisions stipulated in the notifications/ byelaws/Acts/ Rules/regulations including amendments, if any, on the part of the Contractor, the Employer shall have the right to deduct any money due to the Contractor under this contract or any other contract with the employer including his amount of performance security for adjusting the aforesaid payment. The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer. | Please modify the paragraph as below: If the Employer is caused to pay under any law as principal employer such amounts as may be necessary to cause or observe, or for non observance of the provisions stipulated in the notifications/ byelaws/Acts/ Rules/regulations including amendments, if any, on the part of the Contractor, the Employer shall have the right to deduct any money due to the Contractor under this contract or any other contract with the employer including his amount of performance security for adjusting the aforesaid payment. The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer. | Provisions of the Bidding Documents shall remain unchanged. |
|  | 1st para of GCC 18.3.3.3, Section V: General Conditions of Contract [Safety Precautions] | The Contractor will notify well in advance to the Project Manager of his intention to bring to the Site any container filled with liquid or gaseous fuel or explosive or petroleum substance or such chemicals which may involve hazards. The Project Manager shall have the right to prescribe the conditions, under which such container is to be stored, handled and used during the performance of the works and the Contractor shall strictly adhere to and comply with such instructions. The Project Manager shall have the right at his sole discretion to inspect any such container or such construction plant/equipment for which material in the container is required to be used and if in his opinion, its use is not safe, he may forbid its use. No claim due to such prohibition shall be entertained by the Employer and the Employer shall not entertain any claim of the Contractor towards additional safety provisions/conditions to be provided for/constructed as per the Project Manager’s instructions. | Please modify the paragraph as below: The Contractor will notify well in advance to the Project Manager of his intention to bring to the Site any container filled with liquid or gaseous fuel or explosive or petroleum substance or such chemicals which may involve hazards. The Project Manager shall have the right to prescribe the conditions, In consultation with the Contractor, under which such container is to be stored, handled and used during the performance of the works and the Contractor shall strictly adhere to and comply with such instructions. The Project Manager shall have the right at his sole discretion to inspect any such container or such construction plant/equipment for which material in the container is required to be used and if in his opinion, its use is not safe, he may forbid its use. No claim due to such prohibition shall be entertained by the Employer and the Employer shall not entertain any claim of the Contractor towards additional safety provisions/conditions to be provided for/constructed as per the Project Manager‟s instructions. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 18.3.3.22, Section IV: General Conditions of Contract [Safety Precautions] | The Contractor shall follow and comply with all Employer Safety Rules, relevant provisions of applicable laws pertaining to the safety of workmen, employees, plant and equipment as may be prescribed from time to time without any demur, protest or contest or reservations. In case of any discrepancy between statutory requirement and Employer Safety Rules referred above, the latter shall be binding on the Contractor unless the statutory provisions are more stringent. | Please provide copy of Safety rules to enable us understand the provisions and confirm our acceptance/ qualification on the same | Regarding Safety Rules, provisions of the Bidding Documents inter-alia at GCC 18.3.3 (Safety Precautions) nad those specified in the Safety Pact may be referred to which are amply clear. |
|  | GCC 20.1.2.4, Section IV: General Conditions of Contract [Completion of Facilties and Operational Acceptance] | The Project Manager shall, within fourteen (14) days after receipt of the Contractor’s notice under GCC Sub-Clause 20.1.2.3, notify the Contractor in writing of any defects and/or deficiencies. | The Project Manager shall, within fourteen (14) days after receipt of the Contractor’s notice under GCC Sub-Clause 20.1.2.3, notify the Contractor in writing of any defects and/or deficiencies or advise the Contractor to proceed with the Commissioning of the Facilities or the relevant part thereof. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 20.1.2.7, Section V: General Conditions of Contract | As soon as possible after Precommissioning, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract, failing which the Employer will undertake such completion and deduct the costs thereof from any monies owing to the Contractor. | Please modify the paragraph as below: As soon as possible Within reasonable time after Pre-commissioning, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract for Commissioning. In case the contractor fails to complete the outstanding minor items within reasonable time , failing which the Employer, upon notification to the Contractor, will undertake such completion of outstanding minor items and deduct the corresponding costs thereof from any monies owing to the Contractor under this contract. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 20.1.2.9, Section IV : General Conditions of Contract | In the event that the period of suspension under GCC Sub-Clause 20.1.2.8 actually exceeds one hundred eighty (180) days, the Employer and the Contractor shall mutually agree to any additional compensation payable to the Contractor. | Please modify the paragraph as below: In the event that the period of suspension under above Sub-Clause 20.1.2.8 actually exceeds 180 days, the Employer and Contractor shall mutually agree to any additional compensation payable to the Contractor and the defect liability period as per clause GCC / SCC 22.2 shall commence . Upon Completion and/or use of facilities in full or parts, the Employer shall be responsible for the care and custody of the Facilities or the relevant part thereof, together with the risk of loss or damage thereto, and shall thereafter take over the Facilities or the relevant part thereof. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 21.2, Section – IV: General Conditions of Contract [Completion Time Guarantee] | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. | Please modify the paragraph as below: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to half percent (0.5%) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each week or part thereof which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. Such payment shall completely satisfy the Contractor’s obligation to attain Completion of the Facilities or the relevant part thereof within the Time for Completion or any extension thereof. The Contractor shall have no further liability whatsoever to the Employer in respect thereof. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 22.2, Section IV: General Conditions of Contract [Defect Liability] | ………………….. If during the Defect Liability Period any defect should be found in the design, engineering, materials and workmanship of the Plant and Equipment supplied or of the work executed by the Contractor, the Contractor shall promptly, in consultation and agreement with the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace or otherwise make good (as the Contractor shall, at its discretion, determine) such defect as well as any damage to the Facilities caused by such defect. The Contractor shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Facilities arising out of or resulting from any of the following causes: (a) improper operation or maintenance of the Facilities by the Employer (b) operation of the Facilities outside specifications provided in the Contract (c) normal wear and tear. | Bidder requests for modification to the clause as given below; ..... If during the Defect Liability Period any defect should be found in the design, engineering, materials and workmanship of the Plant and Equipment supplied or of the work executed by the Contractor, the Contractor shall promptly, in consultation and agreement with notification to the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace or otherwise make good (as the Contractor shall, at its discretion, determine) such defect as well as any damage to the Facilities caused by such defect. The Contractor shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Facilities arising out of or resulting from any of the following causes: (a) improper operation or maintenance of the Facilities by the Employer (b) operation of the Facilities outside specifications provided in the Contract (c) normal wear and tear. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 22.8, Section IV: GCC and corresponding clause in Section-V: SCC [Defect Liability] | In GCC: If the Facilities or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Facilities or such part, as the case may be, shall be extended by a period equal to the period during which the Facilities or such part cannot be used by the Employer because of any of the aforesaid reasons. Upon correction of the defects in the Facilities or any part thereof by repair/replacement, such repair/replacement shall have the Defect Liability Period extended by a period mentioned in GCC Sub-Clause 22.2 from the time of such replacement/repair of the facilities or any part thereof. In SCC: Supplementing Sub-Clause GCC 22.8 Upon correction of the defects in the (145kV/220KV/245kV/400kV class) Current Transformer/ Capacitive Voltage Transformer / Circuit Breaker / Reactor by repair/replacement, such repair/replacement shall have the Defect Liability Period of the said (145kV/220KV/245kV/400kV class) Current Transformer/ Capacitive Voltage Transformer / Circuit Breaker / Reactor extended by a period of 2 years from the time of such repair/replacement of the said (145kV/220KV/245kV/400kV class) Current Transformer/ Capacitive Voltage Transformer / Circuit Breaker / Reactor to rectify the defect, or up to the expiry of period mentioned in GCC Sub-Clause 22.2, whichever is later. | Bidder requests for the modification of said clause as suggested below: Upon correction of the defects in the Facilities or any part thereof by repair/replacement, such repair/ replacement shall have the Defect Liability Period extended by a period mentioned in GCC Sub-Clause 22.2 from the time such replacement/repair of the facilities or any part thereof. However all such extension shall cease on 12 months from the end of original defect liability period as mentioned in GCC 22.2. | Provisions of the Bidding Documents shall remain unchanged. Further, Bidders are requested to read clauses of the Section-GCC in conjunction with corresponding clause in Section-SCC. |
|  | GCC 22.9, Section IV: General Conditions of Contract GCC [Defect Liability] | Except as provided in GCC Clauses 22 and 29, the Contractor shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, in respect of defects in the Facilities or any part thereof, the Plant and Equipment, design or engineering or work executed that appear after Defect Liability Period except for the liability towards obligations that may survive in terms of the Contract after Defect Liability Period, except where such defects are the result of the gross negligence, fraud, criminal or willful action of the Contractor. | Bidder requests modification of said clause as suggested below: Except as provided in GCC Clauses 22 and 29, the Contractor shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, including but not limited to implied warranties of merchantability and fitness for a particular purpose, or otherwise, in respect of defects in the Facilities or any part thereof, the Plant and Equipment, design or engineering or work executed that appear after Defect Liability Period except for the liability towards obligations that may survive in terms of the Contract after Defect Liability Period, except where such defects are the result of the gross negligence, fraud, criminal or willful action of the Contractor. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 24.2, Section IV: General Conditions of Contract (GCC) [Equipment Performance Guarantees] | If the guarantees specified in Appendix – 8 (Guarantees, Liquidated Damages for Non – Performance) to the Contract Agreement are not established, then the Employer shall, at the Employer’s discretion either (a) reject the equipment, or (b) accept the equipment after assessing liquidated damages in accordance with the provision in the SCC against the Contractor and such amounts shall be deducted from the Contract Price or otherwise recovered from the Contractor. | Please modify the clause as below: If the guarantees specified in Appendix–8 (Guarantees, Liquidated Damages for Non – Performance) to the Contract Agreement are not established, then the Employer shall, at the Employer’s discretion either (a) reject the equipment, or (b) accept the equipment after assessing liquidated damages in accordance with the provision in the SCC against the Contractor and such amounts shall be deducted from the Contract Price or otherwise recovered from the Contractor. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 29.1, Section IV: General Conditions of Contract (GCC) [Loss of or Damage to Property; Accident or Injury to Workers; Indemnification] | The Contractor shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property (other than the Facilities whether accepted or not), arising in connection with the supply and installation of the Facilities and by reason of the negligence of the Contractor or its Subcontractors, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its contractors, employees, officers or agents. | We understand that the overall liability under this Contract is limited to the Contract Price. We propose a cap per damage event as given below, to be added to GCC 29.1: For damages to Employer’s property, which the Contractor is responsible for, the Contractor compensates the costs of the re-construction or restoration of Employer’s property up to an amount of 10' Mio INR per damage event. The above Indemnity obligation is applicable only for the mandatory claims under the law. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 30.2, Section – IV, General Conditions of Contract [Insurance] | The Employer shall be named as co-insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1, except for the Third Party Liability, Workmen Compensation Policy Insurances, and the Contractor’s Subcontractors shall be named as co-insureds under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1 except for the Cargo Insurance During Transport, Workmen Compensation Policy Insurances. All insurer’s rights of subrogation against such coinsureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. | Bidder requests for modification to the clause as given below; The Employer shall be named as co-insured jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1, except for the Third Party Liability, Workmen Compensation Policy Insurances, Automobile Liability Insurance, Contractor's Plant and Machinery (CPM) Insurances and the Contractor‟s Subcontractors shall be named as co-insureds jointly insured under all insurance policies taken out by the Contractor pursuant to GCC Sub-Clause 30.1 except for the Cargo Insurance During Transport, Automobile Liability Insurance, Workmen Compensation Policy Insurances and Contractor's Plant and Machinery (CPM) Insurances. All insurer‟s rights of subrogation against such co-insureds jointly insured for losses or claims arising out of the performance of the Contract shall be waived under such policies. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 30.3, Section IV : General Conditions of Contract [Insurance] | The Contractor shall, in accordance with the provisions of the corresponding Appendix – 3 (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days‟ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy. | Bidder requests for modification to the clause as given below; The Contractor shall, in accordance with the provisions of the corresponding Appendix–3 (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance (or copies of the insurance policies) as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days’ notice shall be given to the Employer by insurers/Contractor prior to cancellation or material modification of a policy. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 30.5, Section – IV, General Conditions of Contract [Insurance] | The Employer shall at its expense take out and maintain in effect during the performance of the Contract those insurances specified in the corresponding Appendix – 3 (Insurance Requirements) to the Contract Agreement, in the sums and with the deductibles and other conditions specified in the said Appendix. The Contractor and the Contractor’s Subcontractors shall be named as co-insureds under all such policies. All insurers‟ rights of subrogation against such coinsureds for losses or claims arising out of the performance of the Contract shall be waived under such policies. The Employer shall deliver to the Contractor satisfactory evidence that the required insurances are in full force and effect. The policies shall provide that not less than twenty-one (21) days’ notice shall be given to the Contractor by all insurers prior to any cancellation or material modification of the policies. If so requested by the Contractor, the Employer shall provide copies of the policies taken out by the Employer under this GCC Sub-Clause 30.5. | Please modify the clause as below: …. The policies shall provide that not less than twenty-one (21) fourteen (14) days’ notice shall be given to the Contractor by all insurers prior to any cancellation or material modification of the policies | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 31.1, Section IV: General Conditions of Contract [Change in Laws and Regulations] | If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in India (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor for which the Employer shall be the sole judge. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement. | Bidder requests for modification to the clause as given below; 31.1 If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in India (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor for which the Employer shall be the sole judge. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 32.2 and 32.4, Section – IV, General Conditions of Contract [Force Majeure] | 32.2 Neither party shall be considered to be in default or in breach of his obligations under the Contract to the extent that performance of such obligation is prevented by any circumstances of Force majure, which arises after date of Notification of Award. 32.4 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GCC Clause 34. | Bidder requests for confirmation that in case of a Force Majeure situation, the Contractor shall get cost relief/compensation in case any additional cost is incurred by him. | Provisions of the Bidding Documents are amply clear. |
|  | GCC 32, Section IV : General Conditions of Contract (GCC) [Force Majeure] | 32. Force Majeure 32.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, 32.2 Neither party shall be considered to be in default or in breach of his obligations under the Contract to the extent that performance of such obligation is prevented by any circumstances of Force majure, which arises after date of Notification of Award. 32.3 If either party is prevented, hindered or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event. 32.4 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GCC Clause 34. | Bidder request the addition to the existing clause as given below; In case of occurrence of a Force Majeure incident for more than 4 months, the Contractor at its discretion may, by giving further notice to the Project Manager, request for deletion of such part in accordance with GCC Clause 33 or, where it affects the whole of the Facilities, as termination of the Contract under GCC Sub-Clause 36.1. | Provisions of the Bidding Documents shall remain unchanged. |
|  | Section IV : General Conditions of Contract Add new GCC 32.5 - Force Majeure |  | Bidder request the addition of following clause to GCC 37, since this is outside Bidder control: Contractor shall not be obligated to fulfill the Contract if such fulfillment is prevented by any impediments arising out of national or international foreign trade or customs requirements or any embargoes or other sanctions. The Parties acknowledge the worldwide outbreak of the COVID-19, which is likely to affect the execution of the Agreement. The Parties agree, that Supplier shall be entitled to reasonable adjustments of the Delivery Schedule/ milestones/ delivery dates as well as to reimbursement of costs to the extent the delay and the costs are caused directly or indirectly by the outbreak of COVID-19. In case force majeure conditions are excceding 180 days for a single event, the parties may terminate the contract after mutual agreement. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 33.2.2, Section IV : General Conditions of Contract Change originating from the Employer | …………………….. HSN/SAC has not been indicated in the Contract for lumpsum quantities/lot/Set as each of these consists of many items for which billing break up shall be furnished during contract execution. GST shall be reimbursed on these items based on HSN /SAC for these items furnished along with billing breakup. However, the reimbursement shall be limited to the amount derived based on the rate indicated in the contract or actual, whichever is less. | HSN/SAC has not been indicated in the Contract for lumpsum quantities/lot/Set as each of these consists of many items for which billing break up shall be furnished during contract execution. GST shall be reimbursed on these items based on HSN /SAC for these items furnished along with billing breakup. However, the reimbursement shall be limited to the amount derived based on the actual rate indicated in the contract or actual, whichever is less. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 33.2.5, Section IV: General Conditions of Contract [Changes Originating from Employer] | The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”). Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. ……………… ……………… | Please modify the clause as below: The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”). Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 34.1, Section IV: General Conditions of Contract [Extension of Time for Completion] | The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) any Change in the Facilities as provided in GCC Clause 33 (b) any occurrence of Force Majeure as provided in GCC Clause 32 (c) any suspension order given by the Employer under GCC Clause 35 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 35.2 or (d) any changes in laws and regulations as provided in GCC Clause 31 or (e) any other matter specifically mentioned in the Contract by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Bidder request for modification to the clause as below: The Time(s) for Completion specified in the SCC shall be extended if the Contractor is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) any Change in the Facilities as provided in GCC Clause 33 (b) any occurrence of Force Majeure as provided in GCC Clause 32 (c) any suspension order given by the Employer under GCC Clause 35 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 35.2 or (d) any changes in laws and regulations as provided in GCC Clause 31 or (e) any other matter specifically mentioned in the Contract or (f) any default or breach of the Contract by the Employer, or any activity, act or omission of the Employer, or the Project Manager, or any other contractors employed by the Employer g) Any delay by the Employer in providing the facilities as per Appendix 4 & 6 of Contract forms (refer our Deviation in Attachment-5B). by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Contractor. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 34.2, Section IV : General Conditions of Contract [Extension of Time for Completion] | Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to Arbitration, pursuant to GCC Sub-Clause 39. | Please modify the paragraph as below: Except where otherwise specifically provided in the Contract, the Contractor shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable within 14 days after the commencement of such event or circumstance. As soon as reasonably practicable after Within 14 days of receipt of such notice and supporting particulars of the claim, the Employer and the Contractor shall agree upon the period of such extension. In the event that the Contractor does not accept the Employer’s estimate of a fair and reasonable time extension, the Contractor shall be entitled to refer the matter to a Dispute Board, pursuant to GCC Sub-Clause 39 | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 35, Section IV : General Conditions of Contract GCC 35 Add new clause (GCC 35.4) | 35. Suspension | Please add a new sub clause as below; 35.4 In the event any of the following occurs Contractor may at its option suspend the provision of its obligations under this Contract: a) Customer fails to make payment of any amount within 30 days after it has become due and payable, or b) Customer fails to perform its obligations necessary for the Contractor to deliver or complete the Work, or c) Delivery and/or completion of the Work is prevented by export or other legally mandated restrictions for more than 6 months; or d) Customer is insolvent. In the event Contractor suspends the provision of its obligations, Customer shall pay the Contractor all additional cost incurred due to such suspension. | Provisions of the Bidding Documents shall remain unchanged. |
|  | Section IV : General Conditions of Contract GCC 40 – Unforeseen Conditions / Subsurface Risks | - | Bidder requests the addition of the following clause: If during the execution of the works on Site the Contractor encounters physical obstructions or conditions which could not reasonably have been foreseen by the Contractor at the latest date for bid submission, the Contractor shall be entitled to recover the additional Time for Completion and cost incurred in consequence. “Physical obstructions and conditions” means natural physical conditions and manmade and other physical constructions and pollutants, which the Contractor encounters at the Site, including subsurface and hydrological conditions. | Provisions of the Bidding Documents shall remain unchanged. |
|  | Section VI - Sample Forms and Procedures | 2. Bid Security Form / 6.Performance Security Form | Bidder presume that these bid / performance securities are interpreted under Indian law with the jurisdiction of Courts of New Delhi. Please add the following regulations in addition: - After expiry of this bid guarantee/performance security guarantee, Employer will immediately return this bid guarantee/performance security guarantee to the Bidder without any further requested by the Bidder. | Provisions of the Bidding Documents are amply clear and shall remain unchanged. |
|  | Appendix-1 Terms and Procedures of Payment, Section VI - Sample Forms and Procedures | Payment Terms | Contractor shall be given Interest free advance payments. Kindly modify the existing clause. | Provisions of the Bidding Documents shall remain unchanged. |
|  | GCC 1.1 (n), Section-IV: General Conditions of Contract (GCC), Vol.-I of the Bidding Documents | “Effective Date” means the date of Notification of Award from which the Time for Completion shall be determined. | The Bidder requests to kindly modify the existing clause with the following: The Effective Date upon which the period until the Time for Completion of the Facilities shall be counted from is the date when all of the following conditions have been fulfilled: (a) This Contract Agreement has been duly executed for and on behalf of the Employer and the Contractor. (b) The Contractor has submitted to the Employer the performance security. (c) The Employer has paid the Contractor the advance payment provided the Contractor has submitted the advance payment guarantee. (d)The Employer has handed over the clear site without any hindrance. Each party shall use its best efforts to fulfill the above conditions for which it is responsible as soon as practicable. | Provisions of the Bidding Documents shall remain unchanged. |
|  | Form 22. Form of Joint Deed of Undertaking by the GIS Manufacturer alongwith the Bidder/ Contractor, Para 2.0 | In case of any breach of the Contract committed by the Contractor, we, the Associate do hereby undertake, declare and confirm that we shall be fully responsible for design, manufacturing, erection, testing and commissioning of complete GIS switchyard under the Contract and undertake to carry out all obligation and responsibilities under this Deed of Joint Undertaking in order to discharge the Contractor’s obligations and responsibilities stipulated in the Contract with respect to GIS portion of the Contract. Further, if the Employer sustains any loss or damage on account of any breach with respect to GIS portion of the Contract, we, the Associate and the Contractor jointly and severally undertake to promptly indemnify, and pay such losses/damages caused to the Employer on its written demand without any demur, reservation, contest or protest in any manner whatsoever. | We would like to clarify that we qualify for the subject project under Route 4 of Annexure A (BDS) with our Associate qualifying as GIS OEM qualifying through Route 1. In line to the subject clause, we wish to re-clarify that our associate shall be liable for only the GIS portion of the Contract and not for the Complete GIS Switchyard. Request to please confirm our understanding | Form No. 22 available in the Bidding Documents for the subject package is applicable for bidders who intended to submit their bid through Route No. 4. Further, as per Form No. 22, the Bidder and GIS manufacturer (as “Associate”) are jointly and severally liable and bound unto the Employer for successful performance of the GIS portion of the Contract of complete GIS switchyard under the Contract. Therefore, the provisions of the Bidding Documents are amply clear and shall remain unaltered. |

*********************************