ANNEXURE-A(SCC)

Page 1 of 2

REFERENCE TO GENERAL CONDITIONS OF CONTRACT

Clause No. of GCC

| 1.0(b) of GCC | Accepting Authority | ED,SR-II, POWERGRID, or his Authorized representative |
| --- | --- | --- |
| 1.0(j) of GCC | Market rate percentage addition to cover overheads & profit | 15 percent |
| 22.2 (iii) of GCC | Schedule of rates applicable | CPWD latest for civil works for scheduled items / Market rate for Non-schedule items |
| 22.2 (vi) A of GCC | Deviation limit for items of works other than those below ground surface | During the execution of the contract, POWERGRID reserves the right to increase or decrease the quantities of the items under the contract but without any change in the base unit price identified in the contract, and other terms & conditions. However, the overall variation shall be limited to ± 25% of the Contract Price on the same rates, terms & conditions. |
| 22.2 (vi) (A)(a) of GCC | Permissible deviation limit for any contract item, substituted item in excess of the original value of item |  |
| 22.2 (vi) (A) (b) of GCC | Permissible deviation limit for items of works not already included in the contract |  |
| 22.2 (vi) (B) of GCC | Deviation limit for items of works below ground surface |  |
| 22.2(vi)B(a) | Permissible deviation limit for an individual trade item |  |
| 23.0 of GCC | Suspension of works: |  |
| 23.1(b) (ii) | Percentage payable to cover Contractor's indirect expenses for suspension exceeding thirty days and not exceeding 3 months. | 4 percent |
| 23.1 (c) | Percentage payable to cover Contractor's indirect expenses for suspension exceeding 3 months | 5 percent |
| 18.0 of GCC | Time allowed for execution of work or Time Schedule. | Refer SCC |

ANNEXURE-A (SCC)

Page 2 of 2

| 24.3 of GCC | Authority competent to “decide if any other cause” of delay is beyond contractor’s control | ED,SR-II, POWERGRID, or his Authorized representative |
| --- | --- | --- |
| 28.2 of GCC | Distribution return of number employed on works to be submitted to Engineer-in-Charge | FORTNIGHTLY |
| 46 of GCC | Defects Liability Periods | 12 (Twelve) Months |
| 64.1 of GCC | Interim bills | Monthly |
| 67.0 of GCC | Loans | Refer SCC |
| 69.0 of GCC | Authority appointing arbitrator | ED,SR-II, POWERGRID, or his Authorized representative |