## Clarification
Clarifications No.-III dated 11.04.2023 to Bidding Documents for Package DC-C&ME for Construction & Interiors of Green Field Data Centre Building including Mechanical & Electrical Works under Establishment of Pilot Data Centre at POWERGRID Manesar substation, Specification No(s).: CC/NT/W-CIVIL/DOM/A06/23/00358.
S.No. | Section | Existing Clauses | Query/Clarification sought by bidders | POWERGRID's Reply
1 | Vol-II, Section-7, Annexure_ Revised Table of Vol-II Section-7 Clause-7-4-2 Manpower | Annexure_ Revised Table of Vol-II Section-7 Clause-7-4-2 Manpower - Revised Table of Manpower - on roll of contractor - HT & LT System , DG Engineer, IBMS/DCIM Operator, HVAC Engineer | Bidder requests that the mentioned on roll manpower be permitted to be subcontracted by the bidder as this is an L1 RFP and as such all bidder need to be cost competitive and with subcontracting the cost advantage gained will also be passed on to PGCIL. Further, the asked profiles non-IT profiles and hence asked quantum of manpower is not maintained on rolls. Further, as chosen Contractor, the onus of project and performance will always lies with the bidder. Thus we request that the revision from on roll manpower to off roll manpower be permitted. | Please refer Amendment-III Sr No.-1 for details.
2 | Vol-II, Section-7, Clause-7.4.4.4 Targets of Service Level Agreement | SLA clause provides for the minimum level of services required as per contractual obligations based on performance indicators and measurements thereof…. | SLA penalty is uncapped as of now, and bidder shall need revenue per quarter to provide services to PGCIL. Further, it may so happen that due to one single component the bidder quarter revenue is eroded by more than 70-80%, which will make the services non viable for any bidder. As such, Bidder request that total SLA penalty in any quarter for not meeting the defined SLA targets be capped to a maximum of 20% of the Quarterly billing or QGR (i.e. AMC for that particular quarter) excluding taxes, for the critical SLA parameters and 10% for the non critical SLA parameters. This is in line with the industry practise for penalty in O&M phase of IT / ME works Government tenders. | Please refer Amendment-III Sr No.-2 for details.
4 | GCC Clause 36.2.6, Section-IV, Volume-I of the Bidding Documents | If the sum that the Contractor is entitled to be paid, pursuant to GCC Sub-Clause 36.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price or the entire Facilities if entire Facilities have been completed or the price for part of the Facilities if part of the Facilities have been completed, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Employer shall pay the balance to the Contractor. For facilitating such payment the Employer shall encash the Bank Guarantees of the Contractor available with the Employer and retain such other payments due to the Contractor under the Contract in question or any other Contract that the Employer may have with the Contractor. | Bidder proposes revision for this clause as it is uncapped as of now , as per under: " ....If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, provided that the Contractor shall not be liable to Excess Cost in excess of (ten) 10 percent of the Total Contract Value for which such option is exercised by the Purchaser,.....". Herein bidder suggests the above as in accordance with the RFP pre qualification only serious bidders shall bid for the RFP. Thus, the project prices quoted shall be genuine and in case of Risk and cost scenario the excess that shall be determined through PGCIL process shall be within 10% of the Total contract value, and in line with the PGCIL estimated budget . Thus we believe that a 10% of TCV as excess shall be sufficient to cover the costs due to such exigencies which may be due to any inflation or other reasons. | The Provisions of the bidding document are amply clear and shall remained unchanged.
5 | GCC Clause 22.8.1, Section-IV, Volume-I of the Bidding Documents | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | Bidder understands and brings to your notice that the design for this RFP (construction and ME works) is provided to the bidders by PGCIL and is not done by the bidder . Further as the bidder, wrt the material supplied bidder is not the OEM & as such does not own the design / material for this works. As such this clause is not applicable to the bidder in this works case. Bidder request to review this clause and request it to be deleted as part of the SCC. | The Provisions of the bidding document are amply clear and shall remained unchanged.
6 | GCC Clause 22.8.1, Section-IV, Volume-I of the Bidding Documents | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | Bidder request that period of latent defects warranty for material to be ended with the contract period, if at all and be limited only to material supplied and not the design of the project. | The Provisions of the bidding document are amply clear and shall remained unchanged.