## Clarification
Clarifications-II dated 27.03.2023 to Bidding Documents for Package DC-C&ME for Construction & Interiors of Green Field Data Centre Building including Mechanical & Electrical Works under Establishment of Pilot Data Centre at POWERGRID Manesar substation, Specification No(s).: CC/NT/W-CIVIL/DOM/A06/23/00358.
S.No. | Section | Existing Clause as per the Bidding Document | Query/Clarification sought by bidders | POWERGRID's Reply
Volume-I of the Bidding Documents
1 | GCC Clause 36.2.6, Section-IV, Volume-I of the Bidding Documents | If the Employer completes the Facilities, the cost of completing the Facilities by the Employer shall be determined. If the sum that the Contractor is entitled to be paid, pursuant to GCC Sub-Clause 36.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price or the entire Facilities if entire Facilities have been completed or the price for part of the Facilities if part of the Facilities have been completed, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Employer shall pay the balance to the Contractor. For facilitating such payment the Employer shall encash the Bank Guarantees of the Contractor available with the Employer and retain such other payments due to the Contractor under the Contract in question or any other Contract that the Employer may have with the Contractor. The Employer and the Contractor shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. | This clause in other similar ME RFP from Govt Departments is having an upper cap on the excess payable by Contractor to the Employer. Request to kindly review to have a capping on this clause. The proposed revision is as under: " ....If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, provided that the Contractor shall not be liable to Excess Cost in excess of (ten) 10 percent of the Total Contract Value for which such option is exercised by the Purchaser,....." | The Provision of bidding document remains unchanged.
2 | GCC Clause 36.2.6, Section-IV, Volume-I of the Bidding Documents | If the Employer completes the Facilities, the cost of completing the Facilities by the Employer shall be determined. If the sum that the Contractor is entitled to be paid, pursuant to GCC Sub-Clause 36.2.5, plus the reasonable costs incurred by the Employer in completing the Facilities, exceeds the Contract Price or the entire Facilities if entire Facilities have been completed or the price for part of the Facilities if part of the Facilities have been completed, the Contractor shall be liable for such excess. If such excess is greater than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Contractor shall pay the balance to the Employer, and if such excess is less than the sums due the Contractor under GCC Sub-Clause 36.2.5, the Employer shall pay the balance to the Contractor. For facilitating such payment the Employer shall encash the Bank Guarantees of the Contractor available with the Employer and retain such other payments due to the Contractor under the Contract in question or any other Contract that the Employer may have with the Contractor. The Employer and the Contractor shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. | Sample Clause - Risk a) The time and the date of delivery of services as specified in Section V of this RFP shall be deemed to be the essence of the contract. b) The purchaser reserves the right to cancel the contract or a portion thereof and purchase the services as specified in Section V of this RFP at the risk and cost of bidder after giving due notice of 30 (thirty) working days to the Successful Bidder even before completion of the contractual delivery schedule if it becomes apparent that the Successful Bidder will not be able to fulfil the contractual obligations. In case the Successful Bidder fails to deliver the services or a portion thereof within the contractual delivery schedule, the purchaser has the right to purchase the services or a portion thereof at the risk and cost of Successful Bidder. c) In the event of cancellation of the contract by purchaser at the risk and cost of the Successful Bidder, the Successful Bidder shall be liable for any loss which the purchaser may sustain on account of risk purchase but the Successful Bidder shall not be entitled to any gain on such purchase made against such default. The manner and method of such purchase shall be at the entire discretion of the purchaser, whose decision will be final. d) Provided further that the Successful Bidder shall not be liable to Excess Cost in excess of (ten) 10 percent of the Total Contract Value for which such option is exercised by the Purchaser. | The Provision of bidding document remains unchanged.
3 | GCC Clause 26, Section-IV, Volume-I of the Bidding Documents | 26. Limitation of Liability 26.1 Except in cases of gross negligence or willful misconduct, (a) the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | Wrt 26.1. (b) - Any defect repair or equipment replacement in the project in defect liability period is part of direct damage, and as such should be capped at the cap for Limitation of liability i.e. project TCV. As such bidder requests to kindly exclude the sub-clause - " ..provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement." . | The Provision of bidding document remains unchanged.
4 | Appendix-2 to the Contract Agreement (Form No. 5), Sample Forms and Procedures, Section-VI | PRICE ADJUSTMENT 1.1 The prices for execution of the entire works covered under the scope of this Specification shall be quoted by the Bidder in the manner specified in the BPS. 1.1.1 The Ex-Works Price Components for all items shall remain firm and no price adjustment shall be applicable for the price components of these items. Other Charges viz. inland transportation, inland insurance, type test charges (if any), Installation Price for Mechanical and Electrical works, Annual maintenance charges and O&M Charges etc., shall also be firm and no price variation shall be payable for these components. Further, All Prices for Indoor/Outdoor Lighting/Illumination Works etc. and other items not specifically mentioned below shall remain FIRM and no price adjustment shall be applicable for these components for the entire duration of the Contract. 1.1.2 The Erection/Installation price of Civil Works will be subject to price adjustment, only for items of work specifically stated under clause 1.2 below, (for which the bidder shall quote a base price), based on separate formulae as per price adjustment provisions given herein: | Considering the price volatility, bidder request for following change to PRICE ADJUSTMENT : We understand lot II shall be ordered maximum by 130 weeks from bidder and the Lot II Prices need to stay firm only for 130 weeks from the project start date, where 130 weeks being the ordering timeline for lot -II agreed as per implementation schedule. In case, order for lot -II is not placed within agreed timeline, the prices for lot II will be mutually agreed. Pls confirm. | The Provision of bidding document remains unchanged.
5 | Appendix-2 to the Contract Agreement (Form No. 5), Sample Forms and Procedures, Section-VI | PRICE ADJUSTMENT 1.1 The prices for execution of the entire works covered under the scope of this Specification shall be quoted by the Bidder in the manner specified in the BPS. 1.1.1 The Ex-Works Price Components for all items shall remain firm and no price adjustment shall be applicable for the price components of these items. Other Charges viz. inland transportation, inland insurance, type test charges (if any), Installation Price for Mechanical and Electrical works, Annual maintenance charges and O&M Charges etc., shall also be firm and no price variation shall be payable for these components. Further, All Prices for Indoor/Outdoor Lighting/Illumination Works etc. and other items not specifically mentioned below shall remain FIRM and no price adjustment shall be applicable for these components for the entire duration of the Contract. 1.1.2 The Erection/Installation price of Civil Works will be subject to price adjustment, only for items of work specifically stated under clause 1.2 below, (for which the bidder shall quote a base price), based on separate formulae as per price adjustment provisions given herein: | Considering the price volatility, bidder request for confirmation on below wrt PRICE ADJUSTMENT : We understand that the Prices for change order ( covered under Clause GCC 33.2.3) to stay firm only for 60 weeks from the project start date, beyond which prices for any change quantity will be mutually agreed. Pls confirm. | The Provision of bidding document are amply clear and shall remain unchanged.
6 | GCC Clause 22.8, Section-IV, Volume-I of the Bidding Documents | If the Facilities or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Facilities or such part, as the case may be, shall be extended by a period equal to the period during which the Facilities or such part cannot be used by the Employer because of any of the aforesaid reasons. Upon correction of the defects in the Facilities or any part thereof by repair/replacement, such repair/replacement shall have the Defect Liability Period extended by a period mentioned in GCC Sub-Clause 22.2 from the time of such replacement/repair of the facilities or any part thereof. | Bidder request to cap the extension of defect liability period clause as OEM cannot extend warranty on daily basis and they extend it on a yearly basis. In any event, if the duration of the Defect Liability and warranty is required to be extended, it should be extended maximum by additional three (3) months, upon mutual consent of the parties. | The Provision of bidding document remains unchanged.
7 | GCC Clause 22.8.1, Section-IV, Volume-I of the Bidding Documents | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | 1. bidder is of understanding that latent defects is levied only for material and design used for civil work. Please confirm the understanding 2. bidder is also of an understanding that the latent defect warranty can be subcontracted with the end ownership being with the bidder. | The Provision of bidding documents are amply clear and shall remain unchanged.
8 | GCC Clause 22.8.1, Section-IV, Volume-I of the Bidding Documents | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | Bidder requests to delete the latent defects warranty requirement for design as design of the facility and item quantities are all mentioned by the Purchasor in the price template, and as such the onus cannot be taken up by the contractor. | The Provision of bidding documents are amply clear and shall remain unchanged.
9 | GCC Clause 22.8.1, Section-IV, Volume-I of the Bidding Documents | At the end of the Defect Liability Period, the Contractor's Liability ceases except for latent defects. The Contractor's liability for latent defects warranty shall be limited to period of ten (10) years from the end of Defect Liability Period. For the purpose of this clause, the latent defects shall be the defects inherently lying within the material or arising out of design deficiency, which do not manifest themselves during the Defect Liability Period defined in this GCC Clause 22, but later. | Bidder request that period of latent defects warranty for material to be ended with the defect liability period. Please confirm the understanding | The Provision of bidding document remains unchanged.
10 | General |  | Request for extension of bid submission end date by 3 weeks from current date. | Please visit the PRANIT portal in timely manner for information on extension of deadline for submission of Bids.
Volume-II of the Bidding Documents
1 | Vol-II, Section-3(C),Clause- 2.1 Technical specifications for air cooled chiller with VFD, Sub Clause-2.1.2, Pg-14 | AHRI/EUROVENT Certified Air Cooled twin rotor semi hermetic Screw Chillers | Tender specification is only accepting EUROVENT certified chillers however we request to change the clause as as "AHRI/EUROVENT Complied." – Schneider will be able to show the testing to our global factories on Eurovent/ AHRI conditions, Since these chillers are made for DC application only, and not for commercial building we don’t have any road map for certification. | The Provision of bidding document remains unchanged
2 | Vol-II, Section-3(C),Clause- 2.1 Technical specifications for air cooled chiller with VFD, Sub Clause-2.1.2, Pg-14 | Air cooled condenser comprising of copper tubes and copper fins with epoxy coating | Tender specification is asking for Copper fins which as per our experience will degrade in case of coming in contact with Air of high Sulphur content, so it’s requested to modify as specification as "Copper Tube & Aluminum Fins with Anti-corrosive coating on Coil for prevention from excessive sulphury environment. | The Provision of bidding document remains unchanged
3 | Vol-II, Section-3(C), Clause- 2.1 Technical specifications for air cooled chiller with VFD,Sub Clause-2.1.9, Pg-20 | For protection of Chiller against unauthorized access, the chiller OEM can provided with Wire Mesh enclosure from factory. | Tender specification is asking for Wire mesh. This clause is applicable for MCHX coil however it is not required to Copper/Aluminum coils. Please modify it as per OEM standard. (MCHX Coil). | The Provision of bidding document remains unchanged.
4 | Vol-II, Section-3(C), Clause- 2.1 Technical specifications for air cooled chiller with VFD,Sub Clause-2.1.13, Pg-21 | Sound pressure levels at 1 meter distance shall be as per AHRI- 370 or ISO- 3744 | Tender specification is asking for sound pressure levels at 1 meter distance shall be as per AHRI- 370 or ISO- 3744. AHRI- 370 or ISO- 3744 testing requires specific kind of Sound pressure chamber which is not available in factory however Sound pressure levels at 1 meter distance can be checked through DB meter with prevention of Background noise. Please accept the above. | The Provision of bidding document remains unchanged.
5 | Vol-II, Section-3(C), Clause- 2.6 Precision Air handling units,Sub Clause-2.6.11, Pg-61 | The display shall provide with track recorded of temperature and humidity with graphically display on the screen. A buzzer provides audible indication of a ‘Warning’ or ‘Alarm’ condition. Unit memory shall hold the 200 most recent alarms with time and date stamp for each alarm. Unit memory shall hold the 400 most recent events with id number, time and date stamp for each event | Tender Specification is looking for display that shall provide with track recorded of temperature and humidity with graphically. Unit memory shall hold the 200/400 most recent alarms. We can provide Graphs that can be generated thru BMS & Unit memory shall hold up to 100 Alarms. Please accept the above. Since the PAHU is connected to BMS which can hold alarm generated for years also. | The Provision of bidding document remains unchanged.
6 | Vol-II, Section-3(C), HVAC, Sub Clause-2.6.3 Cabinet, Pg-58 | The rear and the fans section panels are double-skinned, with 20mm (frontal fan section panel with 40mm) Class ‘O’ (A1 EU) fireproof insulation sandwiched between the skins to reduce noise emission and heat loss. The side panels, which are isolated from the inside of the unit to form a complete double-skinned cabinet, the small service panel for electrical heaters, are also lined with 10mm Class ‘O’ (A1 EU) fireproof insulation . | Tender Specifications call for “The rear and the fans section panels are double skinned, with 20mm (frontal fan section panel with 40mm) Class ‘O’ (A1 EU) fireproof insulation sandwiched between the skins to reduce noise emission and heat loss”. We can provide “Double skinned from the side panels with 15mm thick PUF insulation to reduce the noise level upto desired parameter”. Please accept the above. There is no functional isuue changing in spces to accommodate SE PAHU which are widely used in DC market. | The Provision of bidding document remains unchanged. Also, Please refer earlier issued Amendment-I Sr No.20 for more details.
7 | Vol-II, Section-3(A), Clause-3(A).9 IPDU & SENSORS, Sub Clause-7, Pg-34 | The metering accuracy should be +/- 1% compliant to ANSI C12.1 and IEC 62053-21 at 1% Accuracy Class Requirements for strip level | Tender Specification is asking for metering accuracy should be +/- 1% compliant however we request to consider metering accuracy from "+/- 1% to +/- 3%" which is as per market wide accepted specification. | The Provision of bidding document remains unchanged.
8 | Vol-II, Section-3(A), Clause-3(A).9 IPDU & SENSORS, Sub Clause-8, Pg-34 | 8. Network communication – PDU should have two Network Ports 10/100/1000 Mbps. IPDU should support communication protocols including SMTP, SSL, SNMP (v1, v2, v3), Modbus Communication module should be hot-swappable, so that it can be replaced without powering off the PDU. | Tender Specification requires PDU should have two Network Ports with 10/100/1000 Mbps speed & should support communication protocols including SMTP, SSL, SNMP (v1, v2, v3), Modbus Communication module. We request to consider & amend the clause as PDU’s to be capable to communicate on 10/100Mbps speed, hence request you to revise this clause as "PDU should have minimum one Network Ports of 10/100Mbps or higher”. IPDU should support communication protocols including SMTP, SSL, SNMP (v1, v3), Modbus, TCP/IP. Communication module should be field-replaceable so that there is no need to send the PDU back to the factory. | The Provision of bidding document remains unchanged.
9 | Vol-II, Section-3(A), Clause-3(A).9 IPDU & SENSORS, Sub Clause-15, Pg-35 | The IPDU should support “circuit breaker loss load alarm”. A sudden loss of circuit load when operating under full circuit load will result in a rack IPDU device state alarm. | Tender specification requires circuit breaker loss load alarm. We suggest that to avoid full circuit load, the thresholds need to be configured in the PDU, hence considering the same, please accept to revise this clause as "The Rack PDU shall be configured for generating an alarm when any bank exceeds its configured value, also IPDU should support Low Load configuration warning, with change in internal settings, which should help to indicate that a circuit breaker may have tripped" | The Provision of bidding document remains unchanged.
10 | Volume II, Section - 7 | Annexure_ Revised Table of Vol-II Section-7 Clause-7-4-2 Manpower - Revised Table of Manpower - on roll of contractor - HT & LT System , DG Engineer, IBMS/DCIM Operator, HVAC Engineer | Bidder request that the on roll manpower quantity be reduced , and the manpower to be permitted to be subcontracted . This is requested as these are non IT profiles and as such such a large quantum of manpower is not maintained on rolls and are deployed basis skill & qualification ask as per specific project requirements. The onus of project always lies with the prime bidder. Request revision from on roll manpower to off roll / on roll manpower. | The Provision of bidding document remains unchanged.
11 | Volume II, Section - 7 | Revised Table of Manpower - on roll of contractor | We understand that the employees can be on rolls of the Contractor i.e. the ME works contractor or the civil work contractor for the bid, pls confirm. | The Provision of bidding document remains unchanged as it is amply clear.
12 | SECTION 7: MAINTENANCE SERVICES | SLA clause provides for the minimum level of services required as per contractual obligations based on performance indicators and measurements thereof…. | SLA penalty is uncapped as of now, Bidder request that total SLA penalty in any quarter for not meeting the defined SLA targets be capped to a maximum of 5% of the Quarterly billing or QGR (i.e. AMC for that particular quarter) excluding taxes, in line with the industry standard. The overall annual penalty will be subject to a maximum of 5% of annual AMC value excluding taxes. This is in line with most IT / ME works Government tenders. | The Provision of bidding document remains unchanged.
13 | Vol-II, Section-1, Clause- 1.4.1.2-m, Pg-6 | 3.1 This Specification covers the following scope of works:EM survey / EM report (• EMI (Electro Magnetic Interference) and EMP (Electromagnetic Pulse) Survey, Measurement and Management Plan) - The EM survey can lead to material being required to mitigate the impact of radiation at the site during the project. These items are not yet added in the BOQ. | Request to add the line items required for handling of impact of EM radiation in the site in the price schedule BOQ. In case the estimation of quantity is not feasible a rate card may be sought with one quantity of such items from the bidder to allow for rate discovery. | Please refer Vol-II Section-4, Clause-4.3.4 Sub Clause-ii-C for details regarding deliverables. However, Additional requirement due to for handling/mitigating of impact of EM radiation in the site shall be taken seperately with the contractor as per provision of Contract.
14 | Vol-II, Section-1, Clause- 1.4.1.2-m, Pg-6 | 3.1 This Specification covers the following scope of works: - Liasioning with Haryana Electricity board for obtaining HT external electrical connection for Data Centre. | Please clarify if power connection is available at the site, and what is the scope expected from bidder in terms of liason with Haryana Electricity Board. | Power Connection for Data Centre requirement is not available at site. Necessary Liasioning with Haryana Electricity board for obtaining HT external electrical connection for Data Centre is in the scope of the bidder. Details shall be discussed with the successful bidder.