SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | General | GENERAL DELETIONS/SUBSTITUTIONS/ADDITIONS IN GCC TO BE READ ACCORDINGLY: In addition to the definition of words as contained in the various documents forming part of the contract, the following definitions shall also apply. - The word ‘Invitation for Bids' (IFB) or 'Invitation to Bid' (ITB) or `Invitation to Bid' (INV) shall have the same meaning as the words 'Notice Inviting Tender' (NIT). The words/expressions have been used interchangeably and shall carry the same meaning. - The words ‘Bid' or ‘Offer' shall have the same meaning as the words ‘Tender'. These words have been used interchangeably and shall carry the same meaning. - The words ‘Bidding Documents' or `NIT Documents’ shall have the same meaning as the words `Tender Documents’. This words/ expression has been used interchangeably and shall carry the same meaning. - The word ‘Bidder’ shall have the same meaning as the word ‘Tenderer’. These words have been used interchangeably and shall carry the same meaning. - The word ‘Project Manager’ shall have the same meaning as the word ‘Engineer-in-Charge’. These works have been used interchangeably and shall carry the same meaning. |
|  | General | It is the responsibility of the contractor to apprise himself fully about the location, local facilities available in the vicinity, sources of materials etc. No claim whatsoever and price adjustment shall be given by POWERGRID at any stage for lack of information or facilities or sources of material etc. not available in close vicinity. |
|  | GCC 1.1 (e) & 1.1 (dd) | Supplementing Sub-Clause GCC 1.1(ee) Time for Completion: Activities; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of:. Construction of tensile structure overhead shed at skating ground, Sector-43 township of POWERGRID, Gurugram. Spec. No.: CC/NT/W-MISC/DOM/A14/25/12918; 03 (Three Months). |
|  | GCC 1.0(m) | Replace the existing provision with the following: “Effective Date” means the date of Notification of Award/Brief Letter of Award from which the Time for Completion shall be determined. |
|  | GCC 1.0(u) | Replace the existing provision with the following: “Notification of Award/ Letter of Award” means the official notice issued by the Employer notifying the Contractor that his bid has been accepted. |
|  | GCC 1.0(n) & (v) | Supplementing Sub-Clause GCC 1.1(n) The Employer/ Owner is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurugram (Haryana) - 122001. Kind Attn.: Ch. GM(MM)/GM(MM) / Manager (MM) Telephone Nos.: +91-124-282-2389/2365/2381 Mobile: +91- 9205287432 Fax Nos.:- 0091-(0)124-2571831 Email Address: sangeeta@powergrid.in , arvindg@powergrid.in, rkdadarwal@powergrid.in |
|  | GCC 2.1 | Addition of following new Sub-Clauses after GCC 2.1 GCC 2.1.1 The Contracts to be entered into with the successful Bidder shall be a single contract covering all the Services related to Civil & Electrical works. GCC 2.1.2 The Contract will be signed in two originals and the Contractor shall be provided with one signed original and the rest will be retained by the Employer. GCC 2.1.3 The Contractor shall provide free of cost to the Employer all the engineering data, drawing and descriptive materials submitted with the bid, in at least two (2) copies to form a part of the Contract immediately after Notification of Award. |
|  | GCC 3.2 | Add following new clause at GCC 3.2 The work shall be strictly carried out as per POWERGRID’s Technical Specifications & Price Schedule for the subject package & as per terms & conditions mentioned in the bidding documents inter-alia including drawings provided by POWERGRID, if any, to the successful Bidder. The Contractor at his cost shall arrange, secure and maintain all insurance as may be pertinent to the works and obligatory in terms of law against all perils and the responsibility to maintain adequate insurance coverage at all time during the period of contract shall be of the Contractor alone. The Contractor’s failure in this regard shall not relieve him of any of his contractual responsibilities and obligations. The perils required to be covered under the insurance shall include all risks, but not limited to fire and allied risks, miscellaneous accidents, workmen compensation risks, loss or damage in transit, theft, pilferage, riot and strikes and malicious damages, civil commotions, weather conditions, accidents of all kinds et. The Contractor shall be responsible for the safety and security of employees of the Contractor and his sub-contractors throughout execution of the works. All costs on account of insurance liabilities covered under the Contract will be on Contractor’s account and will be included in the Contract Price. Materials and components not specifically stated in the various documents forming part of the Contract but which are necessary for completion of works shall be deemed to be included in the scope. All such materials and components shall be arranged and transported by the Contractor at his cost and expense. |
|  | GCC 4.1 | Replace the existing provision with the following: Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 38.1 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified at GCC 1.0 (dd). |
|  | GCC 5.3 | Replace the existing provision with the following: The price components shall remain FIRM throughout the currency of the contract and no Price Adjustment shall be applicable under any circumstances. |
|  | GCC 6.0 | Replace the existing provision with the following: 6.1 The prices that are quoted and indicated in the BPS shall include inter alia, all costs such as cost of necessary materials, their transportation to site, cost towards tools, equipment and machineries including cost of personnel that may be required for successful completion of the work as per the Technical Specifications, Vol-II including cost of site arrangement, overheads, insurance, whatsoever, as stipulated in the bidding documents for the total scope of work. Further the price for supply of services are excluding GST, if any, payable. The GST will be reimbursable (along with subsequent variation if any), by the Employer on the supply of services made by the Contractor but limited to the tax liability on the transaction between the Employer and the Contractor. 6.2 Employer would not bear any liability on account of any other taxes, duties, levies applicable locally. 6.3 Employer shall, deduct taxes at source as per the applicable laws/rules, if any, and issue Tax Deduction at Source (TDS) Certificate to the Contractor. The recovery of TDS under GST/Income Tax Act and any other acts as per Govt. regulation related to this work shall be done by the Employer on behalf of ‘Owner‘. TDS so deducted by Employer on behalf of the ‘Owner‘ shall be deposited with the relevant tax authorities and TDS certificates shall be issued on behalf of the Owner using PAN, TIN, TAN of Owner. Relevant challans and copies of the TDS certificates shall be forwarded to ‘Owner for filing necessary returns. In case, wherever E-filing system is applicable, the relevant information would be given to the Owner for issuing TDS certificate, filing returns, etc. 6.4 Reimbursement of GST by the Employer shall be at the rate applicable on the SAC of the services supplied by the Contractor to the Employer. The reimbursement of GST except GST on advance payment shall be against Invoice/Debit Note containing particulars specified under the GST Act and related Rules, Notifications, etc. as notified by the Government in this regard. In the event that the Contractor fails to provide the invoice in the form and manner prescribed under the GST Act and Rules, the Employer shall not be liable to make any payment against such invoice. Reimbursement of GST payment against Advance payment shall be against a proforma invoice. Further, the Contractor shall, within 7 days from the date of receipt of Advance, furnish an Advance Receipt Voucher to the Employer, as prescribed under the GST Law. If there is difference in SAC classification and corresponding rate of GST of an item as confirmed/deemed confirmed by the bidder in its bid and SAC and corresponding rate of GST as interpreted under any interpretation/ judgment/ Notification/ Circular issued under the GST law before or after the award of contract, GST reimbursable to the bidder/Contractor shall be lower of the GST applicable at the rate as confirmed/deemed confirmed in the bid or actual GST paid/payable by the bidder for that item. 6.5 The Contractor shall comply with all tax laws in force in India. The Contractor shall indemnify and hold harmless the Employer from and against any and all liabilities, interest, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such tax laws by the Contractor or its personnel, including the Subcontractors and their personnel. 6.6 Employer’s GSTIN number in each state/UT is published on the Employer’s company website https://www.powergrid.in . While raising invoice/proforma invoice for Supply of Services, the Contractor shall invoice the Owner using the GSTIN of Employer in the state/UT in which the service or part thereof is to be rendered. 6.7 Notwithstanding anything above or elsewhere in the Contract, in the event that the input tax credit of the GST charged by the Contractor is denied by the tax authorities to the Employer for reasons associated with non-compliance/ incorrect compliance by the Contractor, the Employer shall be entitled to recover such amount from the Contractor by way of adjustment from any of the subsequent invoices submitted by the Contractor to the Employer. In addition to the amount of GST, the Employer shall also be entitled to recover interest and penalty, in case any interest and/or penalty are imposed by the tax authorities on the Employer for incorrect/wrong availment of Input Tax Credit. The Employer shall determine whether the denial of credit is linked to the non-compliance/ incorrect compliance of the Contractor and the said determination shall be binding on the Contractor. |
|  | GCC 8.2 | Advance Payment Security: Not Applicable |
|  | GCC 8.3.1 | Replace first para of sub-clause GCC 8.3.1 with the following:- The Contractor shall, within ten (10) days of the Letter of Award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor from time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Alternatively, in place of submission of Contract Performance Guarantee, Bidder may opt for pro-rata deduction at the rate of 10 % from the Running Bill of the contractor as Security Deposit. The deductions shall be continued till the total amount towards Security Deposit reaches 10 % of the contract value. The CPG/Security deposit shall be released within 90 days after completion of Defect Liability period. |
|  | GCC 8.3.1 | Supplementing Sub-Clause GCC 8.3.1 8.3.1.1 If the Contractor delays submission of the performance security(ies) vis-à-vis the period specified in Clause GCC 8.3.1, then without prejudice to any other rights or remedies available with the Employer, following shall also be applicable: - The Defect Liability Period pursuant to Clause GCC 40 for the Facilities or any relevant part thereof covered under the said performance security shall stand extended and the Contractor shall accordingly extend the validity of the Contract Performance Security to be furnished as per Clause GCC 8.3.1 by the period of delay as per Clause GCC 8.3.1.1 (c), over and above the period required as per the Contract. - Alternatively, if the Contractor fails to extend the validity of the performance security pursuant to Clause GCC 8.3.1.1 (a), an amount @prevailing SBI Card Rate applicable for Inland Bank Guarantee +2% per annum on the performance security amount corresponding to the Facilities or any relevant part thereof covered under the said performance security, for the period of delay as per Clause GCC 8.3.1.1 (c) shall be paid by the Contractor to the Employer. The Employer may, without prejudice to any other method of recovery, deduct the amount worked out as above from any monies due or to become due to the Contractor under the Contract. - The period of delay for the above purpose shall be the time elapsed between the due date for submission of performance security as per the Contract and the date of performance security. - In case the Contractor fails to submit the performance security within 90 days of the Notification of Award, the Employer, without prejudice to any other rights or remedies it may possess under the Contract, may consider the bid submitted by the Contractor in future packages as non-responsive in line with ITB 13.6 and/or may terminate the Contract forthwith pursuant to GCC Clause 17. 8.3.1.2 The above extension of Defect Liability Period or deduction shall not relieve the Contractor from any of his obligations and liabilities under the Contract. 8.3.1.3 The Employer shall be sole judge in above regard. 8.3.1.4 Apart from the performance security (ies) to be furnished as per Clause GCC 8.3.1 above, additional performance securities, as specified in the Bidding Documents, shall be arranged and furnished by the Contractor at any time after the Notification of Award. The submission of these performance securities to the Employer shall, however, be one of the conditions precedent for release of payment due against such equipment/ works for which the said performance security is required to be submitted. |
|  | GCC 8.3.2 | Replace the existing provision with the following: The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer as stipulated in SCC or in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergridindia.com. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–CC. Name of Depositor; Name of the Contractor/ Collaborator/ Tower manufacturer/ Licensor etc.. Vendor Code, if applicable; POWERGRID vendor code of the Contractor Collaborator/ Tower manufacturer/ Licensor etc., if existing. Payment Remarks; Performance Security for Construction of tensile structure overhead shed at skating ground, Sector-43 township of POWERGRID, Gurugram. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. |
|  | GCC 8.3.3 | Replace sub-clause 8.3.3 with the following:- Reduction in the security pro rata to the Contract Price of any part of the Facilities is not admissible. However, if the Defects Liability Period has been extended on any part of the Facilities pursuant to GCC Sub-Clause 18.0 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor pursuant to GCC Sub-Clause 40.0, is liable for an extended warranty obligation, the performance security shall be reduced to ten percent (10%) of the value of the component covered by the extended warranty. |
|  | GCC 8.3.6 | Add new sub Clause GCC 8.3.6 During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque/ online payment through POWERGRID ONLINE PAYMENT UTILITY, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 8.4 | Replace the existing provision with the following: Issuing Banks The Bank Guarantee for Performance Security are to be provided by the Contractor, which should be issued either : (a) by a Public Sector Bank located in India, or (b) a scheduled Indian Bank having paid up capital (net of any accumulated losses) of Rs. 1,000 Million or above (the latest annual report of the Bank should support compliance of capital adequacy ratio requirement) or (c) by a foreign bank or a subsidiary of a foreign bank, acceptable to the Employer, with overall international corporate rating or rating of long term debt not less than A- (A minus) or equivalent by a reputed rating agency. Further, the Bank Guarantee should be confirmed by either (i) its corresponding bank located in India; or (ii) a Public Sector Bank located in India; or (iii) a scheduled commercial private bank located in India as per para (b) above. The contractor has the option to submit BG (towards Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; Branch IFSC Code; POWERGRID Current A/c No.. STATE BANK OF INDIA, 4RTH & 5TH FLOOR PARSVNATH CAPITAL TOWER BHAI VEER SINGH MARG GOLE MARKET NEW DELHI 110001.; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram.; ICIC0002451; 000705002702​. In addition to the above, the Bank Guarantee (towards Performance Security) should be submitted in the Physical form as specified in GCC Clause 8. |
|  | GCC 11.4, 11.5 & 11.6 | Add following new sub-Clauses in GCC clause 11.1: 11.4 The sources of the materials to be provided/ supplied by the Contractor shall be got approved from Engineer-in-charge. The various field and laboratory tests involved as per the Quality Plan/ Technical Specifications/ directions of Engineer-in-charge are to be carried out by the successful Bidder (contractor) at his own cost and no additional payment shall be considered on this account. The Bidders should take into account these aspects while submitting their offers. 11.5 Technical Specifications (TS): Work shall be executed as per POWERGRID’s Technical Specifications as detailed in Volume-II of the Bidding Documents & CPWD Specifications for DSR based items. Also latest revisions of relevant IS Codes shall be applicable for the work. For non-scheduled items, work shall be executed as per TS and manufacturer’s specifications/relevant IS codes. 11.6 SFQP of POWERGRID ‘Standard Field Quality Plan’ for “Civil works for Site Packages” (SFQP No. - DOC No. C/FQA/SFQP/SITE-CIVIL-2012 REV.-05 dated 10-07-2024) enclosed as Annexure-SFQP (Volume-III) shall be followed during execution of work. |
|  | GCC 15 & Schedule-A | Supplement GCC Clause 15 with the following : During execution of the contract, POWERGRID reserves the right to increase or decrease the quantity of individual item upto any extent. The overall limit of Quantity variation in the contract shall be upto (+/-) 25% (Twenty Five Percent) of the Contract Price and there will not be any variation limit for individual items of the Contract. Thus, individual items may vary up to any extent. This supersedes the related provisions of GCC and provisions of clause mentioned in Schedule– A of GCC. In case the overall contract price varies by more than ±25%, all such items where executed quantity has varied by more than ±25% will be identified. The rates for all such items for the quantity in variance of ±25% shall be determined as per Clause No. 15.0 of GCC. |
|  | GCC 17.2.1 | Replace GCC 17.2.1 with the following: 17.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons therefor to the Contractor, referring to this GCC Sub-Clause 17.2: (a) if the Contractor becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Contractor is a corporation, a resolution is passed or order is made for its winding up (other than a voluntary liquidation for the purposes of amalgamation or reconstruction), a receiver is appointed over any part of its undertaking or assets, or if the Contractor takes or suffers any other analogous action in consequence of debt (b) if the Contractor assigns or transfers the Contract or any right or interest therein in violation of the provision of GCC Clause 37. (c) if the Contractor, in the judgment of the Employer has violated the ‘Code of Integrity for Public Procurement’ attached as Appendix-III to the Special Conditions of Contract, in competing for or in executing the Contract. In persuasions to its policy for ‘Code of Integrity for Public Procurement’, the Employer will take appropriate measures in line with the above policy if it determines that the firm has, directly or through an agent, violated this Code of Integrity in competing for or in executing, the contract in question. |
|  | GCC 20.6 | Replace the existing provision with the following: As brought in clause 6.0 and subject to as hereinafter provided all charges on account of GST on materials obtained for the works from any source shall be borne by the Contractor. The liability of the Employer shall be limited to reimbursement of GST on the supply of services made by the Contractor. The Input Tax Credit (ITC) available, if any, under GST as per the relevant Government laws wherever applicable has, however, been taken into account by the Contractor. |
|  | GCC 22.3.1 | Supplementing Sub-Clause GCC 22.3.1 Notwithstanding the above, the Contractor shall furnish to the Employer the details/documents evidencing the Contractor’s compliance to the laws applicable to establishments engaged in building and other construction works, as may be sought by the Employer. In particular the Contractor shall submit quarterly certificate regarding compliance in respect of provisions of Employees’ Provident Fund and Misc. Provisions Act 1952 to the Employer. For this purpose, the Contractor as well as its Sub-Contractor(s) should have Provident Fund Code Number and all the workers deployed by the Contractor or Sub-Contractor must be enrolled as members of Provident Fund having an Universal Account Number (UAN). |
|  | GCC 22.6 | Supplementing Sub-Clause GCC 22.6 Labour having “Recognition of Prior Learning”(RPL) Certification (under Pradhan Mantri Kaushal Vikas Yojana(PMKVY)) can also be employed by the Contractor. |
|  | GCC 22.9 (a) | Replace the existing provision with the following: Employee’s Compensation Act 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment. |
|  | GCC 22.9.1.1 | Addition of following new Sub-Clauses after GCC 22.9.1 GCC 22.9.1.1 - The Contractor shall (a) establish an operational system of managing environmental impacts, (b) carry out all the monitoring and mitigation measures set forth in the environment management plan attached to the Special Conditions of Contract as Appendix-I, and (c) allocate the budget required to ensure that such measures are carried out. The Contractor shall submit to the Employer (quarterly) semi-annual) reports on the carrying out of such measures. - The Contractor shall adequately record the conditions of roads, agricultural land and other infrastructure prior to transport of material and construction commencement, and shall fully reinstate pathways, other local infrastructure and agricultural land to atleast their pre-project condition upon construction completion. - The Contractor shall undertake detailed survey of the affected persons during transmission line alignment finalization under the Project, where applicable. and The Contractor shall conduct health and safety programme for workers employed under the Contract and shall include information on the risk of sexually transmitted diseases, including HIV/AIDS in such programs. |
|  | GCC 23.3 | Replace the existing provision with the following: Appendix -II to SCC. |
|  | GCC 31.2 | Add following new clause at GCC 31.2 PROGRESS REPORT During execution of the Contract, the Contractor shall furnish monthly Progress Report to POWERGRID in a format as specified by the EMPLOYER or the Engineer-in-Charge indicating the progress achieved during the month, and total progress upto the month against the scheduled, reasons for delay, if any, and anticipated completion dates in respect of activities covered in the programme/schedules referred to above, if called for by the Owner or the Engineer-in-Charge resources data in a specified format and within a time schedule. The Contractor shall also furnish any other information that is necessary to ascertain progress, if called for by the Engineer-in-Charge. |
|  | GCC 31.3 | Add following new clause at GCC 31.3 CO-OPERATION WITH OTHER AGENCIES The Contractor shall attend at his cost all the meeting with the Engineer-in-Charge and other Sub-Contractors for the Contract. The Contractor shall attend such meetings as and when required and fully co-operate, with such persons and agencies involved. |
|  | GCC 32.4 | Add following new clause at GCC 32.4 The work will also be subjected to the inspection by the Chief Technical Examiner of the Chief Vigilance Commissioner (CVC) and the Contractor shall make necessary arrangements whenever required for this inspection without any additional cost to the Owner. |
|  | GCC 38.0 | Replace GCC 38.0 as follows: Liquidated Damages: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 38 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to Zero point Zero Five percent (0.05%) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of Five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damages which will be suffered by the employer for default on the part of the contractor and said amount will be payable without proof of actual loss or damage caused by such default The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. |
|  | GCC 40.1 | Replace the first para of existing provision with the following: The rates quoted in tender are inclusive of 01 years guarantee and cover maintenance and replacement of defective all items and parts of the high mast flag system except flags. The supply of new flags and their replacement are not included in the scope of contractor from the date of handing over the installation. In guarantee period if any defect found then the same shall be replaced or rectified by the contractor at his own cost to the satisfaction of the Officer in charge/consignee of POWERGRID within one week after the date of notice, otherwise recovery as decided by Officer in charge/consignee shall be made from the security deposit amount or forfeit of Performance Bank Guarantee. |
|  | GCC 41 | Supplementing GCC 41 with the following: Vide Notification dated 8th May 2017 its revision dated 29th May 2019 by Ministry of Steel has published “Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement”. The Contractor shall comply with the guidelines specified in the policy including subsequent amendments/ modifications, if any. Accordingly, the Contractor shall be required to provide a value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the Policy. Such certificate shall be filed within 60 days of commencement of each half year, to the respective executing Region of POWERGRID and shall continue to be filed till the completion of supply of the said products. Further, if the Domestic manufacturer from whom the Contractor had proposed to source the Iron & Steel products is changed during execution of the Contract, the Contractor shall furnish (i) authorization certificate, if applicable, (ii) affidavit of self-certification and (iii) value- addition certificate from the new Domestic manufacturer. |
|  | GCC 41 | Supplementing the existing provision with the following: The insurance policy should cover total value of the project and should be valid from Commencement of Work upto taking over by the Employer. |
|  | GCC 41.3 (a) | Replace the existing provision with the following: Third party liability shall cover bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities which have been accepted by the Employer) occurring in connection with Civil Work. Third party liability insurance with a minimum coverage of Rs.100,000/- (Rupees one hundred thousand only) for each occurrence. The third party liability limit shall be 10% of the project value for single occurrence/ multiple occurrences in aggregate during the entire policy period. The policy shall have to be effective from the date of mobilization as per contract and shall have to be valid up to Defect Liability Period. |
|  | GCC 41.14 | Add following new clause at GCC 41.15 Automobile Liability Insurance The Contractor shall ensure that all the vehicles deployed by the Contractor or its Subcontractors (whether or not owned by them) in connection with the project are duly insured as per RTA act. Further the Contractor or its Subcontractors may also take comprehensive policy (own damage plus third party liability) of each individual vehicles deployed in the project on their own discretion in their own name to protect their own interest. |
|  | GCC 41.15 | Add following new clause at GCC 41.16 Workmen Compensation Policy: - Workmen Compensation Policy shall be taken by the Contractor in accordance with the statutory requirement applicable in India. The Contractor shall ensure that all the workmen employed by the Contractor or its Subcontractors for the project are adequately covered under the policy. - The policy may either be projecting specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Taking Over of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen Compensation Policy’. - Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work, the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal’s statutory liability to persons employed by the Contractor. The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the ‘Workmen Compensation Policy’ effected by the Contractor. |
|  | GCC 41.A | Supplementing the existing provision with the following: The insurance policy should cover total value of the project and should be valid from Commencement of Work upto taking over by the Employer. |
|  | GCC 41.A.3 (a) | Replace the existing provision with the following: Third party liability shall cover bodily injury or death suffered by third parties (including the Employer’s personnel) and loss of or damage to property (including the Employer’s property and any parts of the Facilities which have been accepted by the Employer) occurring in connection with Civil Work. Third party liability insurance with a minimum coverage of Rs.100,000/- (Rupees one hundred thousand only) for each occurrence. The third party liability limit shall be 10% of the project value for single occurrence/ multiple occurrences in aggregate during the entire policy period. The policy shall have to be effective from the date of mobilization as per contract and shall have to be valid up to Defect Liability Period. |
|  | GCC 41.A.16 | Add following new clause at GCC 41.A.16 Automobile Liability Insurance The Contractor shall ensure that all the vehicles deployed by the Contractor or its Subcontractors (whether or not owned by them) in connection with the project are duly insured as per RTA act. Further the Contractor or its Subcontractors may also take comprehensive policy (own damage plus third party liability) of each individual vehicles deployed in the project on their own discretion in their own name to protect their own interest. |
|  | GCC 41.A.17 | Add following new clause at GCC 41.A.17 Workmen Compensation Policy: - Workmen Compensation Policy shall be taken by the Contractor in accordance with the statutory requirement applicable in India. The Contractor shall ensure that all the workmen employed by the Contractor or its Subcontractors for the project are adequately covered under the policy. - The policy may either be projecting specific covering all men of the Contractor and its Subcontractors. The policy shall be kept valid till the date of Taking Over of the project. Alternatively, if the Contractor has an existing ‘Workmen Compensation Policy’ for all its employees including that of the Subcontractor(s), the Contractor must include the interest of the Employer for this specific Project in its existing ‘Workmen Compensation Policy’. - Without relieving the Contractor of its obligations and responsibilities under this Contract, before commencing work, the Contractor shall insure against liability for death of or injury to persons employed by the Contractor including liability by statute and at common law. The insurance cover shall be maintained until all work including remedial work is completed including the Defect Liability Period. The insurance shall be extended to indemnify the Principal for the Principal’s statutory liability to persons employed by the Contractor. The Contractor shall also ensure that each of its Subcontractors shall effect and maintain insurance on the same basis as the ‘Workmen Compensation Policy’ effected by the Contractor. |
|  | GCC 41 | Supplementing the GCC 41 with the following: The scope of such insurance shall be adequate to cover the replacements/ reinstatement cost of the Work/ equipment/ materials for all risks. The insurance policies to be taken should be on replacement value basis and/or incorporating escalation clause. Further, the scope of insurance cover is specified as per following: S.N; Type of Insurance; Insurance Amount; Validity of the Insurances. From; Till. Civil works; Total value of the project; Commencement of Work; Upto taking over by Employer. Third Party Liability Insurance; Min coverage of 01 lakh for each occurrence upto 10% of the project value for single occurrence/ multiple occurrences.; Commencement of Work; Defects Liability Period. Workmen Compensation Insurance; Policy shall cover all the men of Contractor and its sub-contractors as per statutory requirements.. Automobile Liability Insurance; All the vehicles deployed by the Contractor or its Subcontractors (whether or not owned by them) in connection with the supply and installations of the Facilities in the project are duly insured as per RTA act. Further, the Contractor or its Subcontractors may also take comprehensive policy (own damage plus third-party liability) of each individual vehicle deployed in the project on their own discretion in their own name to protect their own interest.. |
|  | GCC 41 | Supplementing the GCC 41 with the following: All the deployed manpower by contractor shall be fully insured through a recognized Insurance Agency against any type of electrical or any kind of hazards/ accidents for associated work. The agency shall take adequate group insurance coverage under workman compensation Act applicable to work on electrical installation maintenance work of his deployed manpower/ workers as required during the currency period. Insurance premium shall be borne by the agency which shall be fully reimbursed by POWERGRID to the contractor after submission of relevant documents/receipts of insurance premium. Any statutory requirement for executing this contract has to be fulfilled by the agency at his own cost. It shall be obligatory on the part of the agency to provide a copy of the group insurance policy to Engineer-In-Charge before deployment of personnel for the subject cited work. |
|  | GCC 44.2 | Add following new clause at GCC 44.2 Further, the Contractor shall not subcontract any work to a subcontractor/sub vendor from such countries which shares a land border with India unless such subcontractor/sub vendor fulfills all requirement in regard to ‘Bidder from a country which shares a land border with India’ as per ITB clause 2.1. This restriction on subcontracting shall not be applicable for procurement of raw materials, components, sub-assemblies etc. However, in case of finished goods procured directly/ indirectly from the vendors from the countries sharing land border with India, such vendor will be required to be registered with the Competent Authority. |
|  | GCC 44.3 | Add following new clause at GCC 44.3 The Contractor shall furnish the details of items, components, raw materials, services etc. procured from MSEs and consumed for completion of scope of works under the contract. The details shall be furnished as per the format enclosed at Section VI, Forms, Volume-I of the bidding documents at the time of raising bills for payment against the supplies made/works done. |
|  | GCC 48.3 | Add following new clause at GCC 48.3 Risk and Cost During the period of construction/Renovation and also during defect liability period, if the contractor fails to rectify any defect pointed out to him, the same shall be got done by POWERGRID at the risk and cost of contractor and recovered from the Contract Performance Guarantee or any other amount payable to the Contractor. |
|  | GCC 55.3 | Add following new clause at GCC 55.3 Bill Tracking System Prior to submission of bills in physical form, the Contractor shall submit its bills using POWERGRID’s Vendor Bill Tracking System as per procedure detailed herein below. Further, the Contractor may also track the status of its bills using POWERGRID’s ‘On-line Vendor Bill Tracking System’. To use this system the Contractor is required to get itself registered once online at POWERGRID’s ERP Portal with the link URL (https://etender.powergrid.in). Once registered, the Contractor may track status of bills submitted, passed and paid by POWERGRID’s Corporate Centre and Regional Office(s) under this Contract and other Contracts awarded on it by POWERGRID by following the method detailed herein below: - Once registered, the Contractor can log-in to POWERGRID’s Vendor Bill Tracking System (BTS) with Vendor Log-In ID and Password. - After login as at (a) above, Contractor is required to make the entry on POWERGRID’s ERP Portal under the tab “Submit New Invoice” and shall fill all details along with the MSE status. Upon submission, a 16 digit unique BTS number will be generated and the Contractor will receive an automated e-mail forwarding the unique BTS number. - The physical bills alongwith printed copy of e-mail received from BTS (unique BTS number) shall be submitted by the Contractor. - On receipt of physical bill, concerned POWERGRID’s official shall online acknowledge the receipt of bill. This action will trigger an automated mail to the Contractor intimating that the physical copy of the bill has been received and is under verification/ processing. However, on receipt of incomplete bill and/or non-receipt of physical bill by POWERGRID official, the incomplete bills/ digital entry in BTS (as the case may be) shall be returned to the Contractor by POWERGRID, which can be viewed under the tab “Invoice Returned”. - The day the payment is made, a mail stating the “Bill number, net payment amount and details of the bank from where the payment has been made” will be sent to the Contractor. The status of Bill submitted by the Contractor can be checked through the BTS number under tab “Invoice Submitted”. |
|  | GCC 55.4 | Add following new clause at GCC 55.4 Paying Authority In-Charge (F&A), PPPFC Manesar shall be the Paying Authority. Engineer-in-Charge will verify the bills and forward to Paying Authority for release of payment, subject to deductions which include statutory deductions and any deductions made by site. |
|  | GCC 56.0 | Replace the existing provision with the following: The price components shall be FIRM throughout the currency of the contract and no price escalation shall be payable under any circumstances. |
|  | GCC 57 57.3 57.4 57.5 | Replace the existing provision with the following: Save as hereinafter provided, such decision in respect of every matter so referred shall be final and binding upon the parties until the completion of the Works and shall forthwith be given effect to by the Contractor who shall proceed with the Works with all due diligence, whether he or the Employer requires arbitration/Conciliation as hereinafter provided or not. If after the Engineer-in-Charge has given written notice of his decision to the parties, no claim to arbitration/Conciliation has been communicated to him by either party within thirty (30) days from the receipt of such notice, the said decision shall become final and binding on the parties. In the event of the Engineer-in-Charge failing to notify his decision as aforesaid within thirty (30) days after being requested as aforesaid, or in the event of either the Employer or the Contractor being dissatisfied with any such decision, or within thirty (30) days after the expiry of the first mentioned period of thirty (30) days, as the case may be, either party may require that the matters in dispute be referred to arbitration/Conciliation as hereinafter provided. |
|  | GCC 59 | Replace the existing provision with the following: 59.1 The arbitration shall be conducted by a sole arbitrator in case the amount of claim is less than Rs. 25 Crore and by three member arbitral tribunal in case the amount of claim is greater than Rs. 25 Crore. Sole Arbitration The sole Arbitrator shall be chosen from a panel of empanelled Arbitrators maintained by POWERGRID. The same shall comprise of retired Judges and retired Senior executives of PSUs other than POWERGRID. Further, the choice of sole Arbitrator shall be governed by the amount of claim in the following manner: Sl no:; Claim amount; Work Experience/ Qualifications. 1; < Rs. 10 Crore; Sole arbitrator-Retired Senior Executives of PSUs other than POWERGRID/Retired Distt Judges/ High Court Judges.. 2; Rs.10 Crore- Rs.25 Crore; Sole arbitrator- Retired High Court/Supreme Court Judges. - In case of invocation of arbitration by POWERGRID, POWERGRID shall, within 30 days, send a list of names of 3 arbitrators from its list/database of Arbitrators and the contractor shall within the period of further 30 days select any one person to act as “Sole Arbitrator”, which will be confirmed by POWERGRID and matter will be referred to such appointed Arbitrator for further arbitration proceedings. - In case of invocation of arbitration by the Contractor, the Contractor shall request POWERGRID for its database of Arbitrators/ chose from the list of Arbitrators available on POWERGRID’s website, and the contractor shall, within 30 days, select any one Arbitrator from the above to act as “Sole Arbitrator”, which will be confirmed by POWERGRID within 30 days and matter will be referred to such appointed Arbitrator for further arbitration proceedings. If the parties fail to appoint sole arbitrator within sixty (60) days after receipt of a notice from the other party invoking Arbitration, the appointment of sole arbitrator shall be done by Courts as per the provisions of Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof. Three member arbitral tribunal The arbitration shall be conducted by three arbitrators, who are retired High Court/Supreme Court Judges, one each to be nominated by the Contractor and the Employer and the third to be appointed by both the arbitrators in accordance with the Indian Arbitration & conciliation Act. If either of the parties fails to appoint its arbitrator within sixty (60) days after receipt of a notice from the other party invoking the Arbitration clause, the arbitrator appointed by the party invoking the arbitration clause shall become the sole arbitrator to conduct the arbitration. In case of failure of the two arbitrators appointed by the parties to reach upon a consensus regarding appointment of presiding Arbitrator, within a period of 30 days from the appointment of the arbitrator appointed subsequently, the presiding arbitrator shall be appointed by Courts as per the provisions of Arbitration & conciliation Act. 59.2 The cost of arbitral proceedings inter-alia including the Arbitrators’ fee, logistics and any other charges shall be equally shared by both parties. In case of Sole Arbitrator, the fees to be paid to the sole Arbitrator shall be as per the terms of empanelment in POWERGRID whereas in case of the three member tribunal, the Arbitrator’s fees shall be as agreed upon by the Arbitrators in line with the Arbitration & Conciliation Act. However, the expenses incurred by each party in connection with the preparation, presentation, etc. of its proceedings shall be borne by each party itself. 59.3 The language of the arbitration proceedings and that of the documents and communications between the parties shall be English. The arbitration shall be conducted in accordance with the provisions of the Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof. The venue of arbitration shall be New Delhi. 59.4 The decision of the sole arbitrator/ the majority of the arbitrators, as the case may be, shall be final and binding upon the parties. In the event of any of the sole arbitrator/ any of the aforesaid arbitrators dying, neglecting, resigning or being unable to act for any reason, it will be lawful for the parties to nominate another sole arbitrator/ another arbitrator in place of the outgoing arbitrator. 59.5 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute/ difference (other than those related to taxation matters) between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018 and DPE OM No. DPE-GM-05/0003/2019-FTS-10937 dated 20.02.2020. The decision through AMRCD will be final and binding on all the concerned. 59.6 During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. |
|  | GCC 62.0 | Add following new clause at GCC 62.0 APPROVAL OF STATUTARY/GOVT. BODIES The Contractor shall wherever required, obtain approval of the Statutory/ Govt./Local bodies for and on behalf of the EMPLOYER, during the construction/renovation and after completion of the project. However, the employer may also help the contractor to the extent of writing letters to the local bodies for expediting approval, if required. The fee/charges levied by the Statutory/Govt./Local bodies shall be reimbursed to the contractor on production of documentary proof. |
|  | GCC 63.0 | Add following new clause at GCC 63.0 Codes and Standards Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied after approval by the Employer. |
|  | GCC Clause No. 59.0 in Schedule-A | Deleted |
|  | Appendix-I to SCC | Enclosed herewith |
|  | GCC 66 | Add following new clause at GCC 66.0 Conciliation 66.1 The mechanism of Dispute resolution through Conciliation shall be available in cases where the amount involved in the dispute exceeds INR 1 Cr. 66.2 The settlement of Disputes through conciliation mechanism shall be done by the Conciliation Committee of Independent Experts (CCIE) constituted by Ministry of Power, Govt. of India as per the procedure outlined in its OM dated 29.12.2021 as detailed herein below and its subsequent amendments/modifications (if any). 66.2.1 Each member of CCIE would be paid a sum of Rs. 50,000/- as sitting fee per sitting. In addition, Rs. 5,000/- per sitting will be paid for local transport charges for each day of proceeding. The conciliation proceedings shall be completed in each case through 5 sittings in a period of not more than three months from the date the reference made to the CCIE. In exceptional cases, if any dispute so merits, the time period may be extended at the discretion of Conciliation Committee (with reasons to be recorded in writing), for a further period of three months. In case, a particular dispute requires more than 5 sittings, the same may be held at the discretion of the CCIE but with a cap on payment of fee for 5 sittings only. The local transport charges shall, however, be paid as provided for each day of sitting beyond the 5 sittings. 66.2.2 The CCIE shall hold day to day sitting at the Headquarter of the Employer or New Delhi and may hold as many sittings every month as it deems appropriate keeping in view the volume of work. 62.2.3 All expenditure incurred on the conciliation proceedings including payment of fees to the Conciliators, office space, logistic, secretarial assistance and other incidental expenses etc. shall be borne by the Employer initially. Thereafter it shall be shared equally by both parties on completion of the conciliation process. 66.3 The procedure of CCIE shall not be treated as alternate arbitration proceedings where both parties come with Statement of claims/defence, arguments/counter arguments, rejoinders, written submissions etc., aided by their respective lawyers. The forum of CCIE is a conciliation forum, where mutual give and take constitutes the essence, rather than strict legal positions of the parties. Hence, the parties are expected to be brief and to the point before the committee with regard to their respective stance and view the exercise in the spirit of conciliation / settlement. 66.4 The Standard Operating Procedure for the conciliation mechanism shall be as follows: i) On receipt of a reference from the Contractor for conciliation of dispute, the concerned Executive Director (Region) of the Employer shall send a communication within 7 working days thereby inviting the Contractor to depute a team of their representatives to interact with the Employer to crystallize the issues and prepare the agenda containing the gist on each dispute. ii) Once a conciliation request has been raised by the contractor, within 30 days the same shall be referred to the CCIE in the event of the matter remaining unresolved internally. iii) The Employer will also be free to suggest the option of resolution of disputes by conciliation in case a dispute has arisen. The contractor may select any one of the CCIEs as constituted by MOP after leaving out those CCIEs which are unavailable due to work load or any other reason as maintained by Central Electricity Authority (CEA). iv) The Conciliation process shall be conducted under Part III of the Arbitration and Conciliation Act, 1996. v) The Conciliation Committee would either be able to resolve and settle the dispute(s) between the parties, or the process may fail. vi) In the event of the conciliation proceedings being successful, the parties to the dispute would sign the written settlement agreement and the conciliators would authenticate the same. Such settlement agreement would then be binding on the parties in terms of Section 73 of the Arbitration and Conciliation Act, 1996. vii) After successful conclusion of Conciliation, proceedings, the Parties to the conciliation process, have to undertake and complete all necessary actions for implementation of the terms of settlement within a period of 30 days from execution of settlement agreement, unless a different timeline not exceeding 60 days is agreed upon in settlement agreement. All pending claims of parties, in connection with the dispute, before any other legal forum are to be withdrawn within the said 30 days in pursuance of the settlement agreement. viii) In case of failure of the conciliation process at the level of the Conciliation Committee, the parties may withdraw from conciliation process and take recourse to the laid down legal process of Courts. However, the option of Arbitration would not be available once the conciliation mechanism has been exercised. 66.5 In cases of disputes pending before the Arbitration Tribunals or the Courts, both of the parties (i.e. Employer and Contractor) need to agree to explore the possibilities of conciliation through the Conciliation Committee of Independent Experts. In case of such agreement, an appropriate reference shall be made to the Conciliation Committee, upon which the Committee shall proceed to examine such reference(s). The option of resolution through conciliation through CCIE would be open only in the event of the parties withdrawing from arbitration proceedings and undertaking to forego their rights to proceed for further arbitration in the subject matter. However, other legal remedies would be open to the parties in the event of the conciliation proceedings not being successful. 66.6 During settlement of disputes and conciliation proceedings, both parties shall be obliged to carry out their respective obligations under the Contract. |
|  | GCC 67.0 | Add following other special conditions at GCC 67.0 - Contractor has to arrange all required insurance/s and safety measures at his own cost. All statutory requirements inter alia including requisite insurances as per Govt. of India laws, by-laws etc. shall be complied by the contractor during the currency of the contract. All safety measures shall be taken by contractor at his own cost as directed by Engineer-in-charge, if any - The bidder shall fully apprise himself of the prevailing conditions at the proposed site, Climatic conditions including monsoon patterns, local conditions and site-specific parameters, availability of construction materials and shall include for all such conditions and contingent measures in the bid, including those which may not have been specifically brought out in the specifications. - The proper coordination & execution of all works / activities shall be the sole responsibility of the Contractor. He shall plan all such activities in advance and execute in such a manner that interfacing activities do not become bottlenecks. - The Contractor shall arrange all labour, tools, equipment, materials, temporary works, constructional plant & machinery, fuel supply, transportation and all other incidental items not shown or specified but as may be required for complete performance of the Works in accordance with drawings, specifications and direction of Engineer in Charge. - Water Supply shall be provided at one point near site. Contractor has to make their own arrangements for pipelines, connections, storage of water, distributions, etc. However, if water source is not available nearby the site, contractor has to make their own arrangements. - Electric Supply shall be provided free at one point near site. Contractor has to make their own arrangements at his own cost for the necessary switch boards, switchgears, wires, etc. However, contractor shall make his own arrangements for suitable standby power. - Contractor has to clean the site prior to handing over of the completed works. |
|  | GCC 68.0 | Add new Clause GCC clause 68.0: 68.0 POWERGRID Whistle Blower and Fraud Prevention Policy The Contractor along with its associate/ collaborators/ sub-contractors/ sub-vendors/consultants/ service providers shall strictly adhere to the Whistle Blower and Fraud Prevention Policy of Employer displayed on its tender website https://apps.powergrid.in/pgciltenders/u/default.aspx and https://www.powergrid.in/index.php/en/code-conductpolicies. The Contractor along with their associate / collaborator / subcontractors / sub-vendors / consultants / service providers shall observe the highest standard of ethics and shall not indulge or allow anybody else working in their organization to indulge in fraudulent activities during execution of the contract. The contractor shall immediately apprise the Employer about any fraud or suspected fraud as soon as it comes to their notice. |

----- End of Section- SCC ----