| S. No. | CLAUSE | EXISTING PROVISION | Amended provision |
| --- | --- | --- | --- |
| 1.0 | IFB Clause 2.0, Section-I, Vol-I of the Bidding Documents | Power Grid Corporation of India Ltd. (A Government of India Enterprise) incorporated under the Companies Act, 1956, having its Registered Office at B-9, Qutab Institutional Area, Katwaria Sarai, New Delhi – 110 016 (hereinafter referred to as ‘POWERGRID’/’Owner’) has decided to set up, as an Owner, the following transmission scheme: Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities. | Power Grid Corporation of India Ltd. (A Government of India Enterprise) incorporated under the Companies Act, 1956, having its Registered Office at B-9, Qutab Institutional Area, Katwaria Sarai, New Delhi – 110 016 (hereinafter referred to as ‘POWERGRID’) has decided to procure 7x500MVA 765/400/33 KV Transformers under ‘Bulk Procurement of 765kV & 400kV class Transformers & Reactors of various Capacities’ to be utilized for RTM/ TBCB /Other Project(s) Requirements. |
| 2.0 | IFB Clause 2.1, Section-I, Vol-I of the Bidding Documents | The procurement activities in respect of the aforesaid Bulk Procurement shall be carried out by the Owner itself and it intends to use domestic funding for eligible payments under the contract for the package as mentioned above. For the purpose of all procurement activities, the Owner shall also be referred to as ‘Employer’. | The procurement activities in respect of the aforesaid Bulk Procurement shall be carried out by POWERGRID itself and it intends to use domestic funding for eligible payments under the contract for the package as mentioned above. For the purpose of all procurement activities, POWERGRID or its nominee is both the Owner and the Employer for whole of the facilities (or a part for which a separate time for Completion is specified) under the subject package. In cases wherein the nominee of POWERGRID is the Owner, during execution of the Contract(s) for the package, certain post award activities such as engineering, quality assurance & inspection, project monitoring, payment processing etc. may be carried out by POWERGRID on behalf of the Owner/Employer. In such cases, POWERGRID will also be referred to as the “Employer” wherever context requires so. The details of such nominee(s) shall be shared prior to the scheduled dispatch of the Equipment. |
| 3.0 | ITB/ BDS Clause 1.1, Section-III, Vol-I of the Bidding Documents GCC/ SCC 1.1(o) & 1.1(w), Section-V, Vol-I of the Bidding Documents | The Owner is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. The Employer is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. …………. | POWERGRID or its nominee is both the Owner and the Employer for whole of the facilities (or a part for which a separate time for Completion is specified) under the subject package. In cases wherein the nominee of POWERGRID is the Owner, during execution of the Contract(s) for the package, certain post award activities such as engineering, quality assurance & inspection, project monitoring, payment processing etc. may be carried out by POWERGRID on behalf of the Owner/Employer. In such cases, POWERGRID will also be referred to as the “Employer” wherever context requires so. The details of such nominee(s) shall be shared prior to the scheduled dispatch of the Equipment. |
| 4.0 | ITB/ BDS Clause 24.1(c), Section-III, Vol-I of the Bidding Documents GCC/ SCC 1.1(e) & 1.1(ee), Section-V, Vol-I of the Bidding Documents GCC/ SCC 21.1, Section-V, Vol-I of the Bidding Documents Appendix-4 (Time Schedule), Section-VI. Vol-I of the Bidding Documents | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Transformer Package- ….; Remark (Indicative Period in Months from Award). (i); Unit-1; 21 (Twenty-One) Months; 21 (Twenty-One) Months [Engineering: 0-8 months. Transformer Supply: Unit 1, 2 & 3: 15 to 17 months Unit 4 to 7: 18 to 20 months Erection, Testing & Commissioning: 16-21 months]. (ii); Unit-2; 21 (Twenty-One) Months. (iii); Unit-3; 21 (Twenty-One) Months. (iv); Unit-4; 21 (Twenty-One) Months. (v); Unit-5; 21 (Twenty-One) Months. (vi); Unit-6; 21 (Twenty-One) Months. (vii); Unit-7; 21 (Twenty-One) Months. | The Time for Completion shall be as under: Sl. No.; Description; Duration in months from the effective date of Contract. (I); Transformer Package- ….; Remark (Indicative Period in Months from Award). (i); Unit-1; 21 (Twenty-One) Months; 21 (Twenty-One) Months [Engineering: 0-8 months. Transformer Supply: Unit 1, 2 & 3: 15 to 17 months Unit 4 to 7: 18 to 20 months Erection, Testing & Commissioning: 16-21 months]. (ii); Unit-2; 21 (Twenty-One) Months. (iii); Unit-3; 21 (Twenty-One) Months. (iv); Unit-4; 21 (Twenty-One) Months. (v); Unit-5; 21 (Twenty-One) Months. (vi); Unit-6; 21 (Twenty-One) Months. (vii); Unit-7; 21 (Twenty-One) Months. Note: The Unit mentioned above includes the aforesaid Transformer ( including Insulating Oil ) and any other item/equipment/material/services ( as per BoQ/Price Schedules ) to be supplied alongwith the said Transformer. The said item/ equipment/ material/ services ( as per BoQ/Price Schedules ) to be supplied along with the aforesaid Transformer (including Insulating Oil) shall be suitably intimated by POWERGRID during execution of the Contract prior to scheduled dispatch of the Transformer. |
| 5.0 | Final Payment (Supply of Goods Portion), Appendix-1 (Terms & Procedure of Payment), Section-VI, Vol-I of the Bidding Documents | 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. 1.1 Supply of Goods Portion …………. C Final Payment Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid as per the following: a) 5% (Five percent) on Successful completion of erection, testing and commissioning of the individual Reactor. b) 5% (Five percent) on proof of submission of required number of reproducibles, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment and on successful completion of erection, testing and commissioning of all Reactors and issuance of Taking Over Certificate. …………….. | 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. 1.1 Supply of Goods Portion …………. C Final Payment Balance 10% (Ten percent) of the Ex-works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid on Successful completion of erection, testing and commissioning of the individual Transformer, proof of submission of required number of reproducibles, O&M Manuals, approved drawings, data sheets, test report, pamphlets and manuals of mandatory spares, maintenance & testing equipment and issuance of Taking Over Certificate. …………….. |
| 6.0 | Final Payment (Supply of Goods Portion), Appendix-1 (Terms & Procedure of Payment), Section-VI, Vol-I of the Bidding Documents | ……….. 1.4 Supply of Services Portion: Price Component for Installation ………. C. Final Payment Final 10% (Ten Percent) payment shall be made as follow: 5% (Five Percent) of the Installation price component shall be paid on commissioning of individual Reactor and Balance 5% (Five Percent) of the Installation price component shall be paid on commissioning of all Reactors and issuance of Taking Over Certificate. ………… | ……….. 1.4 Supply of Services Portion: Price Component for Installation ………. C. Final Payment Final 10% (Ten percent) of the Installation price component shall be paid on commissioning of the individual Transformer and issuance of Taking Over Certificate. ………….. |
| 7.0 | Performance Security Form | ……… To: [Name and address of the Employer] ……….. | ……… To: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) – 122001 …………. |
| 8.0 | Advance Payment Guarantee | ……… To: [Name and address of the Employer] ……….. | ……… To: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) – 122001 …………. |
| 9.0 | Appendix-1 (Terms and Procedures of Payment), Sample Forms and Procedures, Section-VI | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion B Progressive Payment …………………………………… B.1 Fifty Five Percent (55%)** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder:… … … … … … … … … …………………. B.2 Fifteen Percent (15%) of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) shall be paid on receipt and storage at site … … … … … … … … … … … … … … … 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. | Appendix-1 TERMS AND PROCEDURES OF PAYMENT In accordance with the provisions of GCC Clause 8 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules. Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds. 1. TERMS OF PAYMENT In addition to the Conditions stipulated under GCC Clause 8, the following terms & Conditions will apply. - Supply Portion B Progressive Payment# …………………………………… B.1 Fifty Five Percent (55%)** of the Ex-Works price component of Main Equipment/Materials (including Mandatory Spares) shall be paid progressively on submission of documents indicated hereinunder … … … … … … … … … …………………. B.2 Fifteen Percent (15%) of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) shall be paid on receipt and storage at site … … … … … … … … … … … … … … … # Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below. … …. …. ….. … …. …. …. 2. PAYMENT PROCEDURES 2.1 Method of Payment … …. …. ….. … …. …. …. 2.2 Bill Tracking System … …. …. ….. … …. …. …. 2.3 PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID - A bid shall be considered front loaded or unbalanced, if the percentage of Services component (Installation, civil works, F&I and Training/AMC, if any) to Total Contract Price (Supply component including Offshore + Services component including AMC Contracts) quoted by the bidder is less than 1%. - In the event of award on the bidder who have submitted unbalanced/front loaded bid, the percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the percentage by which the percentage of the Services price components in the bid less than the percentage specified at 2.3 a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. No interest shall be payable on the deferred amount. Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. |