| Sl. No. | Clause No./sections | Existing Clause/item | Amendment |
| --- | --- | --- | --- |
|  | Vol-I |  |  |
| 1 | Appendix-1, TERMS AND PROCEDURES OF PAYMENT, Sample Forms & Procedures. Vol-I | 1. TERMS OF PAYMENT ………… …….. B. Progressive Payment ………….. ………….. ………….. ………….. | 1. TERMS OF PAYMENT ………… …….. B. Progressive Payment # ………….. ………….. # Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below. ………….. ………….. |
| 2 | Appendix-1, TERMS AND PROCEDURES OF PAYMENT, Sample Forms & Procedures. Vol-I |  | 2.3 PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID a. A bid shall be considered front loaded or unbalanced, if the percentage of Services component (Installation, civil work, F&I) to Total Contract Price (Supply component + Services component) quoted by the bidder is less than 34 %. b. In the event of award on the bidder who have submitted unbalanced/front loaded bid, the percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the percentage by which the percentage of the Services price components in the bid less than the percentage specified at 2.3 a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. No interest shall be payable on the deferred amount. Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. |
|  | Vol-II |  |  |
| 4 | Clause 2.29, Section 1B of Technical Specification | ---------- ------------------- An undertaking by the proposed supplier of core of HTLS conductor shall be submitted along with the bid (Performa enclosed as Annexure–D to this section). | ---------- ------------------- An undertaking by the proposed supplier of core of HTLS conductor shall be submitted during execution of the Contract (Performa enclosed as Annexure–D to this section). |
| 5 | Clause 2.42, Section 1B of Technical Specification | ---------- ------------------- In case the Contractor is proposing supply of pole structures from his sub- vendors(s), the Contractor will be required to furnish a performance guarantee of 2% of the cost of such transmission line pole structures from the manufacturer(s) at the time of finalizing the manufacturer(s), during execution of the (Format enclosed at Annexure-E) | ---------- ------------------- In case the Contractor is proposing supply of pole structures from his sub- vendors(s), the Contractor will be required to furnish a performance guarantee of 2% of the cost of such transmission line pole structures from the manufacturer(s) at the time of finalizing the manufacturer(s), during execution of the Contract (Format enclosed at Annexure-E) |
|  | Vol-III |  |  |
| 6 | Price Schedule, Schedule-3 | I; 400kV Jhatikara-Dwaraka D/c (HTLS). Item; Item Description; Unit; Qty. 43; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PDC etc.for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+0 for all kind of soil types as mentioned in technical specification.; EA; 10. 44; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PDC etc.for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 with Auxillary cross arm (Vertical configuration) -Tension pole type PDD+6 for all kind of soil types as mentioned in technical specification.; EA; 3. 45; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PDC etc.for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+9 for all kind of soil types as mentioned in technical specification.; EA; 3. 46; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PDC etc.for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+18 for all kind of soil types as mentioned in technical specification.; EA; 7. | I; 400kV Jhatikara-Dwaraka D/c (HTLS). Item; Item Description; Unit; Qty. 43; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PCC etc. for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+0 for all kind of soil types as mentioned in technical specification.; EA; 10. 44; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PCC etc. for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 with Auxillary cross arm (Vertical configuration) -Tension pole type PDD+6 for all kind of soil types as mentioned in technical specification.; EA; 3. 45; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PCC etc. for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+9 for all kind of soil types as mentioned in technical specification.; EA; 3. 46; Design & construction of foundations including necessary excavation, RCC ,placement of reinforcement, PCC etc. for 400 kV DOUBLECIRCUIT (Twin Moose) WZ-5 (Vertical configuration) -Tension pole type PDD+18 for all kind of soil types as mentioned in technical specification.; EA; 7. |
| 4 | Price Schedule, | In view of the above, the existing MS excel file containing Price Schedule namely ‘Price_Schedule’ enclosed in the Bidding Documents, stands replaced by new file namely this ‘Price_Schedule_Rev01’ attached herewith. |  |