| S.N. | Ref Clause No. | Existing Provision in Bidding documents | Bidder’s Queries | POWERGRID’s reply/Clarifications |
| --- | --- | --- | --- | --- |
| VOLUME-I: CONDITIONS OF CONTRACT |  |  |  |  |
|  | ITB 24.1 (c) (BDS), Section-III | The Time for Completion shall be as under: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. 400kV GIS Substation Package SS-123 for:. Extn. of 400/220kV Rajarhat GIS S/S under ‘Eastern Region Expansion Scheme-XXXXI (ERES-XXXXI)’; 16 (Sixteen) months. Extn. of 400/220kV Magarwada GIS S/S under ‘Augmentation of Transformation Capacity at 400/220 kV Magarwada GIS substation in DD & DNH by 400/220 kV, 1x500 MVA ICT (3rd)’; 16 (Sixteen) months. | For both Rajarhat & Magarwada, completion period is 16 Month. We request PGCIL to increase the completion period of Magarwada by atleast 5 Month i.e. 21 Months from the date of Notification of Award as it includes both 400kV & 220kV GIS adapter development at Magarwada. Kindly confirm. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC 1.1 (e) [Definitions], Section IV | “Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the SCC) have been completed operationally and structurally and put in a tight and clean condition and that all works in respect of pre-commissioning of the Facilities (or a specific part thereof where specific parts are specified in the SCC) has been completed (wherever required, as per Technical Specifications) and Commissioning followed by Trail – Operation has been completed, as provided in GCC Sub-Clause 20.1 (Completion of Facilities) hereof. | Bidder requests for the modification of said clause as suggested below: “Completion” means that the Facilities (or a specific part thereof where specific parts are specified in the SCC) have been completed operationally and structurally and put in a tight and clean condition and that all works in respect of pre-commissioning of the Facilities (or a specific part thereof where specific parts are specified in the SCC) has been completed (wherever required, as per Technical Specifications) and Commissioning followed by Trial – Operation has been completed, as provided in GCC Sub-Clause 20.1 (Completion of Facilities) hereof. Furthermore, the facility shall be deemed to have been takeover and the Employer shall issue a TOC if the Facilities is put to use by the Employer. The Employer is also bound to accept commencement of defect liability period from the said deemed date. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 3.3. [Scope of the Facilities] Page 9, Section-IV | The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 years from Completion of the Facilities. The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | The Bidder requests to modify the clause as: The supply of Mandatory Spare Parts, if any, shall be included in the Contract. Beside the aforesaid Mandatory Spares parts, the Contractor shall ensure the availability of functionally equivalent spare parts required for the operation and maintenance of the Facilities to the Employer for a minimum period of 15 10 years from Completion of the Facilities. The Contractor shall carry sufficient inventories to ensure an ex-stock supply of consumable spares for the plant and equipment. If so desired by the Employer, the Contractor shall submit the specifications, price and the terms and conditions relating to the supply thereof for such spares identified by the Employer with validity period of 6 months within 30 days of receipt of request from Employer for its consideration and placement of order. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 3.4 (ii) [Scope of the Facilities] Page 10, Section IV | The Contractor shall guarantee that in the event of termination of production of spare parts by the Contractor or his Sub-Contractor: …………………… (ii) Following such termination, the Contractor shall furnish at no cost to the Employer the blueprints, drawings and specification of the spare parts, if requested. | The Bidder requests for the deletion of the clause, as Bidder requests PGCIL to allow acceptance of Functional equivalents. The Bidder foresees no requirement for the submission of Drawings with PGCIL. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 5 [Scope of the Facilities] Page 10, Section IV | Contractor’s Responsibilities …………………………….. 5.2 The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Facilities (including any data as to boring tests) provided by the Employer, and on the basis of information that the Contractor could have obtained from a visual inspection of the Site (if access thereto was available) and of other data readily available to it relating to the Facilities as of the date twenty-eight (28) days prior to bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities. | The Bidder requests to modify the clause as The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Facilities (including any data as to boring tests) provided by the Employer, and on the basis of information that the Contractor could have obtained from a visual inspection of the Site (if access thereto was available) and of other data readily available to it relating to the Facilities as of the date twenty-eight (28) days prior to bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities. During the course of execution of the project, any changes in the site conditions as a result of work carried out by the Contractor and their sub-contractors shall be considered as a change in the scope. Any resulting changes in the scope resulting in additional reasonable cost shall be reimbursed by the Employer against submission of documentary evidence. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 6.0 [Employer's Responsibilities] Page 13, Section IV | 6.7 All costs and expenses involved in the performance of the obligations under this GCC Clause 6 shall be the responsibility of the Employer. | The Bidder requests to add the following clauses 6.8 All invoices raised by the Contractor in accordance with the provisions of this Contract shall be paid within 30 days by the Employer. In case any invoice remains unpaid beyond such period, Contractor shall be entitled to suspend performance of the Contract until such payment is made at the time and cost of the Employer. 6.9 The Contractor will be entitled to suitable time schedule adjustments and increases in the Price as necessitated by the default or delay of the Employer in performing its obligations under the Contractor. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause No. 6.2 [Employer's responsibilities], Section – IV | The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the corresponding Appendix – 6 (Scope of Works and Supply by the Employer) to the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix. | Please confirm that the site will be available, duly secured with permanent boundary wall and security gate. Please further confirm that in case of any delay in acquiring and providing legal and physical possession of the site and its access, and for providing possession of and access to all other areas reasonably required for the proper execution of the contract, including all requisite rights of way, as applicable, the employer shall pay reasonable cost incurred by the contractor along with suitable time extension. | The provisions of Bidding Documents are amply clear. |
|  | GCC Clause No. 6.3 [Employer's responsibilities], Section – IV | The Employer shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located which such authorities or undertakings require the Employer to obtain them in the Employer's name, are necessary for the execution of the Contract (they include those required for the performance by both the Contractor and the Employer of their respective obligations under the Contract), including those specified in Appendix 6 (Scope of Works and Supply by the Employer) to the Contract Agreement. | Please confirm that in case of delay by Employer in acquiring and providing permits, approvals and/or licenses required for the proper execution of the contract, including all requisite rights of way, as applicable, the Employer shall pay reasonable cost incurred by the contractor along with suitable time extension. | The provisions of Bidding Documents are amply clear. |
|  | GCC Clause 16.1.1 [Design and Engineering] Page 27, Section IV | The Contractor shall execute the basic and detailed design and the engineering work in compliance with the provisions of the Contract, or where not so specified, in accordance with good engineering practice. The Contractor shall be responsible for any discrepancies, errors or omissions in the specifications, drawings and other technical documents that it has prepared, whether such specifications, drawings and other documents have been approved by the Project Manager or not, provided that such discrepancies, errors or omissions are not because of inaccurate information furnished in writing to the Contractor by or on behalf of the Employer. | The Bidder requests for the modification of the clause as: The Contractor shall execute the basic and detailed design and the engineering work in compliance with the provisions of the Contract or as laid down by the established Industry Engineering Standards, or where not so specified, in accordance with good engineering practice. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause No. 20.1.2.7 [Pre-Commissioning], Section V | As soon as possible after Pre-commissioning, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract, failing which the Employer will undertake such completion and deduct the costs thereof from any monies owing to the Contractor | Please modify the paragraph as below: As soon as possible after Pre-commissioning, the Contractor shall complete all outstanding minor items so that the Facilities are fully in accordance with the requirements of the Contract for Commissioning. In case the contractor fails to complete the outstanding minor items within reasonable time, failing which the Employer, upon notification to the Contractor, will undertake such completion of outstanding minor items and deduct the costs thereof from any monies owing to the Contractor under this contract. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 20.2.2.2 [Operational Acceptance] Page 57, Section IV | At any time after any of the events set out in GCC Sub-Clause 20.2.2.1 have occurred, the Contractor may give a notice to the Project Manager requesting the issue of an Operational Acceptance Certificate in the form provided in the Bidding Documents or in another form acceptable to the Employer in respect of the Facilities or the part thereof specified in such notice as of the date of such notice. | The Bidder requests to add the following to the clause as: The Facilities shall also be deemed to have been Accepted in case the Employer puts it into commercial operation at any time prior to such Operational Acceptance. In case Commissioning/Operational Acceptance is delayed by more than 60 days from the scheduled date as notified by the Contractor to the Employer, or the switchyard is put to commercial operations, due to reasons not attributable to contractor, then the switchyard will be considered as deemed commissioned. Consequently, the defect liability period shall start and the final payment due to Contractor (if any) shall become due to the Contractor. Any additional charges on account of delay in commissioning shall be reimbursed by the Employer. The Retention Payments will be released against submission of 10% Retention Bank Guarantee valid till end of the 12 months. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 26.1, [a. Limitation of Liability] Page 64, Section IV | Limitation of Liability – Except in cases of gross negligence or willful misconduct, (a) the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use , loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and | The Bidder requests to modify the clause as Limitation of Liability - Except in cases of gross negligence or willful misconduct, (a) the Contractor and the Employer shall not be liable to the other party for any indirect or consequential loss or damage, loss of use or interruption of operations, loss of production, or loss of profits or interest costs, cost of capital, loss of information and/or data, for claims arising from Customer’s contracts with third parties, loss of power, cost of purchased or replacement power provided that this exclusion shall not apply to any obligation of the Contractor to pay liquidated damages to the Employer and | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 26.1 [(b) Limitation of Liability] Page 64, Section IV | (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | The Bidder requests to modify the clause as: (b) the aggregate liability of the Contractor to the Employer, whether under the Contract, in tort or otherwise, shall not exceed the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment by the Contractor, or to any obligation of the Contractor to indemnify the Employer with respect to patent infringement. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 31.1 [Changes in Laws and regulations] Page 73, Section IV | If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in India (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor for which the Employer shall be the sole judge. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement. | The Bidder requests for modification of the clause as: If, after the date seven (07) days prior to the date of Bid Opening, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed in India (which shall be deemed to include any change in interpretation or application by the competent authorities) that subsequently affects the costs and expenses of the Contractor and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Contractor has thereby been affected in the performance of any of its obligations under the Contract. These adjustments shall be applicable for all transactions between the Employer and the Contractor for supply of goods and services under the Contract but shall not be applicable on procurement of raw materials, intermediary components etc. by the Contractor for which the Employer shall be the sole judge. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the Appendix-2 to the Contract Agreement. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 32, [Force Majeure] Page 73, Section IV | 32. Force Majeure 32.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Contractor, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following (a) war, hostilities or warlike operations (whether war be declared or not), invasion, act of foreign enemy and civil war, (b) rebellion, revolution, insurrection, mutiny, usurpation of government, conspiracy, riot and civil commotion, (c) earthquake, landslide, volcanic activity, flood or cyclone, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster, | The Bidder requests to add the following clause: d) Epidemic's, Covid, Quarantine as covered/mentioned under "any further government notifications related to Covid as released from time to time are to be adhered to." | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 33.2.5 [Changes Originating from Employer] Page 77, Section IV | The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”). Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the Arbitrator in accordance with the provisions of GCC Clause 38 & 39. | The Bidder requests to modify the clause as: The Employer shall issue the Contractor with a Change Order pursuant to GCC Sub-Clause 33.2 by way of amendment to the Contract or in any other manner deemed appropriate. Even if the Employer and the Contractor cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters related to the Change Proposal, the Employer may nevertheless instruct the Contractor to proceed with the Change by issue of a “Pending Agreement Change Order” (“Pending Agreement Amendment”). Upon receipt of a Pending Agreement Change Order, the Contractor shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. If the parties cannot reach agreement within sixty (60) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred to the Arbitrator in accordance with the provisions of GCC Clause 38 & 39. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 34 [Extension of Time for Completion] Page 77, Section IV | (d) any changes in laws and regulations as provided in GCC Clause 31 or (e) any other matter specifically mentioned in the Contract | The Bidder requests to add the clause as (f) any delay or default of the Owner impacting the performance of the Contractor | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC 35 Add new clause (GCC 35.4) Suspension, Section IV | 35. Suspension 35.1 The Employer may request the Project Manager, by notice to the Contractor, to order the Contractor to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons therefor. The Contractor shall thereupon suspend performance of such obligation (except those obligations necessary for the care or preservation of the Facilities) until ordered in writing to resume such performance by the Project Manager. If, by virtue of a suspension order given by the Project Manager, other than by reason of the Contractor‟s default or breach of the Contract, the Contractor‟s performance of any of its obligations is suspended for an aggregate period of more than ninety (90) days, then at any time thereafter and provided that at that time such performance is still suspended, the Contractor may give a notice to the Project Manager requiring that the Employer shall, within twenty-eight (28) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in…………….. 35.1………. 35.2………… 35.3………….. | Please add a new sub clause as below: 35.4 In the event any of the following occurs Contractor may at its option suspend the provision of its obligations under this Contract: a) Customer fails to make payment of any amount within 30 days after it has become due and payable, or b) Customer fails to perform its obligations necessary for the Contractor to deliver or complete the Work, or c) Delivery and/or completion of the Work is prevented by export or other legally mandated restrictions for more than 6 months; or d) Customer is insolvent. In the event Contractor suspends the provision of its obligations, Customer shall pay the Contractor all additional cost incurred due to such suspension. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 36.1.2 (d) (ii) [Termination - Termination for Employer Convenience] Page 80, Section IV | to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors. | The Bidder requests to modify the clause as (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer and to the extent possible by the Contractor, in any subcontracts concluded between the Contractor and its Subcontractors | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 36.1.3 [Termination - Termination for Employer Convenience] Page 80, Section IV | In the event of termination of the Contract under GCC Sub-Clause 36.1.1, the Employer shall pay to the Contractor the following amounts: a) the contract price, properly attributable….................. b) the costs reasonably incurred by the Contractor .................. c) any amounts to be paid by the Contractor to its Subcontractors....... d) costs incurred by the Contractor in protecting the Facilities............ e) the cost of satisfying all other obligations, commitments | The requests for addition of the following: f) reasonable overheads / costs incurred by the Contractor with submission of documentary evidence. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 36.2.2. [Termination for Contractors Default] Page 83, Section IV | If the Contractor a) has abandoned or repudiated the Contract….... b) has without valid reason failed to commence….. c) persistently fails to execute the Contract…...... d) refuses or is unable to provide sufficient materials….... then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GCC Sub-Clause 36.2. | The Bidder requests to modify the clause as If the Contractor a) has abandoned or repudiated the Contract….... b) has without valid reason failed to commence….. c) persistently fails to execute the Contract…...... d) refuses or is unable to provide sufficient materials….... then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Contractor stating the nature of the default and requiring the Contractor to remedy the same. If the Contractor fails to remedy or to take steps to remedy the same within fourteen (14) days thirty (30) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Contractor that refers to this GCC Sub-Clause 36.2. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 36.2.3 [Termination for Contractors Default] Page 83, Section IV | Upon receipt of the notice of termination under GCC Sub-Clauses 36.2.1 or 36.2.2, the Contractor shall, either immediately or upon such date as is specified in the notice of termination, a) cease all further work, except for such work..... b) terminate all subcontracts........ c) deliver to the Employer the parts of the Facilities ..... (d) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Contractor and its Subcontractors | The Bidder requests to modify the clause as Upon receipt of the notice of termination under GCC Sub-Clauses 36.2.1 or 36.2.2, the Contractor shall, either immediately or upon such date as is specified in the notice of termination, a) cease all further work, except for such work..... b) terminate all subcontracts........ c) deliver to the Employer the parts of the Facilities ..... (d) to the extent legally possible, assign to the Employer all right, title and benefit of the Contractor to the Facilities and to the Plant and Equipment as of the date of termination, and, as may be required by the Employer and to the extent possible, in any subcontracts concluded between the Contractor and its Subcontractors | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC Clause 36.4, [Termination for Contractors Default] Page 85, Section IV, | 36.4 In this GCC Clause 36, in calculating any monies due from the Employer to the Contractor, account shall be taken of any sum previously paid by the Employer to the Contractor under the Contract, including any advance payment paid pursuant to the corresponding Appendix (Terms and Procedures of Payment) to the Contract Agreement. | The Bidder requests to add the following clause : 36.5 The Contractor shall be entitled to terminate the Contract under the following circumstances by giving a 30 days’ written notice to the Employer: a. Works have been suspended for more than 180 calendar days due to Employer’s delay or breach of contract; or b. Employer has otherwise materially breached the contract; or c. Employer’s suspension for convenience lasts more than 12 months per event. d. Delayed payment by the Employer beyond 60 days. In each case the Contractor shall be entitled to be paid as per Clause 36.1.3 of the Contract. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC 40 [Unforeseen Conditions / Subsurface Risks], Section IV | not existing | Bidder requests the addition of the following clause: If during the execution of the works on Site the Contractor encounters physical obstructions or conditions which could not reasonably have been foreseen by the Contractor at the latest date for bid submission, the Contractor shall be entitled to recover the additional Time for Completion and cost incurred in consequence. “Physical obstructions and conditions” means natural physical conditions and manmade and other physical constructions and pollutants, which the Contractor encounters at the Site, including subsurface and hydrological conditions. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC 11 (SCC) - Intellectual Property - Copyright. Page 9, Section V, | Supplementing the GCC Clause 11 Notwithstanding the provisions of Clause GCC 11.1 above, the copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer for the material and in the manner as detailed in the Technical Specification, Vol-II of the Bidding Documents. | The Bidder requests to modify the clause as Notwithstanding the provisions of Clause GCC 11.1 above, the copyright in all the drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party exclusively for the Employer under the Contract shall remain vested in the Employer for the material and in the manner as detailed in the Technical Specification, Vol-II of the Bidding Documents. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |
|  | GCC 21.2 (SCC)– [Completion Time Guarantee] Page 18, Section V | If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). | The Bidder requests to modify the clause as: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). The payment of liquidated damages shall be the sole and exclusive remedy to the owner for delay. The Contractor shall not be liable for delays that are not caused by fault (negligence/intentional act) of the Contractor. | The existing provisions of Bidding Documents shall prevail and remain unaltered. |