APPENDIX 1

# TERMS AND PROCEDURES OF PAYMENT

In accordance with the provisions of GCC Clause 12 (Terms of Payment), the Employer shall pay the Contractor in the following manner and at the following times, on the basis of the Price Breakdown given in the section on price schedules.  Payments will be made in the currencies quoted by the Bidder unless otherwise agreed between the parties. The Contractor may make applications for payment in respect of part deliveries as work proceeds.

1.	TERMS OF PAYMENT

1.1	In addition to the Conditions stipulated under GCC Clause 12, the following terms & Conditions will apply.

1.1	Supply portion (Fabricated & Galvanized towers & Line materials)

- Advance Payment

10% (Ten percent) of the CIP price component of the Contract price shall be paid after signing the Contract Agreement and on submission of i) invoice ii) Advance Bank Guarantee* for 110% (one hundred ten percent) of the amount of Advance, iii) Performance Security and (iv) income Tax Order in case of CIP Entry Border Point supplies.

*In case the Contract is awarded to a Joint Venture, the Advance Bank Guarantee shall be in the name of all partners of the Joint Venture.

The Bank Guarantee(s) for advance shall be initially valid upto the end of ninety (90) days after the scheduled date for Completion of the Facilities and shall be extended from time to time till ninety (90) days beyond the actual date of Completion of the Facilities, as may be required under the Contract.

Interest rate applicable on advance payment to the Contractor shall be at the rate equal to 7% per annum considering proportionate adjustment of advance against progressive payments as per below. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment.

The value of bank guarantee towards advance shall be proportionately reduced every three (3) months after First Running Account Bill/Stage payment under the Contract. The cumulative amount of reduction shall be allowed upto full value of the Bank Guarantee upon adjustment of the corresponding advance and certification to this effect by the Employer’s representative. It should be clearly understood that reduction in the value of advance Bank Guarantee shall not in any way dilute the Contractor's responsibility and liabilities under the Contract including in respect of the Facilities for which reduction in the value of security is allowed.

(The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form).

- Progressive Payment

On Shipment: 80% (Eighty percent) of the CIP price of each item excluding that of fabricated tower parts/tower (as identified in the price schedule) shipped shall be paid through irrevocable Letter of Credit (L/C) established in favour of the Contractor and on submission of documents specified in Annexure-I to Appendix-I (Shipping documents). Payment of fabricated tower parts/tower shall, however, be made in the following manner:

- 60% (Sixty percent) of the CIP price of fabricated tower parts/tower shipped shall be paid through irrevocable Letter of Credit (L/C) established in favour of the Contractor and on successful completion of inspection and testing and on the submission of documents specified in Annexure-I to Appendix-I (Shipping documents). The payment of fabricated tower parts/tower shall, however, be made on completed tower basis, as certified by the Employer’ representative.

- Twenty percent (20%) of the CIP price of fabricated tower parts, shall be paid on completion of erection of complete tower and furnishing of necessary certificate by Employer’s representative.

- Final Payment:

The final 10% (Ten percent) of the CIP price of each item as identified in the price schedule enclosed with the Notification of Award/ Contract Agreement shall be paid within 30 days of the certificate by the Employer that the erection of all the towers of the transmission line have been completed and on submission of a Bank Guarantee for full ten percent (10%) amount valid till completion of testing and issuance of Completion (Taking Over) Certificate.

1.2	Price Component for Installation (including Civil Works) and Services

(a)	Advance

Five percent (5%) of the total Contract Price for services viz., survey, installation (including civil works) component shall be paid as initial advance on establishment of Contractor’s Site offices at the respective site(s) and submission of a bank guarantee* of 110% (one hundred ten percent) of the amount of Advance valid till 90 days after Completion of the Facilities and shall be extended from time to time till ninety (90) days beyond the actual date of Completion of the Facilities, as may be required under the Contract.

*In case the Contract is awarded to a Joint Venture, the Advance Bank Guarantee shall be in the name of the Joint Venture covering all partners of the Joint Venture and not in the name of the lead partner or any partner(s) of the Joint Venture alone.

Interest rate applicable on advance payment to the Contractor shall be at the rate equal to 7% per annum considering proportionate adjustment of advance against progressive payments as per below. The said interest rate shall remain fixed and shall be applicable till the advance amount is fully repaid. The interest shall be calculated on the daily progressive balances outstanding as on the date of recovery/adjustment.

(The above is to be incorporated in case the Contractor has opted for the interest bearing initial advance, as declared by it in its bid in the relevant Attachment to Bid Form).

(b)	Progressive Payment

(i)	Further Five percent (5%) of the total installation component (i.e. including civil works but excluding survey) of the Contract price shall be paid after the Contractor brings to site major tools & Plants including tension stringing equipment etc. and on submission of Bank Guarantee for 110% (one hundred ten percent) of the amount. The above Bank Guarantee shall be kept valid till 90 days after Completion of the Facilities

Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section X: Contract Forms and approval of the same by the Engineer In-Charge.

(ii)	Eighty percent (80%) of the total installation (i.e. including civil works but excluding survey) component of the Contract Price shall be paid progressively monthly on pro-rata basis on certification by Employer’s representative, on certification for the quantum of work done and other for the successful completion of quality check point involved in erection by Employer.

(iii)	The balance ten percent (10%) of the total installation (i.e. including civil works but excluding survey) price components of contract price shall be paid on commissioning and issuance of Completion (Taking Over) Certificate by Employer.

- Ninety Five percent (95%) payment for survey will be made on completion of every 25 kms of survey work and on approval by the Employer within 30 days of approval thereof.

- 100% Training Charges shall be paid on successful completion of training and on approval of the same by the Employer.

1.3       Payment of Price Adjustment

Any variation in Contract price due to price adjustment provision of Appendix-2 shall be effected on presentation of invoice supported by calculations as per formulae specified therein.

1.3.1	Any increase in Contract price due to price adjustment provision shall be payable as follows:

Supply Portion:

90% (ninety percent) of the price adjustment amount for the respective shipment shall be paid on receipt of said shipment at site. Balance 10% (ten percent) of the price adjustment amount shall be paid along with the final payment.

Erection Portion:

90% (ninety percent) of the price adjustment amount for the respective billing period shall be paid after certification by Employer’s representative for quantum of work done in the said billing period. Balance 10% (ten percent) of the price adjustment amount shall be paid along with the final payment.

1.3.2	Any reduction in Contract Price due to price adjustment provisions shall be effected by recovering 100% of the reduction amount from Contractor’s invoices falling immediately due for payment or any other payments.

2.	PAYMENT PROCEDURES

2.1	Method of Payment

2.1.1	The Employer shall make payments promptly within thirty (30) days of submission of an invoice/claim by the Contractor, complete in all respects and supported by the requisite documents and fulfillment of stipulated conditions, if any. All the payment shall be released to the Contractor directly except the payment due on shipment, which shall be paid through irrevocable confirmed Letter of Credit. The Letter of Credit shall be established by the Employer in time for shipments to be made as scheduled.

All payments to be made directly to the Contractor shall be made by the Employer though electronic payment mechanism (e-payment) for which necessary details shall be tied up during execution of the Contract. However, a request for payment to be released through cheque shall be considered on case to case basis and merit of the same.

    - In case of Contractor being a Joint Venture of two or more firms, the payment under the Contract shall be received by the Lead Partner on behalf of the Joint Venture, as per power conferred to it in the Power of Attorney. The payment under the Contract, however, can also be received by other Partner (s) based on authorisation of the Lead Partner.

Note:	Pro-rata shall refer to functionally complete part(s) of the facilities, for which unit rates are identified in the contract.

Annexure-I to Appendix 1

Shipping Documents

1.0	For Plant and Equipment including mandatory Spares to be supplied from abroad

Upon shipment, the Contractor shall notify the Employer and the Insurance Company by cable or telex of the full details of the shipment including Contract number, description of goods, quantity, the vessel, the bill of lading/Airway Bill number and date, port of loading, date of shipment, port of discharge, etc.  The Contractor shall mail the following documents to the Employer, with a copy to the Insurance Company.

- Copies of the Contractor’s invoice showing Contract Agreement reference, goods description, quantity, unit price, total amount;

- Original (3/3) and six copies of the negotiable, clean on-board bill of lading/Air way Bill marked freight prepaid and six copies of non-negotiable bill of lading/ Air way Bill;

- Copies of packing list identifying contents of each package; (6 copies)

- Insurance policy / Certificate; (3 copies)

- Manufacturer’s / Contractor’s guarantee certificate of Quality;

- Material Inspection & Clearance Certificate (MICC) for dispatch, issued by the Employer’s representative and the Contractor’s factory inspection report, test certificates; (3 copies) and

- Certificate of origin.

The above documents shall be air mailed/faxed by the Contractor to reach the Employer within one week from date of shipment to enable the Employer to make progressive payment to the Contractor and also make necessary arrangement for payment of custom duties etc.  The Contractor will be responsible for any consequent expenses due to delay in furnishing the above documentation.

- For Domestic Goods

Upon shipment, the Contractor shall notify the Employer and the Insurance Company by cable or telex of the full details of the dispatch including Contract number, description of goods, quantity, R/R or L/R number and date, place of loading, date of dispatch, etc.  The Contractor shall mail the following documents to the Employer, with a copy to Insurance Company.

(1)	Copies of the Contractor’s invoice showing Contract Agreement reference, goods description, quantity, unit price, total amount; (6 copies)

(2)	Copies of packing list identifying contents of each package; (6 copies)

- Railway receipt / receipted LR;

- Manufacturer’s / Contractor’s guarantee certificate of Quality;

- Material Inspection & Clearance Certificate (MICC) for dispatch, issued by the Employer’s representative and the Contractor’s factory inspection report, test certificates; (3 copies);

- Insurance policy / Certificate (3 copies); and

- Certificate of origin.

3.0	Whenever a waiver for the presence of EMPLOYER engineer to witness the testing is accorded, the Supplier, after carrying out inspection and testing as per approved Plan/ Specification should forward test results for approval of EMPLOYER.  The Material Inspection and Clearance Certificate (MICC) will be issued within fifteen (15) days from the date of receipt of test results, if test results furnished establish conformance to specified requirements.