| Sl. No | Clause No / | Description as per Bid Document | Remarks - Query / Clarification | POWERGRID’s Clarification |
| --- | --- | --- | --- | --- |
| 1. | Vol-I, Sec - VI Forms and Procedures Appendix – 2 | Price Variation (PV) | As per referred clause and Appendix, Price variation is applicable only on Tower Parts, whereas all other items are on FIRM Price Basis. Kindly Confirm the rationale for keeping other items outside the Price Variation purview. We draw your kind attention that apart from Tower, Conductor, Earthwire, hardware are directly exposed to commodity rates. As you are very well aware there is high volatility in the market for all commodities like Steel, Aluminium, copper including crude oil. This is due to various economic as well global factors. Prices of commodity is changing on daily level. Considering the project timeline of 12 months, its huge risk to EPC players. Price variation formula only helps contractor to quote very competitive which enable you to optimize your capital budget for the project as well as helps to complete the project on time without any financial crunch faced by EPC contractor. Without Price variation, projects gets unnecessary loading (both end i.e vendor as well as EPC contractor) of cost without having fair idea of future commodity trends which ultimately increases your project cost as well. And sometimes delay the project if contractor faces unviable cost increase in raw Materials Hence we request you to please accept Price variation for all the equipment like your earlier RTM projects. | Provision of the bidding document in this regard are amply clear and shall remain unchanged. |
| 2 | Vol-I, Sec - VI Forms and Procedures Appendix – 2 | Price Variation (PV) | As per referred clause and Appendix, Service Portion - FIRM Price In line with above, we request to allow PV on Installation Price Component (incl. Civil Works), Supply and placement of Reinforcement Steel and Concreting. As you know steel, cement, diesel and labour are key components of service cost and same are very volatile in current market. Kindly allow PV formula for services also like your earlier RTM tenders. | Provision of the bidding document shall remain unchanged. |
| 3 | Special Conditions of Contract (SCC) Supplementing Sub-Clause GCC 1.1(ee) | Time for Completion | As per referred clause and Appendix, Time for Completion: 12(Twelve) Months We draw your kind attention that tender is on designed basis and the project is located in Gujarat. As you are aware that in designed based project, tower and its associated foundation to be first designed and get it approved. After approval, same has to go for type testing in lab. This is minimum 3-4 months job from the date of NOA. Here Towers of wind zone (WZ) 5(with Coastal Factor) are involved. Secondly Gujarat state is not very condusive for ROW clearance. We have observed that many local hinderances comes during project execution. Even if ROW clearance is in your scope, the project gets delayed many times due to such factors. In our opinion 12 months construction period is very stringent considering above facts. Hence we request you to change it to minimum 18 months from NOA date. Incase project to be executed in 12 months timeline, we propose PGCIL to exclude design scope from Bidders scope and include the same in their scope and provide BOQ accordingly. Otherwise these timelines are not executable timeline, rather only a wish period. Hence a more practicable timeline to put considering all the factors. | Provision of the bidding document in this regard shall remain unchanged. |
| 4 | Vol I, Section – II ITB 14.1 | Bid validity period | As per referred clause, price validity is 6 months i.e half period of project execution and that also on FIRM price. We propose to reduce validity by 2 Months. We request PGCIL to please look into bid validity period and make it 60days maximum for such short duration project otherwise valuable timeline is lost in bid evaluation itself, rather same period to be extended to project execution for timely completion of project with quality. | Provision of the bidding document in this regard shall remain unchanged. |