| Sl. No. | Clause/ Drg. No. | Existing provision | Amended provision |
| --- | --- | --- | --- |
|  | ITB Clause 24.1 in BDS in Volume-1 of Bidding document | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.: 5002001872/TRANSFORMER/DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 months (Twelve Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 months (Eleven Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 10 months (Ten Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 10 months (Ten Months). Extension of 220kV Shajhanpur S/S; 8 months (Eight Months). Implementation of 1X 80 MVAR, 765kV Spare Reactor at Bhadla; 12 months (Twelve Months). | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.: 5002001872/TRANSFORMER /DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 (Twelve) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 (Eleven) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 15 (Fifteen) months. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 15 (Fifteen) months. Extension of 220kV Shajhanpur S/S; 8 (Eight) months. Implementation of 1X 80 MVAR , 765kV Spare Reactor at Bhadla; 12 (Twelve) months. |
|  | GCC 1.1(e) & 1.1(ee) in SCC in Volume-1 of Bidding document | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.: 5002001872/TRANSFORMER/DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 months (Twelve Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 months (Eleven Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 10 months (Ten Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 10 months (Ten Months). Extension of 220kV Shajhanpur S/S; 8 months (Eight Months). Implementation of 1X 80 MVAR , 765kV Spare Reactor at Bhadla; 12 months (Twelve Months). | The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.: 5002001872/TRANSFORMER/DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 (Twelve) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 (Eleven) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 15 (Fifteen) months. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 15 (Fifteen) months. Extension of 220kV Shajhanpur S/S; 8 (Eight) months. Implementation of 1X 80 MVAR , 765kV Spare Reactor at Bhadla; 12 (Twelve) months. |
|  | GCC 21.1 in SCC in Volume-1 of Bidding document | Time for Completion: Sl. No.; Activities; Duration in months from the effective date of NOA. 1.; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 months (Twelve Months). 2; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 months (Eleven Months). 3; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 10 months (Ten Months). 4; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 10 months (Ten Months). 5; Extension of 220kV Shajhanpur S/S; 8 months (Eight Months). 6; Implementation of 1X 80 MVAR , 765kV Spare Reactor at Bhadla; 12 months (Twelve Months). | Time for Completion: Sl. No.; Activities; Duration in months from the effective date of NOA. 1.; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 (Twelve) months for bay extension and 15 (Fifteen) months for Transformer. 2; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 (Eleven) months for bay extension and 15 (Fifteen) months for Transformer. 3; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 15 (Fifteen) months. 4; Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 15 (Fifteen) months. 5; Extension of 220kV Shajhanpur S/S; 8 (Eight) months. 6; Implementation of 1X 80 MVAR , 765kV Spare Reactor at Bhadla; 12 (Twelve) months. |
|  | Appendix-4 (Time Schedule) in Section-VI: Sample Forms and Procedures in Volume-1 of Bidding document | 1. The Project Completion Schedule shall be as follows: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.:5002001872/ TRANSFORMER/ DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 months (Twelve Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 months (Eleven Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 10 months (Ten Months). Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 10 months (Ten Months). Extension of 220kV Shajhanpur S/S; 8 months (Eight Months). Implementation of 1X 80 MVAR, 765kV Spare Reactor at Bhadla; 12 months (Twelve Months). 1.1 The activity(ies) under the Contractor’s programme…… | 1. The Project Completion Schedule shall be as follows: Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of Transformer Package TR-34 [Spec. No.:5002001872/ TRANSFORMER/ DOM/A03-CC CS-4]. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Bhadla pooling S/S including associated bays; 12 (Twelve) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Shujalpur S/s including associated bays; 11 (Eleven) months for bay extension and 15 (Fifteen) months for Transformer. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Kohchi; 15 (Fifteen) months. Supply of 1X 500MVA, 420/220/33kV Auto transformer at Hiriyur S/S; 15 (Fifteen) months. Extension of 220kV Shajhanpur S/S; 8 months (Eight Months). Implementation of 1X 80 MVAR, 765kV Spare Reactor at Bhadla; 12 months (Twelve Months). 1.1 The activity(ies) under the Contractor’s programme….. |