| S N | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
| 1 | Appendix-2 (Price Adjustment) in Section – VI: Samples Forms and Procedures in Vol-1 of Bidding document | …… 1.2 All Ex-Works Price Components for Spares, Maintenance & Testing Equipment, etc. and other items not specifically mentioned below shall remain firm and no price adjustment shall be applicable for the price components of these items. 1.3 Other Charges viz. inland transportation, inland insurance, type test charges, computer studies (if any) & training charges etc. shall be firm and no price variation shall be payable for these components. 2. Ex-Works Price Component The formulae for calculating the price adjustment to be applied to the Ex-works price component of the main equipment will be as follows: - Price adjustment formula for Ex-works Price component of Transformer (excluding Insulating Oil) (ratings above 10MVA or voltage above 33kV up to 400kV) …….. …….. B. For Insulating Oil for Transformer …….. | We would like to bring in your kind notice that raw material prices are drastically changing, in this regards request you to kindly consider PV clause for following items also:- AIS Equipment [CVT, Surge Arrestor, Current Transformer, Circuit Breaker] PVC/XLPE Insulated Power and Control Cables. Sub Station Structures (including Bolts & Nuts). Installation (including Civil Works) Price Component. | Existing Provision of bidding document shall prevail. |
| 2 | GCC Clause 6 (Employer’s Responsibilities) in Vol.I Bidding Document | 6. Employer’s Responsibilities …. 6.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the corresponding Appendix – 6 (Scope of Works and Supply by the Employer) to the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in that Appendix. | Internal Site Access Roads We understand that the Internal Site Access Roads Until the plinth of the transformer are made available by the Owner (or by Owner through relevant authorities) to the Contractor for the Project Works i.e. Movement of Construction Vehicles, Transportation of project Personnel, Equipment etc. Please confirm. | Provision of the bidding document is amply clear. Please refer GCC Clause 6 in this regard. |
| 3 | GCC 9.3.1 (Performance Security) in Vol.I Bidding Document | Performance Security 9.3.1 The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. Apart from the Contractor‟s performance security, the Contractor shall be required to arrange additional performance securities, as specified in SCC, within twenty-eight (28) days of the notification of award in favour of the Employer in the form acceptable to the Employer. | We would like to bring to your notice that under this package Tr-34 there are Six Sub-Stations with different completion periods, if one sub-station site under the contract is delayed beyond actual scheduled completion date, we are obligatory to extend the Performnace Bank Guarantee on entire contract price as per the clause 9.3.1. In this regard, and as per our pervious experience with PGCIL, we request you to kindly accept following for us to proceed on this opportunity: - Bidder has to establish performance security independently for each sub-station location under this contract. Performance Security for undelivered/unexecuted portion site/sub-station shall be extended by the contractor time to time till ninety (90) days beyond the actual Defect Liability Period. | Existing Provision of bidding document shall prevail. |