## Sheet1
Clarification No-IV to the Bidding Documents of Package ARP-DMS-05A, ARP-DMS-05B and ARP-DMS-05C for distribution works in Arunachal Pradesh under Comprehensive Scheme for Strengthening of Transmission & Distribution system in NER & Sikkim: Intra State - Arunachal Pradesh; Spec. no.: CC-CS/1073-NER/REW-4244/3/G2 (ARP-DMS-05A); CC-CS/1073-NER/REW-4245/3/G2 (ARP-DMS-05B); CC-CS/1073-NER/REW-4246/3/G2 (ARP-DMS-05C)
Sl.No | Pkg. No | S/s Name | Work Description | Clarification Points | Remarks | Reply by POWERGRID
Status of Proposed 132/33 KV Substations
1 | 5A | Proposed 132/33 KV Koloriang S/s | 25 KM 33KV SC line to Kush HEP | Kindly inform current status of proposed 132/33KV Koloriang S/s. Please inform the estimated time for charging and handover of this S/s . Also please inform 33KV spare bay will be available at Koloriang and Kush HEP. | If after completion of our job source substation is still not available than within how many days handover will be taken form us and what will be the procedure. | The construction of various elements will be alligned as per overall construction schedule. At source, the bay will be made available as per construction schedule.
2 | 5A | Proposed 132/33 KV Palin S/S | 33KV SC incomer line for new 33/11KV Sippi S/s | Kindly inform current status of proposed 132/33KV Palin S/s. Please inform the estimated time for charging and handover of this S/s. Also please inform 33KV spare bay will be available for new S/s | Same as above | The 33KV line is from 132/33KV Palin SS to Tali. At source, the bay will be made available as per construction schedule.
3 | 5B | Proposed 132/33 KV YingKyong S/s | 33KV SC incomer line for new 33/11KV Jengging S/s | Kindly inform current status of proposed 132/33KV Yinkiong S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | The construction of various elements will be alligned as per overall construction schedule. At source, the bay will be made available as per construction schedule.
4 | 5B | Proposed 132/33 KV Kambang S/s | 33KV SC incomer line for new 33/11KV Kaying S/s | Kindly inform current status of proposed 132/33KV Kambang S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | Same as above (refer reply to Sl. No. 3 above)
5 | 5C | 132/33 KV Tezu S/s U/construction by POWERGRID | 15 KM SC line for 33/11 KV existing WaKro S/s | Kindly inform current status of proposed 132/33KV U/construction Tezu S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for existing Wakro S/s | Same as above | Same as above (refer reply to Sl. No. 3 above)
6 | 5C | 132/33 KV Roing S/s U/construction by POWERGRID | 33KV SC incomer line for new 33/11KV Bloung S/s | Kindly inform current status of proposed 132/33KV U/construction Roing S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | Same as above (refer reply to Sl. No. 3 above)
7 | 5C | Proposed 132/33 KV Halaipani S/s | 33KV SC incomer line for new 33/11KV Hawai S/s | Kindly inform current status of proposed 132/33KV Halaipani S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | Same as above (refer reply to Sl. No. 3 above)
8 | 5C | Proposed 132/33 KV DambuK S/s | 33KV SC incomer line for new 33/11KV Bizari S/s | Kindly inform current status of proposed 132/33KV Dambuk S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | Same as above (refer reply to Sl. No. 3 above)
9 | 5C | Proposed 132/33 KV Wallong S/s | 33KV SC incomer line for new 33/11KV Hawai S/s | Kindly inform current status of proposed 132/33KV Wallong S/s. Please inform the estimated time for charging and handover of this S/s Also please inform 33KV spare bay will be available for new S/s | Same as above | 33/11KV Wallong S/S is a new S/s and is under the scope of ARP-DMS-05C. The required bay has been considered under the scope of work.
Non availability of Incomer Line details [Source S/s]
10 | 5A | 33/11KV new Nacho S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | If spare bay is not available than who will constcruct the spare bays and when it will be handed over to the contractor/bidder. | The Incomer 33 kV line is planned in other package.
11 | 5B | 33/11KV new Mechuka S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | Same as above | The proposed S/s is within the boundary of 132/33 kV Substation. So no additional 33 kV line considered
12 | 5C | 33/11KV new Tuting S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | Same as above | The proposed S/s (Tuting is in Package- ARP-DMS-05B). This S/s is within the boundary of 132/33 kV Substation. So no additional 33 kV line considered
13 | 5C | 33/11KV new Anini S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | Same as above | The proposed Anini S/S will be connected to Etalin S/s through 132KV line charged on 33Kv level. The quantity of material for 33 kV Bay has been considered in the BOQ as per requirement.
14 | 5C | 33/11KV new Etalin S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | Same as above | The proposed Etalin will be connected to 132/33Roing S/S through 132KV line charged on 33Kv level. The 33 kV line shall be available at Substation and no bay at source end has been considered in present scope.
15 | 5C | 33/11KV new Halaipani S/s | Source S/s name is not available in tender document. | Kindly inform the name of source S/s and also please inform spare bay is avilable at this S/s | Same as above | The proposed S/s is within the boundary of 132/33 kV Substation. So no additional 33 kV line considered
Lines from existing 33/11KV and 132/33 KV Substations
16 | 5A | Existing 132/33 KV Daporijo S/S | Incomer for new 33/11 KV new Sippi, Maro and Murimugli S/s | Please inform 33kV spare bays are available at existing 132/33 KV Daporijo S/S for the new S/s. | If spare bay is not available than who will constcruct the spare bays and when it will be handed over. | The 33 kV Bays are available at 132/33 kV Daporijo S/s.
Status of Land - Land avaibale/Handed over land
17 | 5A | Giba | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Owner to ensure handing over of land before placing the order else this will effect the overhead and cash flow during execution which in turn will effect the L2 schedule. | Land will be made available as per construction schedule.
18 | 5A | Maro | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
19 | 5A | Murimugli | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
20 | 5A | Nacho | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
21 | 5A | Nyapin | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
22 | 5A | Sippi | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
23 | 5A | Tali | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
24 | 5A | Thalia | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
25 | 5B | Boleng | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
26 | 5B | Jengging | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
27 | 5B | Kaying | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
28 | 5B | Koreng | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
29 | 5B | Maryang | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
30 | 5B | Mechuka | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
31 | 5B | Tuting | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
32 | 5c | Bijari | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
33 | 5c | Bolung | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
34 | 5c | Halaipani | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
35 | 5c | Hawai | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)
36 | 5c | Wallong | Land availability staus - Land identified by DoPAP | Kindly inform when the land will be handed over. | Same as above | Same as above (refer reply to Sl. No. 17 above)