Appendix-4-Rev-01

TIME SCHEDULE

- The Project Completion Schedule shall be as follows:

| Description | Duration in Months from the date of Notification of Award |
| --- | --- |
| Taking Over by the Employer upon successful Completion of: |  |
| Reactor Package -RT- 06 for (i) 1x125MVAr, 400kV Bus Reactor at Kishenpur Sub-Station, (ii) 1x125MVAr, 400kV Bus Reactor at Maharanibagh (GIS) Sub-Station, (iii) 1x125MVAr, 400kV Bus Reactor at Mandola Sub-Station (iv) 1x125MVAr, 400kV Bus Reactor at Hissar Sub-Station, (v) 1x125MVAr, 400kV Bus Reactor at Chamera (GIS) Pooling Sub-Station, (vi) 1x125MVAr, 400kV Bus Reactor at Moga Sub-Station, (vii) 1x125MVAr, 400kV Bus Reactor at Sikar Sub-Station, (viii) 1x125MVAr, 400kV Bus Reactor at Allahabad Sub-Station, (ix) 1x125MVAr, 400kV Bus Reactor at Meerut Sub-Station, (x) 1x125MVAr, 400kV Bus Reactor at Jallandhar Sub-Station and (xi) 1x125MVAr, 400kV Bus Reactor at Patiala Sub-Station under Northern Region Strengthening Scheme (NRSS)- XL. Spec. No.: CC-CS/906-NR1/RT-3925/3/G4 |  |
| 03 nos. Reactor | 15 months (Fifteen Months) |
| 03 nos. Reactor | 16 months (Sixteen Months) |
| 05 nos. Reactor | 18 months (Eighteen Months) |

1.1	The activity(ies) under the Contractor’s programme for Project Completion shall be in the form of a master network (MNW) and shall identify the various activities like design, engineering, manufacturing, supply, installation, factory testing, transportation to site, site testing and commissioning, trial operation and Taking Over etc. of the Facilities or specific part thereof (where specific parts are specified in SCC). The network shall conform to the above Project Completion Schedule.

This master network will be discussed and agreed before Award in line with above, engineering drawing and data submission schedule shall also be discussed and finalised before Award. Liquidated damages for delay in successful Completion of the Facilities or specific part thereof (where specific parts are specified in SCC) and Operational Acceptance at rates specified in Clause 21 of GCC shall be applicable beyond the date specified above.

1.2	The Employer reserves the right to request minor changes in the work schedule at the time of Award of Contract to the successful Bidder.

1.3	The successful Bidder shall be required to prepare detailed Network(s) and project implementation plans & programmes and finalise the same with the Employer as per the requirement specified in Technical Specifications, which shall from a part of the Contract.

1.4	Time for Completion is the essence of Contract.