| S N | Clause | Provision of Bidding Documents | Bidder’s Query | POWERGRID's Reply |
| --- | --- | --- | --- | --- |
| A | Commercial (Volume-I of the Bidding Documents) |  |  |  |  |
| 1. | Payment Terms | If Advance is not opted: For SW: 30% after FAT, 55% after Field Test, 15% against Operational acceptance For HW: 70% after shipment, 15% on receipt of equipment at site (incl. spares), 15% against Operational acceptance | As the OEMs of Hardware & Software for various equipments are not agreeing to the payment terms offered by this contract and our overall scope as SCADA OEM in the project is less than 15%, we request for improved payment terms. 1. Interest free advance 2. For SW: 65% after FAT, 30% after Field Test, 5% against Operational acceptance 3. For HW: 75% after shipment, 20% on receipt of equipment at site (incl. spares), 5% against Operational acceptance | Provision of bidding documents shall remain unchanged. |
| B | Commercial (Volume-I of the Bidding Documents) |  |  |  |
| 2. | Project Completion Schedule Vol-II Part 1 of 7. Page 61 0f 102 | Completion schedule of the project is 15 months from the date of agreement. | The project is site intensive (13 Control centers + 300 Substations) and huge volume of hardware needs to be procured, installed, tested, inspected, dispatched, and commissioned. It would be very challenging. We proposed that critical milestones be defined and met in 15 months whereas the overall project can be allowed to be delivered in 30 months without any Liquidated damages being imposed on the suppliers. We also propose partial acceptance & Sample FAT for the project to expedite the deliveries. | Bidder to comply Technical Specifications. |
| 3. | Re-warranty Clause 22.8 of GCC Page No 64 of 92 | Upon correction of the defects in the Facilities or any part thereof by repair / replacement, such repair / replacement shall have the Defect Liability Period extended by a period mentioned in GCC Sub-Clause 22.2 from the time of such replacement/repair of the facilities or any part thereof. | We request that the Defect Liability period / Latent Defect Liability of any product should be capped to a maximum of 5 years or seize at the completion of AMC tenure. | For Defect Liability Period provisions of Bidding Documents shall remain unchanged. Refer Amendment-V for Latent defects liability. |
| 4. | Support in case of End of Life or End of Support Vol_II Part 1 Page No 67/102 | The contractor has to ensure with OEM for maintenance and services support for the hardware and software delivered under this project till the completion of AMC period. In case, any hardware / software / equipment /component items of the systems supplied under the contract shall reach its End-of-Life (EOL) or End-of Support (EOS) whichever is earlier, the contractor shall replace such item with new Hardware or/and Software without any financial implication to employer. | Cyber Security is ever evolving domain and PGCIL OT infrastructure is mission critical for the power security of the county. Thus, for any equipment which does not pose cyber security threat, we propose to continue service with help of third-party supplier in case OEM support is not available. For equipment which pose cyber security threat on EOL/EOS, we propose PGCIL to supply and we would integrate the same as a scope of this project | Please refer S. no 9 of Clarification-1. |