| SN | Clause No. | Provision in the Bidding Documents | Bidder’s Query/Comments | POWERGRID’S Reply/Clarification |
| --- | --- | --- | --- | --- |
| 1 | Cl. 1.1 (c), Appendix-1: Terms and Procedures of Payment, Section-VI: Sample Forms and Procedures, Vol.-I of the Bidding Documents | Final Payment The balance ten percent (10%) shall be released as per the following: - 7.5% of the Ex-works price component shall be released on erection of each complete tower or after six (6) months of supply of each complete tower whichever is earlier. - Balance 2.5% of the Ex-works price component shall be released on Commissioning of the transmission line. If Commissioning of the line is delayed beyond 12 months from the supply of last lot#, this payment shall be released on submission of an unconditional & irrevocable Bank Guarantee for full 2.5% amount initially valid till scheduled date of commissioning of the transmission line and shall be extended from time to time till the actual date of commissioning of the line. ………………… ………………… | Considering this package being supply package wherein the liability of supplier ceases on handing-over of complete tower and insurance scope is also for transit/marine insurance only. Accordingly, request to consider the release of final payment as following clause:- Final Payment The balance 10% (Ten Percent) of the Ex-Works Price Component shall be paid on receipt of Goods at site and on submission of invoice supported by the Material Acceptance Certificate issued by the Purchaser’s representative. | Provisions of the Bidding Documents shall remain unchanged. |
| 2 | ITB 11.4(b), Section-III: BDS, Vol.-I of the Bidding Documents | Replacing ITB Clause 11.4(b) with the following: Local/inland transportation, In-transit insurance, loading and unloading of the Plant and Equipment including mandatory spares to be supplied shall be quoted separately in Schedule 2, as composite supply of services, with local/inland transportation being the Principal Supply… ……………………. Note: Bidders are required to quote Local/Inland transportation, In-transit insurance, loading and unloading (F&I) charges under Schedule-2 on unit per KM basis. The F&I charges for 500 KM shall be used for bid evaluation. However, the payment of the F&I Charges shall be made on actual distance basis. The computation of the distance for such payment shall be based on the shortest feasible distance by National Highway, State Highway or other roads, in the order of preference, as indicated on such resources as Internet websites like Google Maps, Map my India. | 1) We understand that freight is to be calculated on a distance of 500 km & freight charges to be charged on per Km basis, Hence, please confirm tentative break-up of regions/ locations, enabling transporters to assess the cost and quote accordingly. 2) Please arrange to clarify that supplier shall be independent to supply from any of their tower factory (in case of multiple PGCIL approved manufacturing units) considering the work-load, at the time of issuance of delivery instruction and pre-declaration will not be required for supply from any specific unit. | 1) Please refer Sl. No. 2 of already issued Clarification No. 1 (commercial part) dated 20.03.2020 in this regard. 2) Please refer Clarification No 2 (technical part) attached herewith. |
| 3. | GCC 1.1 (k), Section-V: SCC, Vol.-I of the Bidding Documents | Supplementing Sub-Clause GCC 1.1(k) Delivery Schedule shall be as per Delivery Instruction issued to Supplier from time to time in the event of emergence of requirement. Such Delivery Instruction(s) shall be issued to the Supplier within a period of 02 years from the date of issuance of Notification of Award and this period may be extended further by the Purchaser for 01 year on same rates, terms & conditions. The commencement of supply shall be 90 days from the date of issue of Delivery Instruction. Monthly delivery schedule shall be kept upto 1000 MT. However, based on the requirement this can be increased on mutual agreement basis while finalizing the detailed master network (MNW). Each Delivery Instruction shall contain its separate Delivery Schedule and details of Goods for part of the Facilities based on actual requirement. | Please arrange to clarify that in case of any clashing of DI with existing half yearly/annual dispatch schedule of the factories will be mutually discussed and agreed upon. | Provisions of the Bidding Documents inter-alia at GCC 1.1(k) are amply clear. |
| 4. | General | - | Please confirm the Consignee details / complete address | Please refer Sl. No. 2 of already issued Clarification No. 1 (commercial part) dated 20.03.2020 in this regard Consignee details / address shall be conveyed at the time of issuance of Delivery Instruction in line with the provisions of the Bidding Documents. |
| 5. | ITB 11.5, Section-II: ITB, Vol.-I of the Bidding Documents | The prices shall be in accordance with the following: Adjustable Price: Prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, etc. in accordance with the procedures specified in the corresponding Appendix – 2 to the Form of Contract Agreement. A bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. The price adjustment provision will not be taken into consideration in bid evaluation. Bidders are required to indicate the source of labour& materials indices in Attachment 12. | Please also confirm whether prices are Firm basis or Variable basis | Provisions of the Bidding Documents are amply clear. |