| Sl. No. | # Volume/ Section/ Description | # Clauses | # Bidder’s Query | # POWERGRID Reply |
| --- | --- | --- | --- | --- |
| Volume-I: Condition of Contracts |  |  |  |  |
|  | 5.0, Appendix-2, Section-VI, Sample Forms and Procedures (SFP) | 5.0 The above price adjustment provision shall be invoked by either party subject to the following further conditions: a) For the purpose of Price Adjustment on ex-works price components of the equipment, the date of shipment for Goods shall mean scheduled date of shipment or actual date of shipment, whichever is earlier. Scheduled date of shipment will be ex-works date of despatch, governed by the accepted PERT Network/Bar Chart. Similarly, for the purpose of Price Adjustment on Installation price component, the Billing period shall mean the billing period as per Contract time schedule i.e., the agreed Bar Chart or actual period, whichever is earlier. The Billing period for various Installation activities will be as per agreed Installation Bar Chart indicating monthly schedule of Installation activities for completion of works. However, when the Employer’s specific approval for advancement of shipment/installation activities has been obtained in such case the said advanced date shall be treated as the schedule date of shipment/installation activities for the purpose of working out the price adjustment payable. No price increase shall be allowed beyond the original delivery/ Installation dates unless specifically stated in the Time Extension Letter, if any, issued by the Employer. The Employer will, however, be entitled to any decrease in the Contract Price which may be caused due to lower price adjustment amount in case of delivery of Goods/ Installation beyond the original delivery/Installation dates. Therefore, in case of delivery of Goods/Installation beyond the original delivery/ Installation dates, the liability of the Employer shall be limited to the lower of the price adjustment amount which may work out either on schedule date or actual date of despatch of Goods/ Installation. b) In case IEEMA does not publish any of the price indices, as mentioned above, the Bidder shall indicate any nationally recognised published index for respective items and the source of the same shall be furnished in the Bid. c) In case of non-publication of applicable indices on a particular date, which happens to be the applicable date for Price Adjustment purposes, the published indices prevailing immediately prior to the particular date shall be applicable. d) If the Price Adjustment amount works out to be positive, the same is payable to the Contractor by the Employer and if it works out to be negative, the same is to be recovered by the Employer from the Contractor. e) The Contractor shall promptly submit price adjustment invoices for the supplies made/work done, positively within three (3) months from the date of shipment/ work done, whether it is positive or negative. | "As per given PV formula, base is Calendar month preceding the month of opening of Bids and bid opening is in month of FEB-23 and accordingly base will be monthly average of JAN-23 and we will get the JAN-23 IEEMA Circular in month of FEB-23. Please confirm the month to be considered for offer." | Provisions of the Bidding Documents are amply clear. |
| Volume-II: Technical Specifications |  |  |  |  |
|  | General | General | For the 33 kV cable laying scope cable route is not given in the tender documents. Requesting PGCIL to provide us the cable route. | Refer Sl. No. 1 of Amendment-02. |
|  | Section-I Project (Part-C) R2 - Clause 4 4. REINSTATEMENT & Section-III, Chapter 2 (Cable laying) Clause 15 REINSTATEMENT | Clause 4 4. REINSTATEMENT of Section-I Project (Part-C) R2 & Clause 15 REINSTATEMENT of Section-III, Chapter 2 (Cable laying) | As per Section-I Project (Part-C) R2 - Clause 4 4. REINSTATEMENT " In case of the road surface is cement concrete, asphalt or tarred macadam, resurfacing shall be done by the civic authorities against payment of the restoration charges to be made by Contractor directly to concerned agency." However, Section-III, Chapter 2 (Cable laying) Clause 15 REINSTATEMENT says "In case of the road surface is cement concrete, asphalt or tarred macadam, resurfacing shall be done by the civic authorities against payment of the restoration charges to be made by BSEB directly to concerned agency." Request you to confirm us the who will pay the restoration charges. | Refer Sl. No. 2 the Amendment-02. |
|  | Section-I Project (Part-C) R2 - Clause 4 4. REINSTATEMENT . | Clause 4 4. REINSTATEMENT. | After conducting the WOS, we understand that the cable is to be laid along with new road connecting to tunnel. Which is under construction at this stage. It is very difficult to estimate the road restoration charges which is in the scope of the bidder. As per Section-I Project (Part-C) R2 - Clause 4 4. REINSTATEMENT. Therefore we request Powergrid to consider the same in PGCIL scope or make it unit rate in BOQ. | Bidder to comply the TS. |
|  | 2.0 GTR Rev 15 | Clause 8.3.22 For EHV transformers/reactors | "Insulation oil shall be as per POWERGRID Technical specifications and same grade shall be used for impregnation of the active part & testing at the works of Transformer/Reactor Manufacturer and as well as for filling the Transformer/Reactors at site. Contractor to ensure that windings for Transformer/Reactors are made in air-conditioned environment. Core-coil assembly shall be performed in positive pressurized dust controlled environment. Dust measurements shall be monitored regularly at Transformer / Reactor Manufacturer works. Contractor shall ensure that respective civil foundations & Fire walls for Transformer/ Reactors units to be commissioned, shall be made ready at concerned sites before receipt of Transformer/Reactors units. All the requisite material for Neutral & Delta Bus formation required for charging of complete bank of 765KV class 1-ph Transformer/Reactor units shall be made available at the concerned sites before receipt of the Transformer/Reactor units at site." Please suggest us the manufacturer meeting above clause. Since we have received regret from many reputed make. | Bidder may refer the Compendium of Vendors for approved makes. Further, Clause 8.3.22 of Section: GTR, Rev.15 shall be read in conjunction with Cl. 6.16.1 of Section: Transformer (upto 400kV Class), Rev.13 for requirements of Transformer winding manufacturing atmosphere. |