SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Plant and Equipment to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | GCC 1.1 (e) | Supplementing Clause GCC 1.1 (e) with following: The scope for the Completion, as per Clause 2 of Section Project, Technical Specification, Volume-II of the Bidding Document, shall cover the Pre-commissioning/Commissioning of the Facilities (or a specific part thereof where specific parts are specified in the SCC). |
|  | GCC 1.1(e) & 1.1(ee) | Supplementing Sub-Clause GCC 1.1(e) The Time for Completion shall be as under : Description; Duration in Months from the date of Notification of Award. Taking Over by the Employer upon successful Completion of. Reactor Package RT03 under "Bulk Procurement of 765kV & 400kV Class Transformers & Reactors of various capacities-LOT-3 and SIS/Addl. Cap.”. Spec. No: 5002002360/REACTOR/DOM/A06-CC CS -7; 15 months (Fifteen Months). |
|  | GCC 1.1(o) | Supplementing Sub-Clause GCC 1.1(o) The Employer is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. Kind Attn.: Sr. GM(CS-G7)/ DGM(CS-G7)/Dy. Manager(CS-G7), Power Grid Corporation of India Limited ‘Saudamini’, 3rd Floor, Plot No.-2, Sector-29 Gurugram (Haryana) - 122001. Telephone Nos: +91-124-282- 2399/3313/3316 Mobile: +91- 9910378008/9971399074/9582070532 Fax Nos.:- +91-124-2571 831 Email Address: edward@powergrid.in , nrapendra@powergrid.in , kr.siddhant@powergrid.in |
|  | GCC 1.1(w) | Supplementing Sub-Clause GCC 1.1(w) The Owner is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. Kind Attn.: Sr. GM(CS-G7)/ DGM(CS-G7)/Dy. Manager(CS-G7), Power Grid Corporation of India Limited ‘Saudamini’, 3rd Floor, Plot No.-2, Sector-29 Gurugram (Haryana) - 122001. Telephone Nos: +91-124-282- 2399/3313/3316 Mobile: +91- 9910378008/9971399074/9582070532 Fax Nos.:- +91-124-2571 831 Email Address: edward@powergrid.in , nrapendra@powergrid.in , kr.siddhant@powergrid.in |
|  | GCC 3.1.1 | Add new sub-clause: - (Amendment for change in destination) - During the course of contract, destination of Reactor may be changed by POWERGRID, based on Project exigency. New delivery destination will be intimated to the Contractor, by POWERGRID, in writing. - In case of Change of destination is required, following modalities shall be applicable for Post-LOA modification of F&I charges: The computation of the actual distance travelled, shall be based on the shortest feasible distance by National Highway, State Highway or other roads, in the order of preference. - For computation of the “NEW F&I rate”, bifurcation of the F&I Unit rate (as per LOA) of 20% as Fixed charge & 80% of Variable charge shall be considered. - Variable charge thus computed shall be utilized for reaching Per KM rate with respect to LOA Unit rate, to be multiplied by actual distance travelled, for finalizing new Variable charge, effective for new delivery destination |
|  | GCC 4.1 | Replace GCC 4.1 with the following 4.1 Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. |
|  | GCC 5.1 | Supplementing Clause GCC 5.1 with the following: If case of contract on an Indian Entity, established as Subsidiary/JVC/Group company by its Parent/ Principal company, based on the Financial support of the Parent/ Principal Company pursuant to ITB clause 11.1, the Parent/ Principal Company of such an Indian Entity shall fulfill the following requirements as the case may be: (a) The Parent/ Principal Company shall have a minimum equity participation of 51% in the Subsidiary Company for a lock-in period of seven (7) years from the date of incorporation of Subsidiary Company or upto the end of Defect Liability Period of the contract, whichever is later (applicable in case Contractor is a Subsidiary Company) (b) The Parent/ Principal Company and the Group Company shall have a common source of control, directly or indirectly, so as to exercise a minimum equity participation of 26% or appoint more than 50% of members of Board of Directors in the Group Company. The promoter of the Group Company shall maintain the minimum equity participation in the Group Company for a lock-in period of seven (7) years from the date of incorporation of Group Company or upto the end of Defect Liability Period of the contract, whichever is later (applicable in case Contractor is a Group Company) (c) The Parent/ Principal Company shall have a minimum equity participation of 26% in the Joint Venture Company (JVC) for a lock-in period of 7 years from the date of incorporation of JVC or upto the end of Defect Liability Period of the contract, whichever is later An Indian Reactor Manufacturer, as a promoter of JVC who has designed, manufactured, tested and supplied at least one number of 345kV class or above class of Reactor shall have a minimum equity participation of 51% in the JVC for a lock-in period of 7 years from the date of incorporation of JVC or upto the end of Defect Liability Period of the contract, whichever is later (applicable in case Contractor is a Joint Venture Company) |
|  | GCC 5.7 | Insert a new clause GCC 5.7 as follows: Vide Notification dated 8th May 2017 its revision dated 29th May 2019 by Ministry of Steel has published “ Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement”. The Contractor shall comply with the guidelines specified in the policy including subsequent amendments/ modifications, if any. Accordingly, the Contractor shall be required to provide a value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the Policy. Such certificate shall be filed within 60 days of commencement of each half year, to the respective executing Region of POWERGRID and shall continue to be filed till the completion of supply of the said products. Further, if the Domestic manufacturer from whom the Contractor had proposed to source the Iron & Steel products is changed during execution of the Contract, the Contractor shall furnish (i) authorization certificate, if applicable, (ii) affidavit of self-certification and (iii) value- addition certificate from the new Domestic manufacturer. Violation to minimum prescribed domestic value addition or misrepresentation of facts by the bidder in this regard shall be dealt in line with provisions of the Integrity Pact. |
|  | GCC 9.2.2 | Replace GCC 9.2.2 with the following The security shall be in the Form of unconditional Bank Guarantee attached hereto in Section VI - Sample Forms and Procedures. The security shall be discharged after completion of the facilities or relevant part thereof corresponding to which advance has been drawn. - Procedure for effective reduction in the Advance Payment Security The Advance Payment Security shall be allowed to be reduced every six (06) months after First Running Account Bill/Stage payment under the Contract if the validity of the Bank Guarantee is more than one year. The cumulative amount of reduction shall be allowed upto full value of the Bank Guarantee upon adjustment of the corresponding advance and certification to this effect by the Employer’s representative. It should be clearly understood that reduction in the value of advance Bank Guarantee shall not in any way dilute the Contractor's responsibility and liabilities under the Contract including in respect of the Facilities for which reduction in the value of security is allowed. |
|  | GCC 9.3.1 | Replace First Para of GCC 9.3.1 with following: The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Three percent (3%) of the Contract Price, with a validity upto ninety (90) days beyond the Defect Liability Period. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. |
|  | GCC 9.3.1 | Supplementing GCC Clause 9.3.1 with following: The Performance Securities for the due performance of the Contract in the amount equivalent to three percent (3%) of the Contract Price, shall be provided by the Contractor as per the following: - Performance Security in the amount equivalent to Three percent (3%) of the Ex-works Price of 765KV & 400kV Class Reactors with a validity upto ninety (90) days beyond the Defect Liability Period for said equipments [refer GCC Sub-clause 22.2(i)]. - Performance Security in the amount equivalent to Three percent (3%) of the balance Contract Price for all equipment/materials other than those specified in (i) above, with a validity upto ninety (90) days beyond the Defect Liability Period, applicable for said equipment [refer GCC Sub-clause 22.2(ii)] Further, the Contractor shall arrange additional Performance Security(ies), if applicable, as per Clause no. 4 of Joint Deed of Undertaking mentioned at Sl. No. 20 of Section-VI: Sample Forms and Procedures as detailed below: For Collaborator (as per clause 1.2 of Annexure-A (BDS) – Route-2): - The Performance Security in the amount equivalent to three percent (3%) of the Contract Price for 765kV & 400kV Reactors to be supplied from the Indian manufacturer who have established production line in India for these equipment based on technological support with a validity upto ninety (90) days beyond the Defect Liability Period for said equipment [refer GCC Sub-clause 22.2(i)]. For Parent/Principal Company (as per clause 1.3 of Annexure-A (BDS) – Route-3): - The Performance Security in the amount equivalent to three percent (3%) of the Contract Price for 765kV & 400kV Reactors to be supplied from the Indian entity established as Subsidiary/ JVC/Group company who have established production line in India for these equipment with a validity upto ninety (90) days beyond the Defect Liability Period for said equipment [refer GCC Sub-clause 22.2(i)]. The said security(ies) shall be required to be extended time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. The Performance Security(ies) to be furnished by the Contractor under the Contract shall be in favour of the Employer. The Owner shall also be entitled to enforce these performance security(ies). |
|  | GCC 9.3.1.2 (b) | Replace the Clause reference GCC 9.3.1.1(b) appearing in second line with Clause GCC 9.3.1.2(a) |
|  | GCC 9.3.1.2 (d) | Replace Sub-Clause GCC 9.3.1.2 with following: In case the Contractor fails to submit the performance security within 90 days of the Notification of Award, the Employer, without prejudice to any other rights or remedies it may possess under the Contract, may consider the bid submitted by the Contractor in future packages as non-responsive in line with ITB 13.6 and/or may terminate the Contract forthwith pursuant to GCC Clause 36. |
|  | GCC 9.3.2 | Replace Sub-Clause GCC 9.3.2 The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer/Owner as stipulated in SCC in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergrid.in. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–CC. Name of Depositor; Name of the Contractor/Collaborator/Tower manufacturer/Licensor etc.. Vendor Code, if applicable; POWERGRID vendor code of the Contractor Collaborator/Tower manufacturer/Licensor etc., if existing. Payment Remarks; Performance Security for ………….. [enter the name of the contract and last four digits of the CA number]. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. |
|  | GCC 9.3.3 | Replace existing GCC clause 9.3.3 with following: Reduction in the security pro rata to the Contract Price of any part of the Facilities is not admissible. However, if the Defects Liability Period has been extended on any part of the Facilities pursuant to GCC Sub-Clause 22.8 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor pursuant to GCC Sub-Clause 22, is liable for an extended warranty obligation, the performance security shall be reduced to three percent (3%) of the value of the component covered by the extended warranty. |
|  | GCC 9.3.5 | Add new sub Clause GCC 9.3.5 No interest shall be payable by the Employer on the performance Security. |
|  | GCC 9.3.6 | Add new sub Clause GCC 9.3.6 During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque/ online payment through POWERGRID ONLINE PAYMENT UTILITY, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 9.4 | Replace Clause GCC 9.4 The Bank Guarantee for Advance Payment Security and Performance Security are to be provided by the Contractor, which should be issued either: (a) by a Public Sector Bank located in India, or (b) a scheduled Indian Bank having paid up capital (net of any accumulated losses) of Rs. 1,000 Million or above (the latest annual report of the Bank should support compliance of capital adequacy ratio requirement), or (c) by a foreign bank or a subsidiary of a foreign bank, acceptable to the Employer, with overall international corporate rating or rating of long term debt not less than A- (A minus) or equivalent by a reputed rating agency. Further, the Bank Guarantee should be confirmed by either (i) its corresponding bank located in India; or (ii) a Public Sector Bank located in India; or (iii) a scheduled commercial private bank located in India as per para (b) above. |
|  | GCC 9.4 | Supplementing GCC Clause 9.4 with the following The contractor has the option to submit BG (towards Advance Payment Security and Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Advance Payment Security and Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; IFSC Code; POWERGRID Current A/c No.. State Bank of India, 4th & 5th Floor, Parsvnath Capital Tower, Bhai Veer Singh Marg, Gole Market, New Delhi - 110001; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram; ICIC0002451; 000705002702. Note: Any one of the above account details can be used for the issuance of Bank Guarantee using SFMS Platform. In case of Bank Guarantee (towards Advance Payment Security and Performance Security) verification through SFMS facility of ICICI Bank, the applicant has to provide a unique identifier of POWERGRID to the issuing bank. This unique identifier needs to be incorporated by the issuing bank in Field 7037of the IFIN 760 COV/ IFIN 767 COV while transmitting these messages to the Beneficiary Bank through SFMS. The unique identifier of POWERGRID is PGCIL50948846. In addition to the above, the Bank Guarantee (towards Advance Payment Security and Performance Security) should be submitted in the Physical form as specified in GCC Clause 9. |
|  | GCC 15.1 | The corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement specifies major items of supply or services and a list of approved Subcontractors against each item, including vendors. Insofar as no Subcontractors are listed against any such item, the Contractor shall prepare a list of Subcontractors for such item for inclusion in such list. The Contractor may from time to time propose any addition to or deletion from any such list. The Contractor shall submit any such list or any modification thereto to the Employer for its approval in sufficient time so as not to impede the progress of work on the Facilities. Such approval by the Employer for any of the Subcontractors shall not relieve the Contractor from any of its obligations, duties or responsibilities under the Contract. Further, the Contractor shall not subcontract any work to a subcontractor/sub vendor from such countries which shares a land border with India unless such subcontractor/sub vendor fulfills all requirement in regard to ‘Bidder from a country which shares a land border with India’ as per ITB clause 2.1. This restriction on subcontracting shall not be applicable for procurement of raw materials, components, sub-assemblies etc. However, in case of finished goods procured directly/indirectly from the vendors from the countries sharing land border with India, such vendor will be required to be registered with the Competent Authority. |
|  | GCC 15.3 | Replace the existing provision with the following: For items or parts of the Facilities not specified in the corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement for Supply of Goods Contract(s), the Contractor may employ such Subcontractors as it may select, at its discretion. |
|  | GCC 15.5 | Adding New sub clause GCC 15.5 The Contractor shall sign the Integrity Pact with its Subcontractors before employing under the Contract. |
|  | GCC 18.1.3(a) | Replace GCC 18.1.3(a) with the following: (a) The Contractor shall provide and employ on the Site in the installation of the Facilities such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. Labour having “Recognition of Prior Learning”(RPL) Certification (under Pradhan Mantri Kaushal Vikas Yojana(PMKVY)) can also be employed by the Contractor. The Contractor is encouraged to use local labor preferably from weaker sections of society particularly SC & ST persons, that has the necessary skills. |
|  | GCC Cl. 18.3.1.4(a) | Replace the existing Sub-Clause 18.3.1.4 (a) as follows: (a) Employee’s Compensation Act 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment. |
|  | GCC Cl. 18.3.3.17 | Replace GCC Clause 18.3.3.17 with the following: The Contractor shall deploy Safety Officer(s)/Safety Supervisor(s) /Safety Steward(s) in line with requirements as specified in the Safety Plan. The qualifications and experience, roles and responsibilities of the Safety Officer(s)/Safety Supervisor(s) /Safety Steward(s) shall be as prescribed in the Safety Plan. In case, the Contractor fails to deploy Qualified Safety Officer(s)/Safety Supervisor(s) /Safety Steward(s) under each Contract, as specified in the Safety Plan, then the Contractor shall be responsible for payment of a sum of Rs. 15,00,000/- per quarter or part thereof, on a pro-rata basis, till the Safety Officer(s)/ Safety Supervisor(s) /Safety Steward(s)) is deployed, to be deposited with the Employer, which will be retained in the Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26. Further, the Project Manager shall have the right at his sole discretion to stop the work in line with GCC Sub-Clause 18.3.3.19 till the Safety Officer(s)/ Safety Supervisor(s) /Safety Steward(s) is deployed by the Contractor. The name and address of such Safety Officers Safety Supervisor(s) /Safety Steward(s) of the Contractor will be promptly informed in writing to Project Manager or his authorised representative with a copy to Safety Officer-In charge before he starts work or immediately after any change of the incumbent is made during currency of the Contract. |
|  | GCC Cl. 18.3.3.18 | Replace GCC 18.3.3.18 with the following: In case any accident occurs during the construction/ erection or other associated activities undertaken by the Contractor thereby causing any minor or major or fatal injury to his employees due to any reason, whatsoever, it shall be the responsibility of the Contractor to promptly inform but no later than 4 hrs. of the occurrence of the same, to the Project Manager in prescribed form and also to all the authorities envisaged under the applicable laws. Notwithstanding above, in case of any fatal accident, the Board of Directors of Contractor shall review the incidence and a copy of Board’s resolution signed by the Director/Company Secretary of the firm alongwith action plan for avoidance of such incidences in future shall be furnished promptly but no later than 60 days, to the Employer. Besides above, the CEO of the Contractor shall meet and apprise POWERGRID APEX SAFTEY BOARD alongwith the Board’s resolution of the cause of the fatal accident occurred and their future action plan/safety preparedness to prevent recurrence of such accidents in future within 60 days of the occurrence of the fatal accident. In case of failure of the Contractor to complete the above actions within 60 days, an extended period of 4 weeks is permitted to the Contractor to complete the same, along with a penalty of 0.05% of Contract Price as awarded, per week of delay or part thereof limited to Rs. 2.5 lakh per week, which shall be deposited in the Safety Corpus Fund. In case of failure of the Contractor to complete the above actions within the extended period of 4 weeks as above, the bids submitted by the Contractor shall be treated as non-responsive till completion of the same. In case of a fatal accident in a contract awarded to Joint Venture of 2 or more firms, partner(s) of the JV who was responsible for the execution of the said works as per their scope under the Contract, shall submit its Board Resolution and apprise the POWERGRID APEX SAFETY BOARD as brought out above. In case of a fatal accident in a contract awarded to and being executed by an Associate of Contractor, the Associate who is executing the erection/services contract corresponding to the scope of work in which accident has occurred, shall submit its Board Resolution and apprise the POWERGRID APEX SAFETY BOARD as brought out above. |
|  | GCC Cl. 18.3.3.23 | Replace GCC 18.3.3.23 with the following: If the Contractor fails in providing safe working environment as per Employer Safety Rules or continues the work even after being instructed to stop work by the Project Manager as provided in GCC Sub-Clause 18.3.3.19 above, the Contractor shall promptly pay to Employer, on demand by the Employer, a recovery at the rate of Rs. 10,000/- per day or part thereof to be deposited in Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26, till the instructions are complied with and so certified by the Project Manager. However, in case of accident taking place causing injury to any individual, the provisions contained in GCC Sub-Clause 18.3.3.24 shall also apply in addition to recovery mentioned in this Clause. |
|  | GCC Cl. 18.3.3.24 | Replace GCC Clause 18.3.3.24 with the following: In case of an accident at Site or adjacent thereto, the Contractor shall be responsible for payment of a sum as indicated below to be deposited with the Employer, which will be passed on by the Employer to such person or next to kith and kin of the deceased: a; Fatal injury or accident causing death; Rs. 15,00,000/- per person. b; Major injuries or accident causing 25% or more permanent disablement; Rs. 5,00,000/- per person. Permanent disablement shall have same meaning as indicated in Employee’s Compensation Act. The amount to be deposited with Employer and passed on to the person mentioned above shall be in addition to the compensation payable under the relevant provisions of the Employee’s Compensation Act and rules framed there under or any other applicable laws as applicable from time to time. In case the Contractor does not deposit the above mentioned amount with Employer, such amount shall be recovered by Employer from any monies due or becoming due to the Contractor under the contract or any other on-going contract. Notwithstanding above, while executing the Contract(s), in case of any permanent disablement in hands/legs due to any accident(s), the Contractor shall arrange to provide modern electronic artificial Limb (Hands/Legs) to the victims of the accident either through any NGO or directly and also provide necessary training to the victims to use the same. The cost/expenditure, if any, shall be borne by the Contractor and the details of the same shall be provided to POWERGRID for information. The above shall be in addition to the compensation payable to the victim as applicable. In case of first fatal accident, a warning letter shall be issued to the Contractor. In case of any subsequent fatal accident, the Contractor shall withdraw its Representative (Project Manager) immediately and shall appoint its Representative (Project Manager) afresh pursuant to GCC Clause 13.2. The Contractor’s Representative (Project Manager) removed hereinabove, thereafter shall not be permitted to work in any of projects/works of the Employer. |
|  | GCC Cl. 18.3.3.25 | Replace GCC 18.3.3.25 with the following: Notwithstanding above, the Contractor shall also be responsible for payment of sum as indicated below additionally which shall be deposited in Safety Corpus Fund pursuant to GCC Sub-Clause 18.3.3.26: a.; Upon 1st Fatal Accident; 1% of the Contract price as awarded, limited to Rs. 50,00,000/-. b.; Upon 2nd Fatal Accident; 1.5% of the Contract price as awarded, limited to Rs. 75,00,000/-. c.; Upon 3rd Fatal Accident; 2% of the Contract price as awarded, limited to Rs. 1,00,00,000/-. d.; Re-occurrence of Fatal Accident even after 3rd Fatal Accident; 2% of the Contract price as awarded, limited to Rs. 1,00,00,000/- per fatal accident. For the purpose of calculation of the aforesaid amounts, ‘Contract price, as awarded’, shall mean the total Contract Price for both Supply of Goods and Services for the works/facilities as per the originally awarded Contract/Notification/ Letter of Award (where contract has not been signed) exclusive of any taxes & duties additionally payable/reimbursable by POWERGRID or any change/adjustment due to Price Variation or subsequent amendments to the Contract or Notification/Letter of Award (where contract has not been signed). In case of a fatal accident in a contract awarded to Joint Venture of 2 or more firms, for the purpose of recoveries as per GCC Sub-Clause 18.3.3.24 and GCC Sub-Clause 18.3.3.25 above, the monies shall be recovered from the monies payable under the Contract to the JV in proportion to the price component of the scope of work of the respective partner. However, in case of shortfall in the recoveries of the due amount from any partner, the amount of such shortfall shall be recovered from the other partners(s) of JV. In case of a fatal accident in a contract awarded to and being executed by an Associate of Contractor, for the purpose of recoveries as per GCC Sub-Clause 18.3.3.24 and GCC Sub-Clause 18.3.3.25 above, the monies shall be recovered from the monies payable to the Contractor and the Associate under their respective contract(s) in proportion to the Contract Price of respective portion of scope, as awarded. However, if such monies to be recovered under any of the Contracts (say Services Contract), cannot be recovered from the concerned contractor (say Associate), it shall be suitably recovered from the other contracts (say CIF and Ex-works Supply contract). GST, if any, applicable on recoveries as mentioned at GCC Sub-Clause 18.3.3, shall be payable by the Contractor in addition to the amount of recoveries mentioned therein. |
|  | GCC Cl. 18.3.3.28 | Replace GCC Clause 18.3.3.28 with the following: The Contractor shall also submit ‘Safety Plan’ as per proforma specified in Section – Sample Forms and Procedures of the Bidding Documents alongwith all the requisite documents mentioned therein and as per check-list contained therein to the Engineer In-Charge for its approval within 30 days of Notification of award. Further, one of the conditions for release of first progressive payment / subsequent payment towards Services Contract shall be submission of “Safety Plan‟ alongwith all requisite documents and approval of the same by the Engineer In-Charge. |
|  | GCC Cl. 18.3.3.29 | Addition of following new sub-clause GCC Clause 18.3.3.29: Non-reporting of any accident to the Employer in any ongoing contract with the Employer or any suppression of facts/related information in regard to accident shall lead to determination of bid of such Contractors as non-responsive for all packages whose date of bid opening, originally scheduled and/or actual falls within a period of one year reckoned from the date on which the Employer determines Non-reporting of the accident/Suppression of facts/related information in regard to accident by the Contractor. |
|  | GCC 20.2.1 | Deleted as Guarantee Tests are not applicable. |
|  | GCC 20.2.2.1 (II) | Deleted as Functional Guarantees are not applicable. |
|  | GCC 21.1 | Supplementing the Clause GCC 21.1 with the following: Time for Completion: Sl. No.; Activities; Duration in months from the effective date of NOA. 1.; Reactor Package RT03 under " Bulk Procurement of 765kV & 400kV Class Transformers & Reactors of various capacities- LOT-3 and SIS/Addl. Cap.” Spec. No.: 5002002360/REACTOR/DOM/A06-CC CS -7; 15 months (Fifteen Months). |
|  | GCC 21.2 | Replace GCC 21.2 with the following: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price plus GST payable thereon for the whole of the facilities, (or a part for which a separate time for completion is agreed). The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damage which will be suffered by the Employer for default on the part of the Contractor and said amount will be payable without proof of actual loss or damage caused by such default. The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. |
|  | GCC 22.2 | Replace the first para of GCC Sub-Clause 22.2 with the following: “The Defect Liability Period shall be as under: - Sixty (60) months for 765kV & 400kV Class Reactors from the date of Taking Over /Completion of Facilities (or any part thereof). For the purpose of this clause, the Measurable Defects as per the Technical Specifications shall also be considered for 765kV & 400kV Class Reactors. - Twelve (12) months from the date of Taking Over/Completion of Facilities for all items other than those specified in (i) above. |
|  | GCC 22.8 | Supplementing Sub-Clause GCC 22.8 Upon correction of the defects in the 765kV & 400kV Class Reactor by repair/replacement, such repair/replacement shall have the Defect Liability Period of the said 765kV & 400kV Class Reactor extended by a period of 2 years from the time of such repair/replacement of the said 765kV & 400kV Class Reactor to rectify the defect, or up to the expiry of period mentioned in GCC Sub-Clause 22.2, whichever is later. |
|  | GCC 22.8.1 | Replacing the 2nd line of GCC Sub-Clause 22.8.1 with the following: The Contractor's liability for latent defects warranty shall be limited to period of five (05) years from the end of Defect Liability Period. |
|  | GCC 23 | Deleted as Functional Guarantees are not applicable. |
|  | GCC 24.1 | Applicable for - 125MVAR 420kV Class Reactors, - 80 MVAR 765kV Class Reactors, - 110 MVAR 765kV Class Reactors |
|  | GCC 24.2 (b) | Supplementing Clause GCC 24.2 (b) LD for Non-Performance of the Equipment The maximum loss at rated condition (voltage, current and frequency, as applicable) for each equipment shall be corrected in accordance with IEC-60076 for the purpose of comparison of maximum losses with measured losses for levy of liquidated damages. If during factory tests, if measured loss(es) are found to be more than the specified maximum value(s), Employer at his discretion may accept or reject the equipment after assessing the liquidated damages (LD) against the contract as per rates given below and such amount plus GST payable thereon shall be deducted from the contract price or otherwise recovered from Contractor. No cost benefit shall be considered in case measured losses are less than the specified maximum losses. Differential Price Factors for Liquidated Damages: The factors and the respective Indian Rupees value per unit of differential loss (applicable for each item/unit of facilities) for purpose of calculating differential price shall be as stipulated below: Sl. No.; Equipment; Parameter; Value of Liquidated Damages in Indian Rupees (applicable for each item/unit of the facilities) per unit of parameter differential with respect to maximum losses. 1.; 110 MVAR, 765kV, 1-Phase Reactor; Differential Total Load Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. Differential I2R Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. 2.; 80 MVAR, 765kV, 1-Phase Reactor; Differential Total Load Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. Differential I2R Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. 3.; 125 MVAR, 400kV 3-Phase Reactor; Differential Total Load Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. Differential I2R Loss (KW)*; INR 8,00,000/- (Indian Rupees Eight Lakhs only) per kW. Note: (*)During factory test, in case measured value of I2R Loss or Total Load Loss exceeds the specified value, then applicable Value of Liquidated damages shall be the amount of differential I2R Loss or differential Total Load Loss, whichever is higher. Also for a fraction of a kW, the penalty shall be applied on pro-rata basis. Liquidated damages shall be applied in the following manner depending on the variation of losses with respect to the guaranteed values: - Measured losses exceeding Guaranteed value by 0 to +2%: Rates of LD mentioned above However, the equipment shall not be accepted if either of the measured losses (i.e. Total Load Loss, I2R Loss) are more than +2 percent of the Maximum losses, at rated condition, specified in Technical Specifications, Volume-II of the Bidding Documents. |
|  | GCC 30.1(a) (I) (ii) | Replace the existing Provision GCC 30.1(a) (I) (ii) as below: Transit Insurance Policy for indigenous equipment Similarly, Transit Insurance Policy shall be taken wherein only inland transit is involved for the movement of Plant and Equipment including mandatory Spares supplied from within India. The policy shall cover movement of Plant and Equipment including mandatory Spares from the manufacturer’s works to the project’s warehouse at final destination site. Inland Transit Clause (ITC) ‘A’ along with Strike Riots & Civil Commotion (SRCC) extension cover shall be taken. |
|  | GCC 33.2.3 | Supplementing Clause GCC 33.2.3 Percentage for the Change Proposal under this Clause shall be limited to Fifteen (15) percent. |
|  | GCC 39.6 | Replace the existing Provision GCC 39.6 as below: 39.6 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute/ difference (other than those related to taxation matters) between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018 and DPE OM No. DPE-GM-05/0003/2019-FTS-10937 dated 20.02.2020. The decision through AMRCD will be final and binding on all the concerned. 39.7 During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. |
|  | Appendix to SCC | Enclosed herewith |

----- End of Section-V (SCC) ---