SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Plant and Equipment to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | General |  |
|  | GCC 1.1 (b), (c), (d), (m), (r), (v), (y), (dd) | Not Applicable |
|  | GCC 1.1(o) | Supplementing Sub-Clause GCC 1.1(o) The Employer is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. |
|  | GCC 1.1(w) | Supplementing Sub-Clause GCC 1.1(w) The Owner is: Power Grid Corporation of India Limited, `Saudamini’, Plot No.-2, Sector-29, Gurgaon (Haryana) - 122001. |
|  | GCC 1.1 (ee) | Supplementing Sub-Clause GCC 1.1(ee) Time for Completion: Sl. No.; Activities; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of:. 1; Package-1 for Proto type testing of in-house designed towers for 400 kV D/C (Quad) Jaypore-Jagdalpur Transmission line (with minimum capacity of 2100 mVA / Ckt at nominal voltage) associated with Inter-regional ER-WR Interconnection under TBCB: Package-1 is for proto testing of following three towers [ Complete in all respect as per BoQ/TS] SN; Type of Tower for which in-house design & testing is required. 1; 400 kV D/C Tower Type DA (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. 2; 400 kV D/C Tower Type DB (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. 3; 400 kV D/C Tower Type DC(WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. Spec.No.CC/NT/S-TWT/DOM/A04/23/00904 Note: Bidders should indicate schedule for (a) Development of Structural and shop drawings; (b)Fabrication and inspection of proto towers; & (c) Testing of proto tower.; 05 (Five) Months. 2.; Package-2 for Proto type testing of in-house designed towers for 400 kV D/C (Quad) Jaypore-Jagdalpur Transmission line (with minimum capacity of 2100 mVA / Ckt at nominal voltage) associated with Inter-regional ER-WR Interconnection under TBCB: Package-2 is for proto testing of following 02 towers [ complete in all respect as per BOQ/TS]. SN; Type of Tower for which in-house design & testing is required. 1; 400 kV D/C Tower Type DD45 (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability. 2; 400 kV D/C Tower Type DD60 (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability. Spec.No:CC/NT/S-TWT/DOM/A04/23/00905; 05 (Five) Months. |
|  | GCC 2.1.1 | Replace GCC 2.1.1 with the following: The Contracts to be entered into with the successful Bidder shall be as under: Package-wise Single Contract covering complete scope of work as per BOQ/Technical specification including all Plants & Equipments, Services etc., shall be entered with the Contractor. |
|  | GCC 2.1.2 | Not applicable. |
|  | GCC 2.9 | Not applicable. |
|  | GCC 3.1 | Replace GCC 3.1 with the following: Unless otherwise expressly limited in the Technical Specifications, the Contractor's obligation shall include the provision of all Plant and Equipment and the performance of all Services required for the design, the manufacture (including procurement, quality assurance, construction, erection on test bed) of the Plant and Equipment and the completion and performance testing of the facilities in accordance with the plans, procedures, specifications, drawings, codes and any other documents as specified in the Technical specifications. ……………. |
|  | GCC 3.3,3.4, 3.5 | Not applicable. |
|  | GCC 4.1 | Replace GCC 4.1 with following: 4.1 Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 21.2 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. |
|  | GCC 5.2 | Replace GCC 5.2 with following: The Contractor confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Facilities provided by the Employer, and on the basis of information that the Contractor could have obtained relating to the Facilities as of the date twenty-eight (28) days prior to bid submission. The Contractor acknowledges that any failure to acquaint itself with all such data and information shall not relieve its responsibility for properly estimating the difficulty or cost of successfully performing the Facilities. |
|  | GCC 5.7 | Insert a new clause GCC 5.7 as follows: Vide Notification dated 8th May 2017 and its revision dated 29th May 2019 by Ministry of Steel has published “ Policy for providing preference to Domestically Manufactured Iron & Steel Products in Government Procurement”. The Contractor shall comply with the guidelines specified in the policy including subsequent amendments/ modifications, if any. Accordingly, the Contractor shall be required to provide a value- addition certificate on half-yearly basis (Sep 30 and Mar 31), duly certified by the Statutory Auditors of the Domestic Manufacturer, that the claims of value-addition made for the product during the preceding 6 months are in accordance with the Policy. Such certificate shall be filed within 60 days of commencement of each half year, to the respective executing Region of POWERGRID and shall continue to be filed till the completion of supply of the said products. Further, if the Domestic manufacturer from whom the Contractor had proposed to source the Iron & Steel products is changed during execution of the Contract, the Contractor shall furnish (i) authorization certificate, if applicable, (ii) affidavit of self-certification and (iii) value- addition certificate from the new Domestic manufacturer. Violation to minimum prescribed domestic value addition or misrepresentation of facts by the bidder in this regard shall be dealt in line with provisions of the Integrity Pact. |
|  | GCC 6.2, 6.5, 6.6 | Not Applicable |
|  | GCC 7.1 | Supplementing GCC Clause 7.1 - Prices of all work and materials covered under the scope of this specification shall be firm and not subjected to any Price Adjustment. - Notwithstanding the break-up of the contract price, the contract shall, at all times, be construed as a single source responsibility contract and any breach in any part of this contract shall be treated as a breach of the entire contract. - The contract price is based on tentative weight of towers and the no. of tests to be carried out as indicated in the Bid. However, the actual payment shall be made on the basis of actual weight of fabricated tower parts, bolts & nuts and actual nos. of tests carried out on the basis of unit rates. |
|  | GCC 9.2 | Not applicable. |
|  | GCC 9.3.1 | Replace First Para of GCC 9.3.1 with following: The Contractor shall, within twenty-eight (28) days of the notification of award, provide a performance security for the due performance of the Contract in the amount equivalent to Ten percent (10%) of the Contract Price, with a validity upto ninety (90) days beyond the completion of complete scope of tower testing for respective packages. The same shall be extended by the Contractor time to time till ninety (90) days beyond the actual completion of complete scope of tower testing for respective packages, as may be required under the Contract. |
|  | GCC 9.3.1.2 (b) | Replace the Clause reference GCC 9.3.1.1(b) appearing in second line with Clause GCC 9.3.1.2(a). |
|  | GCC 9.3.2 | Replace Sub-Clause GCC 9.3.2 The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer as stipulated in SCC or in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergrid.in. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–CC@. Name of Depositor; Name of the Contractor/Collaborator/Tower manufacturer/Licensor etc.. Vendor Code, if applicable; POWERGRID vendor code of the Contractor Collaborator/Tower manufacturer/Licensor etc., if existing. Payment Remarks; Performance Security for ………….. [enter the name of the contract and last four digits of the CA number]. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. |
|  | GCC 9.3.3 | Replace existing GCC clause 9.3.3 with following: Reduction in the security pro rata to the Contract Price of any part of the Facilities is not admissible. |
|  | GCC 9.3.4 | Not applicable. |
|  | GCC 9.3.5 | Add new sub Clause GCC 9.3.5 No interest shall be payable by the Employer on the performance Security. |
|  | GCC 9.3.6 | Add new sub Clause GCC 9.3.6 During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque/ online payment through POWERGRID ONLINE PAYMENT UTILITY, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 9.4 | Replace Clause GCC 9.4 in SCC Issuing Banks The Bank Guarantee for Advance Payment Security and Performance Security are to be provided by the Contractor, which should be issued either: (a) by a Public Sector Bank located in India, or (b) a scheduled Indian Bank having paid up capital (net of any accumulated losses) of Rs. 1,000 Million or above (the latest annual report of the Bank should support compliance of capital adequacy ratio requirement), or (c) by a foreign bank or a subsidiary of a foreign bank, acceptable to the Employer, with overall international corporate rating or rating of long term debt not less than A- (A minus) or equivalent by a reputed rating agency. Further, the Bank Guarantee should be confirmed by either (i) its corresponding bank located in India; or (ii) a Public Sector Bank located in India; or (iii) a scheduled commercial private bank located in India as per para (b) above. |
|  | GCC 9.4 | Supplementing GCC Clause 9.4 with the following The contractor has the option to submit BG (towards Advance Payment Security and Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Advance Payment Security and Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; IFSC Code; POWERGRID Current A/c No.. State Bank of India, 4th & 5th Floor, Parsvnath Capital Tower, Bhai Veer Singh Marg, Gole Market, New Delhi - 110001; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram; ICIC0002451; 000705002702. Note: Any one of the above account details can be used for the issuance of Bank Guarantee using SFMS Platform. In case of Bank Guarantee (towards Advance Payment Security and Performance Security) verification through SFMS facility of ICICI Bank, the applicant has to provide a unique identifier of POWERGRID to the issuing bank. This unique identifier needs to be incorporated by the issuing bank in Field 7037of the IFIN 760 COV/ IFIN 767 COV while transmitting these messages to the Beneficiary Bank through SFMS. The unique identifier of POWERGRID is PGCIL50948846. In addition to the above, the Bank Guarantee (towards Advance Payment Security and Performance Security) should be submitted in the Physical form as specified in GCC Clause 9. |
|  | GCC 9.5 | Not applicable. |
|  | GCC 10.3 | Not applicable |
|  | GCC 10.4 | Replace GCC 10.4 as follows: The price for supply of services are excluding GST, if any, payable. The GST will be reimbursable (along with subsequent variation if any), by the Employer on the supplies made by the Contractor but limited to the tax liability on the transaction between the Employer and the Contractor. |
|  | GCC 11 | Supplementing GCC Clause 11 as follows: Notwithstanding the provisions of Clause GCC 11.1 above, the copyright in all drawings, documents and other materials containing data and information for design(s) which have been developed by the Contractor or by any third party under the Contract shall remain vested in the Employer, for the material and in the manner as detailed in the Technical Specification, Vol-II of the Bidding Documents. |
|  | GCC 12.2 | Replace GCC 12.2 with the following: The Contractor shall not use such documents, data and other information received from the Employer for any purpose other than the design, procurement of Plant and Equipment, construction or such other work and services as are required for the performance of the Contract. |
|  | GCC 13.2 | Replace the following in GCC 13.2: “Contractor‟s Representative & Construction Manager” by “ Contractor’s Representative” |
|  | GCC 13.2.4 | Not applicable. |
|  | GCC 15.1 | Replace GCC 15.1 as follows: The corresponding Appendix (List of Approved Subcontractors) to the Contract Agreement specifies major items of supply or services and a list of approved Subcontractors against each item, including vendors. Insofar as no Subcontractors are listed against any such item, the Contractor shall prepare a list of Subcontractors for such item for inclusion in such list. The Contractor may from time to time propose any addition to or deletion from any such list. The Contractor shall submit any such list or any modification thereto to the Employer for its approval in sufficient time so as not to impede the progress of work on the Facilities. Such approval by the Employer for any of the Subcontractors shall not relieve the Contractor from any of its obligations, duties or responsibilities under the Contract. Further, the Contractor shall not subcontract any work to a subcontractor/sub vendor from such countries which shares a land border with India unless such subcontractor/sub vendor fulfills all requirement in regard to ‘Bidder from a country which shares a land border with India’ as per ITB clause 2.1. This restriction on subcontracting shall not be applicable for procurement of raw materials, components, sub-assemblies etc. However, in case of finished goods procured directly/indirectly from the vendors from the countries sharing land border with India, such vendor will be required to be registered with the Competent Authority. |
|  | GCC 15.5 | Adding New sub clause GCC 15.5 The Contractor shall sign the Integrity Pact with its Subcontractors before employing under the Contract. |
|  | GCC 18 | Replace GCC 18 as follows: 18.0 Services The Contractor shall provide all the Services as brought out in Contract Agreement. Further, while providing the Services, the Contractor shall follow and comply with all the Statutory Laws including Labour Laws, Safety Regulations etc including safety of Employer’s representative for the subject work. It shall be the sole responsibility of the Contractor to adhere to Laws and Statutory requirement in connection of delivering Services to the Employer. The Employer, shall not be held liable in any way whatsoever, for the default of Contractor in this regard. |
|  | GCC 20 | Replace GCC 20 with the following: 20. Completion of the Facilities/ Tower Testing 20.1 Completion of the Facilities / Tower Testing As soon as the Services, in the opinion of the Contractor, has been completed as specified in the Technical Specifications read in conjunction with the Service Instruction, the Contractor shall so notify the Employer in writing. The Employer after verification shall notify the Contractor of deficiencies, if any. The Contractor shall make good of the deficiencies and shall so notify the Employer in writing. The Employer after verification shall issue to the Contractor an Service Acceptance Certificate verifying the date on which the supply of Services have been completed and accepted. Such certificate shall not relieve the Contractor of any of his obligations which otherwise survive, by the terms and conditions of Contract (read in conjunction with Service Instruction) after issue of such certificate. |
|  | GCC 21.1 | Supplementing the Clause GCC 21.1 with the following: Time for Completion: Sl. No.; Activities; Duration in months from the effective date of Contract. Taking Over by the Employer upon successful Completion of:. 1; Package-1 for Proto type testing of in-house designed towers for 400 kV D/C (Quad) Jaypore-Jagdalpur Transmission line (with minimum capacity of 2100 mVA / Ckt at nominal voltage) associated with Inter-regional ER-WR Interconnection under TBCB: Package-1 is for proto testing of following three towers [ Complete in all respect as per BoQ/TS] SN; Type of Tower for which in-house design & testing is required. 1; 400 kV D/C Tower Type DA (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. 2; 400 kV D/C Tower Type DB (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. 3; 400 kV D/C Tower Type DC(WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability 2. Spec.No.CC/NT/S-TWT/DOM/A04/23/00904 Note: Bidders should indicate schedule for (a) Development of Structural and shop drawings; (b)Fabrication and inspection of proto towers; & (c) Testing of proto tower.; 05 (Five) Months. 2.; Package-2 for Proto type testing of in-house designed towers for 400 kV D/C (Quad) Jaypore-Jagdalpur Transmission line (with minimum capacity of 2100 mVA / Ckt at nominal voltage) associated with Inter-regional ER-WR Interconnection under TBCB: Package-2 is for proto testing of following 02 towers [ complete in all respect as per BOQ/TS]. SN; Type of Tower for which in-house design & testing is required. 1; 400 kV D/C Tower Type DD45 (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability. 2; 400 kV D/C Tower Type DD60 (WZ-3, WITH QUAD AL 59 MOOSE Conductor) and Reliability. Spec.No:CC/NT/S-TWT/DOM/A04/23/00905; 05 (Five) Months. Note: Bidders should indicate schedule for (a) Development of Structural and shop drawings; (b)Fabrication and inspection of proto towers; & (c) Testing of proto tower. |
|  | GCC 21.2 | Replace GCC 21.2 with the following: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to 0.05% (zero point zero five percent) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damage which will be suffered by the Employer for default on the part of the Contractor and said amount will be payable without proof of actual loss or damage caused by such default. The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. |
|  | GCC 22,23,24 & 27 | Not applicable. |
|  | GCC 30 | Replace the existing Provision GCC 30 as below: Contractor shall be fully responsible for maintaining all statutory Insurances at their own cost. |
|  | GCC 33.2.3 | Supplementing Sub-Clause GCC 33.2.3 The quantity variation limit for the subject package(s) shall be as below: - Quantity variation provision( positive/negative ) has been kept one (1) towers for each contract. The quantity variation however should be exercised within pendency of original contract. - The quantities in tower testing BOQ are normally tentative based on the design of towers finalized. Tower testing being a R&D work , failure may happen during testing and few existing members may have to be replaced with newly fabricated tower members. This additional fabrication/election/dismantling shall also be payable to contractor due to which quantity variation can take place. The clause for quantity variation (+ ve or – ve) (without any limit subject to actuals) of individual items in the tender document without any change in unit price/ Rate(s) or other terms and conditions. |
|  | GCC 39.6 | Replace the existing Provision GCC 39.6 as below: 39.6 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute/ difference (other than those related to taxation matters) between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018 and DPE OM No. DPE-GM-05/0003/2019-FTS-10937 dated 20.02.2020. The decision through AMRCD will be final and binding on all the concerned. 39.7 During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. |
|  | Appendix-I to SCC | Enclosed herewith |

----- End of Section-V (SCC) ----