SECTION – V

SPECIAL CONDITIONS OF CONTRACT (SCC)

Construction of Transformer and Reactor repair facility at ±500kV HVDC Bhiwadi terminal

SPECIAL CONDITIONS OF CONTRACT (SCC)

The following bid specific data for the Goods/Services to be procured shall amend and/or supplement the provisions in the General Conditions of Contract (GCC)

| Sl. No. | GCC Clause Ref. No. | Amendment/Supplement to GCC |
| --- | --- | --- |
|  | GCC 1.1(n) & (v) | Supplementing Sub-Clause GCC 1.1(n) & (v) The Owner/ Employer is: Power Grid Corporation of India Limited Northern Region –I, Regional Headquarter, SCO Bay No. 5 to 10, Sector 16A, Faridabad (Haryana), Pin-121002 |
|  | GCC 1.1 (e) & 1.1 (dd) | Supplementing Sub-Clause GCC 1.1(ee) Time for Completion: Sl. No.; Activities; Duration from the effective date of Contract. 1; Taking Over by the Employer upon successful Completion of: Construction of Transformer and Reactor repair facility at ±500kV HVDC Bhiwadi terminal; Fourteen (14) Months. |
|  | General | Addition/ Deletion / Substitutions to the different section of the Bidding Documents - The words ‘Bid’ or ‘Offer’ shall have the same meaning as the word ‘Tender’. These words have been used interchangeably and shall carry the same meaning. - The words ‘Bidding Documents’ or ‘NIT Documents’ shall have the same meaning as the words ‘Tender Documents’. These words / expressions have been used interchangeably and shall carry the same meaning. The word ‘Notice Inviting Tender’ shall have the same meaning as the word ‘Invitation for Bids’. These works have been used interchangeably and shall carry the same meaning. |
|  | GCC 3.2 | Add new GCC Sub clause 3.2 as under: The work shall be strictly carried out as per POWERGRID’s Technical Specifications for the subject package & as per terms & conditions mentioned in the bidding documents inter-alia including drawings provided by POWERGRID, if any, to the successful Bidder. The Contractor at his cost shall arrange, secure and maintain all insurance as may be pertinent to the works and obligatory in terms of law against all perils and the responsibility to maintain adequate insurance coverage at all time during the period of contract shall be of the Contractor alone. The Contractor’s failure in this regard shall not relieve him of any of his contractual responsibilities and obligations. The perils required to be covered under the insurance shall include all risks, but not limited to fire and allied risks, miscellaneous accidents, workmen compensation risks, loss or damage in transit, theft, pilferage, riot and strikes and malicious damages, civil commotions, weather conditions, accidents of all kinds et. The Contractor shall be responsible for the safety and security of employees of the Contractor and his sub-contractors throughout execution of the works. All costs on account of insurance liabilities covered under the Contract will be on Contractor’s account and will be included in the Contract Price. Materials and components not specifically stated in the various documents forming part of the Contract but which are necessary for completion of works shall be deemed to be included in the scope. All such materials and components shall be arranged and transported by the Contractor at his cost and expense. |
|  | GCC 4 | Replace the para with the following: 4. Time for Commencement and Completion 4.1 Time for Completion is the essence of Contract. The Contractor shall commence work on the Facilities from the Effective Date of Contract and without prejudice to GCC Sub-Clause 38.1 hereof, the Contractor shall thereafter proceed with the Facilities in accordance with the time schedule specified in the corresponding Appendix – 4 (Time Schedule) to the Contract Agreement. 4.2 The Contractor shall attain Completion of the Facilities (or of a part where a separate time for Completion of such part is specified in the Contract) within the time stated under Time for Completion or within such extended time to which the Contractor shall be entitled under GCC Clause 18 hereof. |
|  | GCC 8.2 | Stands deleted as Advance is not admissible under the subject package |
|  | GCC 8.3.1 | Replace GCC clause 8.3.1 with the following: Bank Guarantee towards performance security in the amount equivalent to Ten percent (10%) of the contract price, with a validity upto ninety (90) days beyond the Defect Liability Period shall be submitted within 28 days of the issuance of NOA/LOA. The same shall be extended by the Supplier time to time till ninety (90) days beyond the actual Defect Liability Period, as may be required under the Contract. The original CPG(s) shall be released by the POWERGRID after successful completion of Defect Liability/Warranty period. |
|  | GCC 8.3.1.2 (d) | Replace Sub-Clause GCC 8.3.1.2(d) In case the Contractor fails to submit the performance security within 90 days of the Notification of Award, the Employer, without prejudice to any other rights or remedies it may possess under the Contract, may consider the bid submitted by the Contractor in future packages as non-responsive in line with ITB 13.6 and/or may terminate the Contract forthwith pursuant to GCC Clause 17. |
|  | GCC 8.3.1.5 | Add GCC Clause 8.3.1.5 8.3.1.5 Apart from the performance security (ies) to be furnished as per Clause GCC 8.3.1 above, additional performance securities, as specified in the Bidding Documents, shall be arranged and furnished by the Contractor at any time after the Notification of Award. The submission of these performance securities to the Employer shall, however, be one of the conditions precedent for release of payment (other than Initial/Mobilization advance) due against such equipment/ works for which the said performance security is required to be submitted. |
|  | GCC 8.3.2 | Replace the existing provision with the following: The performance security shall, at the contractor’s option, be in the form of a crossed bank draft/pay order /banker certified cheque in favour of Employer as stipulated in SCC or in the Form of unconditional Bank Guarantee attached hereto in the Section VI - Sample Forms and Procedures. Alternatively, if performance security is to be submitted in favor of POWERGRID, the same can be submitted as online payment through POWERGRID ONLINE PAYMENT UTILITY- https://epay.powergrid.in, a link of which is provided on the POWERGRID website www.powergrid.in. While making online payment towards performance security, the bidder shall choose Segment as “Suppliers” and fill in details as follows: Payment Category; Performance Security. Sub-category; Performance Security Payment–NR1. Name of Depositor; Name of the Contractor. Vendor Code, if applicable; POWERGRID vendor code of the Contractor. Payment Remarks; Performance Security for Construction of Transformer and Reactor repair facility at ±500kV HVDC Bhiwadi terminal. The copy of ‘Online Payment Acknowledgement – Suppliers’ generated subsequent to the payment shall be submitted by the Contractor. The online payment facility shall be for payment in Indian Rupees only. No interest shall be payable by the Employer/Owner on the Performance Security.. |
|  | GCC 8.3.5 | Replace the existing provision with the following: Reduction in the security pro rata to the Contract Price of any part of the Facilities is not admissible. However, if the Defects Liability Period has been extended on any part of the Facilities pursuant to GCC Clause 39/40 hereof, the Contractor shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Contractor immediately after its expiration, provided, however, that if the Contractor pursuant to GCC Sub-Clause 40, is liable for an extended warranty obligation, the performance security shall be reduced to Ten percent (10%) of the value of the component covered by the extended warranty. |
|  | GCC 8.3.7 | Add the new GCC sub-clause 8.3.7 as per following: During execution of contract the Contractor, after submission of Performance Security in form of a crossed bank draft/pay order /banker certified cheque, may opt to furnish the Performance Security in form of bank guarantee for the same amount and as per same terms of the Contract. On acceptance by the Employer of Performance Security submitted in the form of Bank Guarantee following receipt of confirmation from the issuing Bank, the said amount shall be refunded. |
|  | GCC 8.4 | Replace the existing provision with the following: Issuing Banks The Bank Guarantee for Advance Payment Security and Performance Security are to be provided by the Contractor, which should be issued either : (a) by a Public Sector Bank located in India, or (b) a scheduled Indian Bank having paid up capital (net of any accumulated losses) of Rs. 1,000 Million or above (the latest annual report of the Bank should support compliance of capital adequacy ratio requirement) as per attached list only [List is placed at Annexure-I to Section-V (SCC)], or (c) by a foreign bank or a subsidiary of a foreign bank, acceptable to the Employer, with overall international corporate rating or rating of long term debt not less than A- (A minus) or equivalent by a reputed rating agency. Further, the Bank Guarantee should be confirmed by either (i) its corresponding bank located in India; or (ii) a Public Sector Bank located in India; or (iii) a scheduled commercial private bank located in India as per the attached list only [List is placed at Annexure-I to Section-V (SCC)]. The contractor has the option to submit BG (towards Advance Payment Security and Performance Security) using SFMS Platform. The Account details of POWERGRID for the purpose of Bank Guarantee (towards Advance Payment Security and Performance Security) to be issued using SFMS Platform are as given below: Name of the Bank and Address; IFSC Code; POWERGRID Current A/c No.. State Bank of India, 4th & 5th Floor, Parsvnath Capital Tower, Bhai Veer Singh Marg, Gole Market, New Delhi - 110001; SBIN0017313; 10813608670. ICICI Bank, Unit No. 01, Solitaire Plaza, DLF Phase III, M.G. Road, Gurugram; ICIC0002451; 000705002702. Note: Any one of the above account details can be used for the issuance of Bank Guarantee using SFMS Platform. In case of Bank Guarantee (towards Advance Payment Security and Performance Security) verification through SFMS facility of ICICI Bank, the applicant has to provide a unique identifier of POWERGRID to the issuing bank. This unique identifier needs to be incorporated by the issuing bank in Field 7037of the IFIN 760 COV/ IFIN 767 COV while transmitting these messages to the Beneficiary Bank through SFMS. The unique identifier of POWERGRID is PGCIL50948846. In addition to the above, the Bank Guarantee (towards Advance Payment Security and Performance Security) should be submitted in the Physical form as specified in GCC Clause 8. |
|  | GCC 11.1 | Supplementing Sub-Clause GCC 11.1 The various field and laboratory tests involved as per the Quality Plan/ Technical Specifications/ directions of Engineer-in-charge are to be carried out by the successful Bidder (contractor) at his own cost and no additional payment shall be considered on this account. The Bidders should take into account his aspect while submitting their offers. |
|  | GCC Clause 15 | Supplement the GCC Clause 15.2 (vi) with the following: During execution of the contract, POWERGRID reserves the right to increase or decrease the quantity of individual item upto any extent. The overall limit of Quantity variation in the contract shall be upto (+/-) 25% (Twenty Five Percent) of the Contract Price and there will not be any variation limit for individual items of the Contract. Thus, individual items may vary to any extent. |
|  | GCC 17.2.1(c) | Replace GCC Clause 17.2.1 (c) with the following: If the Contractor, in the judgment of the Employer has engaged in corrupt or fraudulent practices in competing for or in executing the Contract. For the purpose of this Sub-Clause: “Corrupt Practice” means offering, giving, receiving, or soliciting anything of value to influence the action of Employer official(s) in the procurement process. “Fraudulent Practice‟” means any act including suppression/ misrepresentation of facts, submissions of forged/ false documents, making false declarations etc. that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial gain or benefit, or to avoid an obligation, or to influence procurement process to the detriment of interest of the Employer, including collusive practices among bidders (prior to or after bid submission) to establish bid prices at artificial, non-competitive levels and to deprive Employer of the benefits of competitive prices. “collusive practice” shall also include an arrangement between two or more parties designed to achieve an illegitimate purpose to the detriment of interest of Employer. “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; “Obstructive practice” means (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede investigation into allegations of a corrupt, fraudulent, coercive, or collusive practice; and/ or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation, or (bb) acts intended to materially impede the exercise of the contractual rights or audit or access to information. In persuasions of its policy, the Employer will sanction a firm or individual, including declaring ineligible, either indefinitely or for a stated period of time, to be awarded a contract if it at any time determines that the firm has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for, or in executing, a contract. |
|  | GCC 20.6 | Replace the existing provision with the following: As brought in clause 6.0 and subject to as hereinafter provided all charges on account of GST on materials obtained for the works from any source shall be borne by the Contractor. The liability of the Employer shall be limited to reimbursement of GST on the supply of services made by the Contractor. The Input Tax Credit (ITC) available, if any, under GST as per the relevant Government laws wherever applicable has, however, been taken into account by the Contractor. |
|  | GCC 22.3.1 | Supplementing Sub-Clause GCC 22.3.1 Notwithstanding the above, the Contractor shall furnish to the Employer the details/documents evidencing the Contractor’s compliance to the laws applicable to establishments engaged in building and other construction works, as may be sought by the Employer. In particular the Contractor shall submit quarterly certificate regarding compliance in respect of provisions of Employees’ Provident Fund and Misc. Provisions Act 1952 to the Employer. For this purpose, the Contractor as well as its Sub-Contractor(s) should have Provident Fund Code Number and all the workers deployed by the Contractor or Sub-Contractor must be enrolled as members of Provident Fund having an Universal Account Number (UAN). |
|  | GCC 22.6 | Supplementing Sub-Clause GCC 22.6 Labour having “Recognition of Prior Learning”(RPL) Certification (under Pradhan Mantri Kaushal Vikas Yojana(PMKVY)) can also be employed by the Contractor. |
|  | GCC 22.9 (a) | Replace GCC 22.9 (a) with the following: (a) Employee’s Compensation Act 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment. |
|  | GCC 23 | Replace the existing provision with the Appendix -II to SCC. |
|  | GCC 31.2 | Add following new clause at GCC 31.2 PROGRESS REPORT During execution of the Contract, the Contractor shall furnish monthly Progress Report to POWERGRID in a format as specified by the Owner or the Engineer-in-Charge indicating the progress achieved during the month, and total progress upto the month against the scheduled, reasons for delay, if any, and anticipated completion dates in respect of activities covered in the programme/schedules referred to above, if called for by the Owner or the Engineer-in-Charge resources data in a specified format and within a time schedule. The Contractor shall also furnish any other information that is necessary to ascertain progress, if called for by the Engineer-in-Charge. |
|  | GCC 31.3 | Add following new clause at GCC 31.3 CO-OPERATION WITH OTHER AGENCIES The Contractor shall attend at his cost all the meeting with the Engineer-in-Charge and other Sub-Contractors for the Contract. The Contractor shall attend such meetings as and when required and fully co-operate, with such persons and agencies involved. |
|  | GCC 32.4 | Add following new clause at GCC 32.4 The work will also be subjected to the inspection by the Chief Technical Examiner of the Chief Vigilance Commissioner (CVC) and the Contractor shall make necessary arrangements whenever required for this inspection without any additional cost to the Owner. |
|  | GCC 38.0 | Replace the existing provision with the following: Liquidated Damages: If the Contractor fails to comply with the Time for Completion in accordance with Clause GCC 21 for the whole of the facilities, (or a part for which a separate time for completion is agreed) then the Contractor shall pay to the Employer a sum equivalent to Zero Point Zero Five Percent (0.05%) of the Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed) as liquidated damages for such default and not as a penalty, without prejudice to the Employer's other remedies under the Contract, for each day which shall elapse between the relevant Time for Completion and the date stated in Taking Over Certificate of the whole of the Works (or a part for which a separate time for completion is agreed) subject to the limit of Five percent (5%) of Contract Price for the whole of the facilities, (or a part for which a separate time for completion is agreed). The parties agree that the sum specified above is not a penalty but a genuine pre-estimate of the loss/damages which will be suffered by the employer for default on the part of the contractor and said amount will be payable without proof of actual loss or damage caused by such default The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any monies due or to become due to the Contractor. The payment or deduction of such damages shall not relieve the Contractor from his obligation to complete the Works, or from any other of his obligations and liabilities under the Contract. |
|  | GCC 40.0 | Replace first para of GCC clause 40.0 Defect liability period shall be Twelve (12) Months from the certified date of completion and handing over of the works |
|  | GCC 44 | Supplementing GCC 44.1 as follows: Further, the Contractor shall not subcontract any work to a subcontractor/sub vendor from such countries which shares a land border with India unless such subcontractor/sub vendor fulfills all requirement in regard to ‘Bidder from a country which shares a land border with India’ as per ITB clause 2.1. |
|  | GCC 44.2 | Add following new clause at GCC 44.2 The Contractor shall furnish the details of items, components, raw materials, services etc. procured from MSEs and consumed for completion of scope of works under the contract. The details shall be furnished as per the format enclosed at Section VI, Forms, Volume-I of the bidding documents at the time of raising bills for payment against the supplies made/works done. |
|  | GCC 48.3 | Add following new clause at GCC 48.3 Risk and Cost During the period of construction and also during defect liability period, if the contractor fails to rectify any defect pointed out to him, the same shall be got done by POWERGRID at the risk and cost of contractor and recovered from the Contract Performance Guarantee or any other amount payable to the Contractor. |
|  | GCC 55.0 | Supplementing Sub-Clause GCC 55.0 Price Basis: Price variation is applicable as per Appendix-2 Price Adjustment of Section-VI Sample Forms & Procedures of Volume-1 of bidding documents. |
|  | GCC 59 | Replace the existing provision with the following: 59.1 All disputes or differences in respect of which the decision, if any, of the Project Manager and/or the Head of the Implementing Authority has not become final or binding as aforesaid shall be settled by arbitration in the manner provided herein below: 59.2 The arbitration shall be conducted by a sole arbitrator in case the amount of claim is less than Rs. 25 Crore and by three member arbitral tribunal in case the amount of claim is greater than Rs. 25 Crore. Sole Arbitration The sole Arbitrator shall be chosen from a panel of empanelled Arbitrators maintained by POWERGRID. The same shall comprise of retired Judges and retired Senior executives of PSUs other than POWERGRID. Further, the choice of sole Arbitrator shall be governed by the amount of claim in the following manner: Sl no:; Claim amount; Work Experience/ Qualifications. 1; < Rs. 10 Crore; Sole arbitrator-Retired Senior Executives of PSUs other than POWERGRID/Retired Distt Judges/ High Court Judges.. 2; Rs.10 Crore- Rs.25 Crore; Sole arbitrator- Retired High Court/Supreme Court Judges. - In case of invocation of arbitration by POWERGRID, POWERGRID shall, within 30 days, send a list of names of 3 arbitrators from its list/database of Arbitrators and the contractor shall within the period of further 30 days select any one person to act as “Sole Arbitrator”, which will be confirmed by POWERGRID and matter will be referred to such appointed Arbitrator for further arbitration proceedings. - In case of invocation of arbitration by the Contractor, the Contractor shall request POWERGRID for its database of Arbitrators/ chose from the list of Arbitrators available on POWERGRID’s website, and the contractor shall, within 30 days, select any one Arbitrator from the above to act as “Sole Arbitrator”, which will be confirmed by POWERGRID within 30 days and matter will be referred to such appointed Arbitrator for further arbitration proceedings. If the parties fail to appoint sole arbitrator within sixty (60) days after receipt of a notice from the other party invoking Arbitration, the appointment of sole arbitrator shall be done by Courts as per the provisions of Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof. Three member arbitral tribunal The arbitration shall be conducted by three arbitrators, who are retired High Court/Supreme Court Judges, one each to be nominated by the Contractor and the Employer and the third to be appointed by both the arbitrators in accordance with the Indian Arbitration & conciliation Act. If either of the parties fails to appoint its arbitrator within sixty (60) days after receipt of a notice from the other party invoking the Arbitration clause, the arbitrator appointed by the party invoking the arbitration clause shall become the sole arbitrator to conduct the arbitration. In case of failure of the two arbitrators appointed by the parties to reach upon a consensus regarding appointment of presiding Arbitrator, within a period of 30 days from the appointment of the arbitrator appointed subsequently, the presiding arbitrator shall be appointed by Courts as per the provisions of Arbitration & conciliation Act. 59.3 The cost of arbitral proceedings inter-alia including the Arbitrators’ fee, logistics and any other charges shall be equally shared by both parties. In case of Sole Arbitrator, the fees to be paid to the sole Arbitrator shall be as per the terms of empanelment in POWERGRID whereas in case of the three member tribunal, the Arbitrator’s fees shall be as agreed upon by the Arbitrators in line with the Arbitration & Conciliation Act. However, the expenses incurred by each party in connection with the preparation, presentation, etc. of its proceedings shall be borne by each party itself. 59.4 The language of the arbitration proceedings and that of the documents and communications between the parties shall be English. The arbitration shall be conducted in accordance with the provisions of the Indian Arbitration and Conciliation Act, 1996 or any statutory modification thereof. The venue of arbitration shall be New Delhi. 59.5 The decision of the sole arbitrator/ the majority of the arbitrators, as the case may be, shall be final and binding upon the parties. In the event of any of the sole arbitrator/ any of the aforesaid arbitrators dying, neglecting, resigning or being unable to act for any reason, it will be lawful for the parties to nominate another sole arbitrator/ another arbitrator in place of the outgoing arbitrator. 59.6 Notwithstanding the above, in case the contractor is a Central Public Sector Enterprise (CPSE)/Government Organization or Department then the dispute or difference between the Employer and the Contractor shall be settled through Administrative Mechanism for Resolution of CPSEs Disputes (AMRCD) as mentioned in DPE OM No. 4(1)/2013-DPE(GM)/FTS-1835 dated 22.05.2018. The decision through AMRCD will be final and binding on all the concerned. 59.7 During settlement of disputes and arbitration proceedings, both parties shall be obliged to carry out their respective obligations under the contract. |
|  | GCC 62.0 | Add following new clause at GCC 62.0 APPROVAL OF STATUTARY/GOVT. BODIES The Contractor shall wherever required, obtain approval of the Statutory/ Govt./Local bodies for and on behalf of the Owner, during the construction and after completion of the project. However, the owner may also help the contractor to the extent of writing letters to the local bodies for expediting approval, if required. The fee/charges levied by the Statutory/Govt./Local bodies shall be reimbursed to the contractor on production of documentary proof. |
|  | GCC 63.0 | Add following new clause at GCC 63.0 Codes and Standards Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied after approval by the Employer. |
|  | Appendix-I to SCC | Enclosed herewith |

----- End of Section-V (SCC) ----