TECHNICAL SPECIFICATION

- General information and scope:

  - The Scope of contract includes collection of material CLR Polymer Insulator from POWERGRID Kota Store & work of replacement of CLR Long Rod polymer Insulators by New Composite Long Rod Polymer Insulators in 400 kV RAPP(C)–Chittorgarh/Kankroli D/C transmission line and deposition of replaced insulators/ unused insulators / other material back to POWERGRID Kota store. The address of store is given below:

Power Grid Corporation of India Ltd.

400/220 KV Sub-Station, Nanta, Near Karani Mata Temple

Kota – 324008

The Engineer-in-Charge for the subject package shall be DGM, Kota or his authorized representative.

  - The contractor will make necessary arrangement for:

    - Safe handling, loading, unloading, transportation of polymer insulators along with fitting/ materials from POWERGRID store to the site, during installation period.

    - Dismantling of CLR Polymer Insulators.

    - Necessary arrangement to send the dismantled insulators of each batch to POWERGRID Kota store as per Instruction of Engineer-In-Charge.

    - Installation of new Polymer Insulator Strings at identified locations along with other requisites like fixing of pin etc.

  - The contractor shall deploy at least 10 nos. of Gangs of skilled manpower for completion of the work in the allotted shutdown period. It shall also be ensured that each contract shall complete the replacement of insulator strings within the stipulated period.

  - The contractor shall arrange himself all tools and plants including discharge rod, equipment, safety appliances, consumables, transportation, store cum erection and transit insurance of insulators, labor and other items in sufficient quantity as may be required for executing the work at his own cost except store cum erection insurance (OSM insurance). The polymer insulators shall be provided by POWERGRID free of cost, which shall be issued from POWERGRID stores.

  - The exact number of locations/strings may vary depending upon the site conditions and shall be decided by Engineer-in-Charge.

  - Contractor should mobilize team for taking up the work immediately after getting the intimation of shutdown from POWERGRID. Further, the contractor should deploy maximum gangs so that the above work may be completed in minimum shutdown.

  - POWERGRID shall not pay any additional amount on account of:

    - Delay in Availability of shutdown on particular day due to system constraints.

    - Mobilization and execution of work in the shutdown period is the essence of the contract. However, in case shutdown on particular day is not available, POWERGRID will not pay any idling charges.

  - In case new polymer insulators get damaged during erection, the contractor will replace them at their own cost. If the contractor fails, the necessary amount shall be deducted from their bills as per POWERGRID norms.

  - Wastage / Breakage:

    - Wastage/ Breakage for old/ dismantled insulators:  5 % Wastage/ Breakage of the quantity of dismantled insulators shall be allowed. Recovery shall be made for damaged insulators exceeding 5 % of dismantled quantity. However, the damaged insulators shall be returned to POWERGRID store.

    - Wastage/ Breakage for new polymers insulators to be erected: No wastage/ breakage of the quantity of new polymers insulators to be erected shall be allowed. Recovery shall be made for damaged insulators of new polymer insulators.

- Mobilization and Execution:

  - Contractor shall ensure that while execution of the said work, no damage/ tempering is done to POWERGRID’s property like conductors and hardware fittings etc. It is the responsibility of the contractor to keep himself in contact with the Officer-In-charge regarding availability of shutdown/ date of execution of work. The contractor shall engage an adequate number of gangs to complete the entire scope of work in the allotted shutdown period.

  - While changing insulator, due care must be taken to maintain the existing sag, sufficient availability of T&P like torque wrench shall be used for fixing various line materials and components.

  - The Contractor will mobilize and deploy atleast 10 nos. of Gangs with supervisory staff. Each gang shall be equipped with the necessary T&P, PPE, Discharge rods etc., required for replacement of both suspension and tension insulator strings.

- Co-ordination:

  - The contractor must remain in constant touch with the Officer-In-charge regarding availability of required outages and to prepare an advance schedule thereof.

  - The contractor shall have to obtain a sub-station permit on a day-to-day basis which will be issued by a POWERGRID official for specific time duration to the authorized Engineer approved by Officer-In-Charge.

  - Failure to return the clear permit within the stipulated time will be viewed seriously. All care shall be taken to return the permit on time.

  - Any damage to POWERGRID’s property such as conductors, hardware, cross-arm, gantry, etc. will have to be rectified by replacing the damaged items by the contractor, otherwise, the cost will be recovered as per assessment of POWERGRID.

  - It may be noted that all the materials, tools & plants, PPE etc. required for the work are to be arranged by the contractor at his own cost. POWERGRID shall not in any way be held liable for any loss or damage to such materials, tools & plants.

- Safety:

  - All safety rules regarding human life and as per I.E. rules are to be observed by the contractor.

  - The contractor shall provide all the personal protective equipment like safety shoes, safety helmet, safety belt, fall arrestor, discharge rod, first aid box, emergency vehicle support etc. at his own cost to carry out the work in safe environment. No person shall be permitted to work on site without proper PPEs.

  - The work shall be carried out S/C lines in offline condition. While working on double circuit line, shutdown will be allowed on one circuit at a time and during the execution of the work. Another circuit shall remain in charged condition. The contractor shall take adequate safety measures to protect personnel from the potentially dangerous voltage built up due to electromagnetic and electrostatic coupling and contractor shall deploy suitable Gangs who have prior experience to carry out similar work.

  - The contractor shall ensure the use of safety apparatus by all labor/supervisors during execution of work. It is the responsivity of the contractor to complete the entire job without any accident / mishap.

  - Each site should be assigned with safety steward who shall be responsible for safety compliance during site works. POWERGRID shall bear no liability whatsoever towards any violations by the contractor in this regard. The contractor shall be responsible for safe execution of work adopting safe work procedures. Penalty shall be imposed by the POWERGRID Engineer-In-charge in case of non-compliance & recovered from the contractor.

- Guidelines for storage, condition monitoring and use of removed polymer insulators:

  - After removal of CLR Polymer insulators, insulators shall be transported to designated stores. Proper cushioning shall be provided to avoid damage to insulators during transportation.

  - Dismantled insulators shall be segregated in batches based on type, rating/make and year. Proper record of healthy & broken insulator in batched based on manufacturer, rating and month & year of manufacturing may be maintained, only after this, insulator shall be received in the POWERGRID store in unpacked condition.

- Work Schedule: Time is essence of contract. The entire work shall be completed in 10 days of shutdown of each 400 kV RAPP(C)–Chittorgarh Ckt & 400 kV RAPP(C)-Kankroli Ckt of the D/C transmission line within three (03) months.

- Regulatory Compliance: It shall be the responsibility of the contractor to comply with all statutory obligations under various enactments applicable to the contract. The agency shall be responsible to secure compliance with all Central & State Government laws as well as Rules, Regulations, Byelaws and other of the local authorities and statutory bodies as may be in force from time to time as applicable. The agency shall also be responsible for giving the required notice to any statutory or local bodies as required by law and obtain all requisite license/ permission as applicable to the agency as required for carrying out the work envisaged in the contract. POWERGRID shall bear no liability whatsoever towards any violations by the agency in this regard.

- Labor Laws:  The contractor shall comply with all labour laws applicable to workmen engaged by them to carrying out work and POWERGRID shall bear no liability whatsoever towards any violations by the agency in this regard.

- Labor License: The contractor shall take the required labour license etc. from the concerned Labour Department before start of the work if not taken earlier. The contractor at his own cost shall bear all the charges pertain to obtain the Labour License for execution of the work. POWERGRID shall not reimburse any amount nor been any liability to such accounts.

- The contractor must submit an electrical license for working on 765/400/220 kV transmission line.

- Insurance: All the deployed manpower by the contractor shall be fully insured through recognized Insurance Agencies against any type of electrical or any kind of hazards/ accidents for associated work. The agency at his own cost shall take adequate group insurance coverage under Workmen Compensation Act applicable to work on EHV electrical transmission lines maintenance work of his deployed manpower/ workers as required during the period of contract. Insurance premium shall be borne by the contractor itself. Any statutory requirement for executing this contract must be fulfilled by the contractor at his own cost. It shall be obligatory on the part of the contractor to provide a copy of the Insurance Policy to Engineer-In-Charge before deployment of personnel for the work.

- The contractor shall be responsible for payment to deployed workers/ manpower / highly skilled fitter as per minimum wages act applicable during entire duration of contract.

- SAFETY PLAN: The contractor must submit the duly signed safety plan along with all the annexures attached with it prior to start of work. The standard format has been attached for reference of the contractor.

- In case, it is found that agency has not complied with any statutory requirement under various labour laws /acts, POWERGRID being the principal employer shall make the payment and will recover the same with penalty and 15 % overhead charges from the due payment of the agency/contractor.

- Quantity Variation: During the execution of the contract, POWERGRID reserves the right to increase/decrease the quantities of items under the contract without any changes in unit price or other terms and conditions shall remain firm during the contractual period. Such variation shall not be subjected to any limitation of the individual items but the total variation in all such items under the contract shall be limited to (+/-) 25 % of the total contract price.

************************