


Amendment No-II dated 06/08/2026 to the Bidding Documents for 400kV GIS Extn Substation Package SS-157 (including Transformer) for (a) Extn. of 400kV Jeypore (POWERGRID) S/S under “Eastern Region Expansion Scheme-49”, (b) Extn. of 220/132kV Purnea (POWERGRID) S/S and (c) 1 x 200MVA, 220/132kV Transformer at Purnea (POWERGRID) S/S under “Eastern Region Expansion Scheme-52”; Specification No.: CC/NT/W-GIS/DOM/A06/26/07684
	

	Sl. No
	Clause Ref.
	Existing provision
	Amended provision

	1
	Appendix-I to Contract Agreement, Terms and Procedures of Payment, Section-VI, Vol-I of bidding documents

	1.1 Supply of Goods Portion

………………………………………….

B	Progressive Payment

Payment of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines::

……………………………………………….




C	Final Payment 

…………………………


	1.1 Supply of Goods Portion

………………………………………….

B	Progressive Payment#

Payment of the Ex-works price of Main Equipment/ materials (including Mandatory Spares) for each consignment shall be made progressively on certification of the Employer and on the basis of work performed using the following guidelines:

……………………………………………….

# Percentage of Progressive Payment shall be suitably adjusted in case of unbalanced/ front loaded bid as per the methodology brought-out at sl. No. 2.3 below.

C	Final Payment 

…………………………

2.3 	PAYMENT PROCEDURES IN CASE OF UNBALANCED / FRONT LOADED BID 

a. 	A bid shall be considered front loaded or unbalanced, if the Percentage of Services component (Installation, civil works, and F&I) to Total Contract Price (Supply component + Services component) quoted by the bidder is less than 19.62% 

b.	In the event of award on the bidder who have submitted unbalanced/front loaded bid, the Percentage of Progressive payment against Supply of Goods portion (refer sl. No. 1.1 above) shall be deferred by the Percentage by which the Percentage of the Services price components in the bid is less than the Percentage specified at 2.3a above in the bidding documents. No interest shall be payable on the deferred amount. The aforesaid deferred amount shall be paid on pro-rata basis upon completion of installation of the respective item and its certification by the Project Manager. 

No interest shall be payable on the deferred amount. 

Price Variation and Quantity variation shall continue to be governed by the unit price quoted by the bidder. 
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