| Sl No | Clause Ref. | Existing provision in the Bidding Documents | Amended provision |
| --- | --- | --- | --- |
| 1. | Clause 1.4(A) of Appendix-1: Terms and Procedures of Payment, Section-VI:Samples Forms and Procedures, Vol.-I of the Bidding Documents | 1.4 Supply of Services Portion: Price Component for Installation (including Civil Works) A. Survey Payment for survey shall be paid on pro-rata basis on completion of survey and approval of the same by the Employer. B. Interest Bearing Initial Advance (Optional) Ten percent (10%): B.1 1st Installment of 05% (Five)^^ of the total Installation price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid on Establishment of Contractor’s site offices, commencement of stub setting work & certification by Project Manager that satisfactory mobilisation for erection exists and on submission of (a) Proforma invoice(s),, (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. B.2 2ndInstallment of 05% (Five)^^ of the total Installation price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid on completion of 5 route kms of stringing & certification of the same by Project Manager and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. (d) A declaration by the contractor stating that 1st Installment (5%) of advance has been utilized against the mobilization works for the subject contract. C Interest bearing Advance for purchase of T&P^^: 02% (Two) of the total Installation price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be payable for purchase of T&P for Erection / Stringing (excluding TSE)/ Safety PPEs based on the requirements as specified in the Technical Specifications (Volume-II of the bidding document), on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. ……………………………………………………………………………………………………………………………… D Progressive Payment D1. Sixty Eight (68%)^^^^ (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid on completion of the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice. ^^^^ The percentage of this payment shall vary depending on whether the Contractor opts for various advances and inadmissibility of advance for the reason specified above. Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section – Sample Forms and Procedure and approval of the same by the Engineer In-Charge. D2. Ten percent (10%) of total Installation price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid in three equal parts, each on physical construction of 1/3rd of the Transmission Line section including liquidation of defects/deficiencies on the line section and certification of the same by Employer’s representative and on submission of GST invoice. E. Final Payment E1. 5% (five percent) of the erection price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid after successful commissioning of the transmission line. E2. 5% (five percent) of the erection price component (excluding the price component for survey and the amount linked to establishment of Facilities for Labour) shall be paid after issuance of Taking Over Certificate. ……………………………………………………………………..……………………………………………………….. | 1.4 Supply of Services Portion: Price Component for Installation (including Civil Works) A.1 Survey Payment for survey shall be paid on pro-rata basis on completion of survey and approval of the same by the Employer. A.2 Drawing Development and Tower Testing/Special Tower Testing Hundred percent (100%) of the Contract Price for a particular tower (under Activity Description: ‘Tower Testing’/’Special Tower Testing’ of Price Schedule-3) shall be paid after successful completion of all the activities of proto-type testing of that tower in line with the provision of the Bidding Documents and acceptance/ certification of the same by the Employer and on submission of GST invoice in respect of proto-type testing of that tower. Further, for release of above payment, it would be mandatory for Contractor to sign the Contract Agreement and to submit the Performance Securities in line with GCC Clause 9.3. B. Interest Bearing Initial Advance (Optional) Ten percent (10%): B.1 1st Installment of 05% (Five)^^ of the total Installation price component (excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour) shall be paid on Establishment of Contractor’s site offices, commencement of stub setting work & certification by Project Manager that satisfactory mobilisation for erection exists and on submission of (a) Proforma invoice(s),, (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. B.2 2ndInstallment of 05% (Five)^^ of the total Installation price component (excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour) shall be paid on completion of 5 route kms of stringing & certification of the same by Project Manager and on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. (d) A declaration by the contractor stating that 1st Installment (5%) of advance has been utilized against the mobilization works for the subject contract. C Interest bearing Advance for purchase of T&P^^: 02% (Two) of the total Installation price component ( excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour ) shall be payable for purchase of T&P for Erection / Stringing (excluding TSE)/ Safety PPEs based on the requirements as specified in the Technical Specifications (Volume-II of the bidding document), on submission of (a) Proforma invoice(s), (b) Advance Bank Guarantee for [{110% (one hundred ten percent) of the amount of Advance} Plus {amount of GST reimbursable on Advance as per the Proforma invoice}] in line with GCC Clause 9.2 and (c) Performance Securities in line with GCC Clause 9.3. ………………………………………………………………………………………………………………………………………… D Progressive Payment D1. Sixty Eight (68%)^^^^ ( excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour ) shall be paid on completion of the each of the items of Erection activity and on successful completion of quality check point involved in Installation, submission of the details of items, components, raw materials, services etc. procured/availed from MSEs, if any, for the preceding 6 months, in respect of all the contracts in the respective executing Region of POWERGRID as per format enclosed at Section VI, Forms, Volume-I of the bidding documents and certification by Employer’s representative and on submission of GST invoice. ^^^^ The percentage of this payment shall vary depending on whether the Contractor opts for various advances and inadmissibility of advance for the reason specified above. Further, one of the conditions for release of first progressive payment / subsequent payment shall be submission of ‘Safety Plan’ alongwith all requisite documents in line with GCC clause on Safety Precaution and proforma provided in this Section – Sample Forms and Procedure and approval of the same by the Engineer In-Charge. D2. Ten percent (10%) of total Installation price component ( excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour ) shall be paid in three equal parts, each on physical construction of 1/3rd of the Transmission Line section including liquidation of defects/deficiencies on the line section and certification of the same by Employer’s representative and on submission of GST invoice. E. Final Payment E1. 5% (five percent) of the erection price component ( excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour ) shall be paid after successful commissioning of the transmission line. E2. 5% (five percent) of the erection price component ( excluding the price component for survey, Drawing Development and Tower Testing/Special Tower Testing and the amount linked to establishment of Facilities for Labour) shall be paid after issuance of Taking Over Certificate. ……………………………………………………………………..………………………………………………………………….. |