## PBQ
Clarification No-I (Commercial) dated 11/07/2025 to the bidding documents for Tower Package TW03 for Zing-Zingbar to Sissu portion of ±350 KV HVDC Pang-Kaithal Transmission Line associated with Transmission system for evacuation of RE power from renewable energy parks in Leh (5 GW Leh-Kaithal transmission corridor). Spec No.: CC/NT/W-TW/DOM/A04/25/06315
Sl. No. | Volume/Section/ Clause No. | Description | Bidder’s Query | POWERGRID Reply
1 | BOQ Item | Tower testing is in the scope of the bidder. | As per BOQ/ Price Schedule, tower testing scope included in the bidder scope, but the payment terms for testing of tower is not available in tender. We request you to amend the same. | Refer Amendment No-II.
2 | General | Supply of conductor is in the scope of POWERGRID | As per BOQ/ Price Schedule, Conductor is supplied by POWERGRID, in this regard please provide the total cost of the Conductor for calculation of cost of “EAR (Erection All Risk Policy) Policy. | The data shall be shared with the successful bidder.
3 | Appendix-1 TERMS AND PROCEDURES OF PAYMENT |  | Advance Payment Terms: We request you to consider providing an interest-free advance and allow the submission of an insurance surety bond in place of a bank guarantee against the advance. | Refer Amendment No-I
4 | Appendix-1 TERMS AND PROCEDURES OF PAYMENT |  | As per Terms of Payment Interest Bearing Advance is to be given for the package, we request you to kindly provide Interest Free Advance for the subject package. Please confirm. Moreover, kindly modify the Advance Security to read as 100% instead of 110% of the amount of Advance. | The provisions of bidding documents shall remain unchanged.
5 | Appendix-1 TERMS AND PROCEDURES OF PAYMENT |  | As per the scope Testing of Towers is in scope, therefore we request you to kindly modify the payment terms of service portion to read as below. Drawing Development and Tower Testing Hundred percent (100%) of the Contract Price for a particular tower (under Activity Description: ‘Drawing Development and Tower Testing’ of Price Schedule-3) shall be paid after successful completion of all the activities of proto-type testing of that tower in line with the provision of the Bidding Documents and acceptance/ certification of the same by the Employer and on submission of GST invoice in respect of proto-type testing of that tower. Accordingly the other payment terms be modify as per the above terms of payment. Please confirm. | Refer Amendment No-II.
6 | Appendix-1 TERMS AND PROCEDURES OF PAYMENT | Twenty percent (20%) of the Ex-works price component for the fabricated tower parts/tower (including Bolts & Nuts) excluding all other materials shall be paid on completion of erection of complete tower and furnishing of necessary certificate by Employer’s representative. & The balance ten percent (10%) of the Ex-works price component for fabricated Tower/ Tower Parts (including Bolts & Nuts) excluding all other materials shall be paid on quarterly basis on erection and liquidation of defects/deficiencies of corresponding erected towers on prorata basis | It may please be noted that the line passes through mountainous terrain and experiences snowfall, resulting in a limited working window of only 3–4 months per year. Given this constraint, executing the line within the stipulated period will be challenging. Moreover, under the stipulated terms of payment, a significant portion of the cash flow will remain tied up, further impacting project execution. Therefore we propose following Terms of Payment for Supply portion. A. Interest Free Advance (Optional*): Ten percent (10%) of the total Ex-works price component of Fabricated Tower/ Tower Parts (including Bolts & Nuts) and all other materials shall be paid as an interest bearing initial advance. B. Eighty percent (80%)^ of the Ex-works price component of Fabricated Tower/ Tower Parts (including Bolts & Nuts) and all other materials, shall be paid on dispatch of the same and on submission of the documents C. The balance 10% (ten percent) of the Ex-works price component of Fabricated Tower/ Tower Parts (including Bolts & Nuts) and all other materials shall be paid pro-rata on receipt of Items at site | The provisions of bidding documents shall remain unchanged.